## FY16-17
FY 2016-17 Report
| Original Estimated Project Budget | Current Estimated Project Budget | FY 2016-17 Encumbered | Percent Encumbered | FY 2016-17 Expended | Percent Expended | Remaining Project Balance | Percent Remaining
December 2018 Quarterly Report
DPS 12/18 | 38778877 | 38778877 | 1674646 | 4.318% | 23039554 | 59.41% | 14064677 | 36.27%
TMD 12/18 | 19562500 | 19559181 | 169746 | 0.8679% | 19389435 | 99.13% | 0 | 0%
TPWD 12/18 | 91000000 | 89144982 | 15341481 | 17.21% | 73803501 | 82.79% | 0 | 0%
TDCJ 12/18 | 56393901 | 67380574 | 5132408 | 7.617% | 62248166 | 92.38% | 0 | 0%
TFC 12/18 | 217156348 | 217156348 | 106356568 | 48.98% | 91016461 | 41.91% | 19783319 | 9.11%
TXDOT 12/18 | 40127926 | 67198859 | 2965593 | 4.413% | 63218552 | 94.08% | 1014714 | 1.51%
Totals | 463019552 | 499218821 | 131640442 | 26.37% | 332715669 | 66.65% | 34862710 | 6.983%
September 2018 Quarterly Report
DPS 9/18 | 38778877 | 38778877 | 2011618 | 5.187% | 22492344 | 58% | 14274915 | 36.81% | *Reflects the updated (7/11/18) TFC revised numbers.
TMD 9/18 | 19562500 | 19559181 | 667864 | 3.415% | 18891317 | 96.59% | 0 | 0%
TPWD 9/18 | 91000000 | 89194804 | 18516437 | 20.76% | 70678367 | 79.24% | 0 | 0%
TDCJ 9/18 | 56393901 | 67380574 | 6712902 | 9.963% | 60667672 | 90.04% | 0 | 0%
TFC 9/18 | 217156348 | 217156348 | 114616725 | 52.78% | 82186973 | 37.85% | 20352650 | 9.372%
TXDOT 9/18 | 40127926 | 67198859 | 7456311 | 11.1% | 59742548 | 88.9% | 0 | 0%
Totals | 463019552 | 499268643 | 149981857 | 30.04% | 314659221 | 63.02% | 34627565 | 6.936%
June 2018 Quarterly Report *
DPS 6/18 | 38778877 | 38778877 | 1566407 | 4.039% | 22386298 | 57.73% | 14826172 | 38.23%
TMD 6/18 | 19562500 | 19559181 | 3598556 | 18.4% | 15960625 | 81.6% | 0 | 0%
TPWD 6/18 | 91000000 | 88983987 | 27114080 | 30.47% | 61869907 | 69.53% | 0 | 0%
TDCJ 6/18 | 56393901 | 67380574 | 12519249 | 18.58% | 54861325 | 81.42% | 0 | 0%
TFC 6/18 | 217156348 | 217156348 | 126972112 | 58.47% | 70598080 | 32.51% | 19586156 | 9.019%
TXDOT 6/18 | 40127926 | 67198859 | 10266705 | 15.28% | 56932154 | 84.72% | 0 | 0%
Totals | 463019552 | 499057826 | 182037109 | 36.48% | 282608389 | 56.63% | 34412328 | 6.895%
March 2018 QUARTERLY REPORT
DPS 3/18 | 38778877 | 38778877 | 1183806 | 3.053% | 21945945 | 56.59% | 15649126 | 40.35%
TMD 3/18 | 19562500 | 19559181 | 6929654 | 35.43% | 12629527 | 64.57% | 0 | 0%
TPWD 3/18 | 91000000 | 89289278 | 44689768 | 50.05% | 44599510 | 49.95% | 0 | 0%
TDCJ 3/18 | 56393901 | 67380574 | 20720163 | 30.75% | 46660411 | 69.25% | 0 | 0%
TFC 3/18 | 217156348 | 217156348 | 139594635 | 64.28% | 57299202 | 26.39% | 20262511 | 9.331%
TXDOT 3/18 | 40127926 | 67198859 | 15023652 | 22.36% | 52175207 | 77.64% | 0 | 0%
Totals | 463019552 | 499363117 | 228141678 | 45.69% | 235309802 | 47.12% | 35911637 | 7.191%
December 2017 QUARTERLY REPORT
DPS 12/17 | 38778877 | 38778877 | 2207682 | 5.693% | 20664113 | 53.29% | 15907082 | 41.02%
TMD 12/17 | 19562500 | 19559181 | 10213930 | 52.22% | 9345251 | 47.78% | 0 | 0%
TPWD 12/17 | 91000000 | 89301999 | 59714941 | 66.87% | 29587058 | 33.13% | 0 | 0%
TDCJ 12/17 | 56393901 | 67380574 | 26890785 | 39.91% | 40489789 | 60.09% | 0 | 0%
TFC 12/17 | 217156348 | 217156348 | 157362926 | 72.47% | 39447457 | 18.17% | 20345965 | 9.369%
TXDOT 12/17 | 40127926 | 67198859 | 28253893 | 42.05% | 38944966 | 57.95% | 0 | 0%
Totals | 463019552 | 499375838 | 284644157 | 57% | 178478634 | 35.74% | 36253047 | 7.26%
September 2017 QUARTERLY REPORT
DPS 9/17 | 38778877 | 38778877 | 2274264 | 5.865% | 20581594 | 53.07% | 15923019 | 41.06%
TMD 9/17 | 19562500 | 19559182 | 11926010 | 60.97% | 7633172 | 39.03% | 0 | 0%
TPWD 9/17 | 91000000 | 91000000 | 70307573 | 77.26% | 18602833 | 20.44% | 2089594 | 2.296%
TDCJ 9/17 | 56393901 | 67380436 | 29779745 | 44.2% | 37600691 | 55.8% | 0 | 0%
TFC 9/17 | 217156348 | 217156348 | 171818990 | 79.12% | 22963614 | 10.57% | 22373744 | 10.3%
TXDOT 9/17 | 40127926 | 67198859 | 34004826 | 50.6% | 33194033 | 49.4% | 0 | 0%
Totals | 463019552 | 501073702 | 320111408 | 63.89% | 140575937 | 28.05% | 40386357 | 8.06%
JUNE 2017 QUARTERLY REPORT
DPS 6/17 | 38778877 | 38778877 | 5754879 | 14.84% | 6503922 | 16.77% | 26520076 | 68.39%
TMD 6/17 | 19562500 | 19073737 | 12192539 | 63.92% | 6880898 | 36.08% | 0 | 0%
TPWD 6/17 | 91000000 | 91000000 | 36437072 | 40.04% | 12734722 | 13.99% | 41828206 | 45.97%
TDCJ 6/17 | 56393901 | 67455180 | 22855492 | 33.88% | 31802939 | 47.15% | 12796749 | 18.97%
TFC 6/17 | 217156348 | 217156348 | 174204035 | 80.22% | 14226767 | 6.551% | 28725546 | 13.23%
TXDOT 6/17 | 200000000 | 64698859 | 55788445 | 86.23% | 20113762 | 31.09% | 8910414 | 13.77%
Totals | 622891626 | 498163001 | 307232462 | 61.67% | 92263010 | 18.52% | 118780991 | 23.84%
MARCH 2017 QUARTERLY REPORT
DPS 3/17 | 38778877 | 38778877 | 8386884.28 | 21.63% | 2533050.42 | 6.532% | 27858942.3 | 71.84%
TMD 3/17 | 19562500 | 19562500 | 6092097 | 31.14% | 4990681 | 25.51% | 8479722 | 43.35%
TPWD 3/17 | 91000000 | 91000000 | 29260218 | 32.15% | 8257861 | 9.075% | 53481921 | 58.77%
TDCJ 3/17 | 56393901 | 59932443 | 26555599 | 44.31% | 25920990 | 43.25% | 7455854 | 12.44%
TFC 3/17 | 217156348 | 217156348 | 179531584 | 82.67% | 11215827 | 5.165% | 26408937 | 12.16%
TXDOT 3/17 | 200000000 | 62655451 | 45815594 | 73.12% | 13488142 | 21.53% | 3351715 | 5.349%
Totals | 622891626 | 489085619 | 295641976.28 | 60.45% | 66406551.42 | 13.58% | 127037091.3 | 25.97%
DECEMBER 2016 QUARTERLY REPORT
DPS 12/16 | 38778877 | 38778877 | 7839491.37 | 20.22% | 2531236 | 6.527% | 28408149.63 | 73.26%
TMD 12/16 | 19562500 | 19562500 | 8532569 | 43.62% | 2392501 | 12.23% | 8637430 | 44.15%
TPWD 12/16 | 91000000 | 91000000 | 31513563 | 34.63% | 4330345 | 4.759% | 55156092 | 60.61%
TDCJ 12/16 | 56393901 | 59932443 | 30669243 | 51.17% | 18600253 | 31.04% | 10662947 | 17.79%
TFC 12/16 | 217156348 | 217156348 | 154977395 | 71.37% | 8294124 | 3.819% | 53884829 | 24.81%
TXDOT 12/16 | 200000000 | 60235481 | 36687187 | 60.91% | 8408329 | 13.96% | 15139965 | 25.13%
Totals | 622891626 | 486665649 | 270219448.37 | 55.52% | 44556788 | 9.156% | 171889412.63 | 35.32%
SEPTEMBER, 2016 QUARTERLY REPORT
DPS 9/16 | 38778877 | 38778877 | 2162778.32 | 5.577% | 1793696.42 | 4.625% | 34822402.26 | 89.8%
TMD 9/16 | 19562500 | 19562500 | 8931737 | 45.66% | 943263 | 4.822% | 9687500 | 49.52%
TPWD 9/16 | 91000000 | 91000000 | 10624197 | 11.67% | 2370519 | 2.605% | 78005284 | 85.72%
TDCJ 9/16 | 56393901 | 58765393 | 32020908 | 54.49% | 14055123 | 23.92% | 12689362 | 21.59%
TFC 9/16 | 217156348 | 217156348 | 97731599 | 45.01% | 5413721 | 2.493% | 114011028 | 52.5%
TXDOT 9/16 | 200000000 | 62400000 | 18103047 | 29.01% | 2247514 | 3.602% | 42049439 | 67.39%
Totals | 622891626 | 487663118 | 169574266.32 | 34.77% | 26823836.42 | 5.5% | 291265015.26 | 59.73%
JUNE, 2016 QUARTERLY REPORT
DPS 6/16 | 38778877 | 38778877 | 903724.93 | 2.33% | 1793696.42 | 4.625% | 36081455 | 93.04%
TMD 6/16 | 19562500 | 19562500 | 6464547 | 33.05% | 108872 | 0.5565% | 12989081 | 66.4%
TPWD 6/16 | 91000000 | 91000000 | 7089127 | 7.79% | 1191692 | 1.31% | 82719181 | 90.9%
TDCJ 6/16 | 56393901 | 57638273 | 29712683 | 51.55% | 6544679 | 11.35% | 21380911 | 37.09%
TFC 6/16 | 217156348 | 217156348 | 17508535 | 8.063% | 2419828 | 1.114% | 197227985 | 90.82%
TXDOT 6/16 | 200000000 | 200000000 | 5139554 | 2.57% | 481243 | 0.2406% | 194379203 | 97.19%
Totals | 622891626 | 624135998 | 66818170.93 | 10.71% | 12540010.42 | 2.009% | 544777816 | 87.29%
MARCH, 2016 QUARTERLY REPORT
DPS 3/16 | 38778877 | 38778877 | 0 | 0% | 0 | 0% | 38778877 | 100%
TMD 3/16 | 19562500 | 19562500 | 644301 | 3.294% | 22694 | 0.116% | 18895505 | 96.59%
TPWD 3/16 | 91000000 | 91000000 | 5978999 | 6.57% | 371487 | 0.4082% | 84649514 | 93.02%
TDCJ 3/16 | 56393901 | 56685613 | 32900866 | 58.04% | 1985964 | 3.503% | 21798783 | 38.46%
TFC 3/16 | 217156348 | 217156348 | 12176876 | 5.607% | 511856 | 0.2357% | 204467616 | 94.16%
TXDOT 3/16 | 200000000 | 200000000 | 1535625 | 0.7678% | 98690 | 0.04934% | 198959830 | 99.48%
Totals | 622891626 | 623183338 | 53236667 | 8.543% | 2990691 | 0.4799% | 567550125 | 91.07%
DECEMBER, 2015 QUARTERLY REPORT
DPS 12/15 | 38778877 | 38778877 | 0 | 0% | 0 | 0% | 38778877 | 100%
TMD 12/15 | 19562500 | 19562500 | 711000 | 3.635% | 0 | 0% | 18851500 | 96.37%
TPWD 12/15 | 91000000 | 91000000 | 4057560 | 4.459% | 6187 | 0.006799% | 86936253 | 95.53%
TDCJ 12/15 | 56393901 | 57644001 | 20632937 | 35.79% | 423472 | 0.7346% | 36587592 | 63.47%
TFC 12/15 | 217156348 | 217156348 | 0 | 0% | 0 | 0% | 217156348 | 100%
TxDOT 12/15 | 200000000 | 200000000 | 313105 | 0.1566% | - |  | 200000000 | 100%
Totals | 622891626 | 624141726 | 25714602 | 4.12% | 429659 | 0.06884% | 598310570 | 95.86%
.

## DPS
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2018-12-15
| Prepared by: | Tavia Wendlandt
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (FY19 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-62601 | Statewide Temporary DM Staff | Temporary staff needed to administer DM projects. (estimate two years) | General Revenue (Fund 0001) | 215000 | 215000 | Duration of projects | NA | NA | 0 | 144462.41 | 0 |  | 70537.59 | No
2 | 3-COR-17-62737 | Corpus Christi District Office (Reg 3) DM Multi-system project 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Complete ongoing DM projects (HVAC, Sanitary Sewer, Etc.) | General Revenue (Fund 0001) | 780000 | 780000 | 2018-04-20 | 100% | 100% |  | 780000 |  |  | 0 | No
3 | 6-ANW-17-62738 | Austin Northwest Area Office (Reg 6) Roof Replacement 13730 Research Boulevard Austin, Texas 78750 | Partial roof replacement (Built up portion only) | General Revenue (Fund 0001) | 250000 | 625000 | 2018-05-11 | 100% | 100% |  | 625000 |  |  | 0 | No
4 | 2-LUF-17-62603 | Lufkin Lease Refresh - Lufkin CID Lease (Reg 2) 2815 John Redditt Dr. Lufkin, Texas 75904 | Refurbishment and equipping of a certain leased facility in Lufkin for use by CID as per Rider 63. | General Revenue (Fund 0001) | 200000 | 337356.12 | 2017-09-12 | 100% | 100% |  | 340641.63 |  |  | -3285.51 | No
5 | HQ-C-16-62905 | Austin HQ (Building C) Dormitory Renovations Floor 2&3 5805 North Lamar Blvd Austin, Texas 78752 | Dormitory floors 2 and 3 are vacant since 2009 due to fire marshal code violations. Renovations will bring these floors into current building code compliance to allow for additional recruit classes to be held. | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 1300000 | 2017-01-01 | 100% | 100% |  | 1631329.05 |  | 15500 | -346829.05 | No
6 | HQ-CAM-16-62906 | Austin HQ (Campus) Dual Power Feed 5805 North Lamar Blvd Austin, Texas 78752 | Upgrade existing single power source to the complex. Austin Energy will provide two separate power grids to provide redundant power back up for the crime lab, data centers and other critical DPS functions. | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 2182097 | TBD by TFC | 50% | 0% | 213026.64 | 71014.07 |  |  | 1898056.29 | No
7 | HQ-A-16-62895 | Austin HQ (Building A) Data Center Upgrades 5805 North Lamar Blvd Austin, Texas 78752 | Replace existing HVAC, electrical, and fire suppression system, provide redundancy for HVAC/Electrical in the Data Center. | General Revenue (Fund 0001) | 0 | 1750000 | 2018-02-28 | 100% | 100% | 0 | 1750000 | 0 |  | 0 | No
8 | 7-CAP-16-62322 | Austin Capital Services (Reg 7) 1500 N. Congress Austin, Texas 78701 Generator Replacement | Replace existing ATS and package Generator unit at the Capital Services Building. (Additional funding needed according to TFC estimates) | General Revenue (Fund 0001) | 0 | 150000 | 2017-05-31 | 100% | 100% | 0 | 150000 | 0 |  | 0 | No
9 | 1-GAR-17-62606 | Garland Regional Headquarters (Reg 1) HVAC Replacement 350 West IH-30 Garland, Texas 75043 | Heating Ventilation Air Conditioning (HVAC) System replacement in the Annex Facility | General Revenue (Fund 0001) | 400000 | 400000 | TBD by TFC | 0% | 0% | 0 | 400000 | 0 |  | 0 | No
10 | 1-HUR-17-62607 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | General Revenue (Fund 0001) | 302623 | 302623 | TBD by TFC | 0% | 0% | 0 | 302623 | 0 |  | 0 | No
11 | 5-WIC-17-62608 | Wichita Falls Sub-District Office (Reg 5) Roof Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Replace Roof of main building - construction phase. (TFC is engineering roof replacement from Rider 45 DM funds) | General Revenue (Fund 0001) | 200000 | 182157.5 | 2017-03-30 | 100% | 100% |  | 174135.34 |  |  | 8022.16 | No
12 | 2-BEU-17-62609 | Beaumont District Office (Reg 2) HVAC Replacement 7200 Eastex Freeway Beaumont, Texas 77708 | Replacement of Heating Ventilation Air Conditioning (HVAC) Distribution System. | General Revenue (Fund 0001) | 315000 | 315000 | 2017-12-30 | 100% | 100% | 0 | 192396 |  |  | 122604 | No
13 | 3-LAR-17-62610 | Laredo District Office (Reg 3) Vacant area refresh 1901 Bob Bullock Loop Laredo, Texas 78043 | Vacant lab area - Refresh all deteriorated finishes and systems, lighting, roof, HVAC, and other infrastructure serving that area. | General Revenue (Fund 0001) | 150000 | 150000 | 2017-10-19 | 100% | 100% |  | 111202 |  |  | 38798 | No
14 | 5-ABI-17-62611 | Abilene District Office (Reg 5) HVAC Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | General Revenue (Fund 0001) | 260000 | 260000 | TBD by TFC | 0% | 0% | 0 | 260000 | 0 |  | 0 | No
15 | 1-CLE-17-62612 | Cleburne Area Office (Reg 1) HVAC Replacement 600 W. Kilpatrick St. Cleburne, Texas 76031 | Heating Ventilation Air Conditioning (HVAC) System replacement | General Revenue (Fund 0001) | 325000 | 325000 | 2017-05-15 | 100% | 100% | 0 | 65826 | 0 |  | 259174 | No
16 | 5-CHI-17-62613 | Childress Area Office (Reg 5) HVAC Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replacement of Heating Ventilation Air Conditioning (HVAC) System. | General Revenue (Fund 0001) | 500000 | 500000 | 2018-12-30 | 100% | 90% | 0 | 500000 | 0 |  | 0 | No
17 | 2-HGR-17-62614 | Houston Grant Road Driver License Office (Reg 2) Drainage Repairs - 10503 Grant Road Houston, Texas 77070 | DL parking lot repairs and drainage deficiencies | General Revenue (Fund 0001) | 250000 | 250000 | TBD by TFC | 0% | 0% | 0 | 250000 | 0 |  | 0 | No
18 | 4-ODE-17-62615 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) (Combined with project 4-ODE-17-62847) Replacing seven RTUs and 1 exhaust fan on the roof | General Revenue (Fund 0001) | 150714 | 150714 | Rolled into priority project 38. Estimated completion 5/30/17 | 100% | 100% | 0 |  | 0 | 0 | 150714 | No
19 | 4-GAT-17-62616 | El Paso Gateway East Driver License Office (Reg 4) HVAC Replacement 7300 Gateway East El Paso, Texas 79915 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | General Revenue (Fund 0001) | 200000 | 80000 | 2017-03-06 | 100% | 100% | 0 | 54913 | 0 |  | 25087 | No
20 | HQ-L-16-62617 | Austin HQ (Building L) HVAC Replacement 5710 Guadalupe Austin, Texas 78752 | Partial RTU replacements and DDC install - Building L - Fleet Operations | General Revenue (Fund 0001) | 78000 | 78000 | 2018-10-31 | 100% | 100% | 9409 | 95024.16 |  |  | -26433.16 | No
21 | HQ-GA-17-62618 | Austin HQ (Building G Annex) Chiller/Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chillers/boilers in Building G Annex - Multi-Service Facility | General Revenue (Fund 0001) | 769600 | 769600 | TBD by TFC | 0% | 0% |  | 769600 |  |  | 0 | No
22 | HQ-E-17-62619 | Austin HQ (Building E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace boiler in Building E - Law Enforcement Facility | General Revenue (Fund 0001) | 78000 | 78000 | TBD by TFC | 0% | 0% |  | 278000 |  |  | -200000 | No
23 | HQ-C-17-62620 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial HVAC replacement for Building C Training Academy | General Revenue (Fund 0001) | 520000 | 520000 | TBD by TFC | 0% | 0% |  | 520000 |  |  | 0 | No
24 | HQ-A-17-62621 | Austin HQ (Building A) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building A | General Revenue (Fund 0001) | 1040000 | 1040000 | TBD by TFC | 0% | 0% |  | 1040000 |  |  | 0 | No
25 | HQ-E-17-62622 | Austin HQ (Building E) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building E - Law Enforcement Facility | General Revenue (Fund 0001) | 1787058 | 1787058 | TBD by TFC | 0% | 0% | 0 | 1787058 | 0 |  | 0 | No
26 | HQ-O-17-62623 | Austin HQ (Building O) Sprinkler System 5601 Guadalupe Austin, Texas 78752 | Add Sprinklers (Fire Marshal recommendation) - Building O Fleet Operations | General Revenue (Fund 0001) | 26000 | 26000 | TBD by TFC | 0% | 0% | 0 | 26000 | 0 |  | 0 | No
27 | 2-CON-17-62624 | Conroe District Office (Reg 2) Ductwork Replacement 2 Hilbig St. Conroe, Texas 77301 | Ductwork replacement-system reviewed and found contaminants and poor IAQ in facility due to condition of ductwork. Funding request to replace all flex duct and have the hard duct cleaned and sealed. (Includes office and Motor Vehicle Theft (MVT) Garage | General Revenue (Fund 0001) | 603870 | 603870 | TBD by TFC | 0% | 0% | 0 | 603870 | 0 |  | 0 | No
28 | 1-GAR-17-62625 | Garland Regional Headquarters (Reg 1) Site Lighting Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged site lighting. | General Revenue (Fund 0001) | 134006 | 134006 | TBD by TFC | 0% | 0% | 0 | 134006 | 0 |  | 0 | No
29 | 1-GAR-17-62626 | Garland Regional Headquarters (Reg 1) Electrical Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged electrical system | General Revenue (Fund 0001) | 574870 | 574870 | TBD by TFC | 0% | 0% | 0 | 574870 | 0 |  | 0 | No
30 | 1-GAR-17-62627 | Garland Regional Headquarters (Reg 1) Plumbing Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged plumbing (i.e.: Natural Gas system, domestic water system and fixtures, etc.) | General Revenue (Fund 0001) | 517577 | 517577 | TBD by TFC | 0% | 0% | 0 | 517577 | 0 |  | 0 | No
31 | 1-GAR-17-62628 | Garland Regional Headquarters (Reg 1) Foundation Study 350 West IH-30 Garland, Texas 75043 | Several signs of stress and settlement is seen throughout the facility, specifically on the Westside of the building. Recommend a professional structural engineering study be conducted for resolution. | General Revenue (Fund 0001) | 150000 | 150000 | TBD by TFC | 0% | 0% | 0 | 150000 | 0 |  | 0 | No
32 | 2-PIE-17-62629 | Pierce Sub-District Office (Reg 2) Foundation Study 19692 US Hwy 59 El Campo, Texas 77437 | Northwest wall and a part of Northeast wall are showings signs of structural degradation. Recommend professional study. | General Revenue (Fund 0001) | 150000 | 150000 | TBD by TFC | 0% | 0% | 0 | 150000 | 0 |  | 0 | No
33 | 2-BAY-17-62630 | Baytown Area Office (Reg 2) Foundation Repairs 5420 Decker Drive Baytown, Texas 77520 | Repair foundation / interior finishes | General Revenue (Fund 0001) | 150000 | 150000 | TBD by TFC | 0% | 0% | 0 | 150000 | 0 |  | 0 | No
34 | 5-CHI-17-62631 | Childress Area Office (Reg 5) Foundation Study 1700 Ave. F Northwest Childress, Texas 79201 | The retaining walls are cracking and showing signs of structural problems. Recommend professional study. | General Revenue (Fund 0001) | 150000 | 150000 | TBD by TFC | 0% | 0% | 0 | 150200 | 0 |  | -200 | No
35 | 1-SUL-17-62632 | Sulphur Springs Area Office (Reg 1) Foundation Study 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Settlement cracks in foundation, exterior walls, and interior wall systems. Recommend a professional structural engineering study be conducted for resolution. | General Revenue (Fund 0001) | 150000 | 150000 | TBD by TFC | 0% | 0% | 0 | 150000 | 0 |  | 0 | No
36 | 2-CON-17-62633 | Conroe District Office (Reg 2) Foundation Study 804 Interstate 45 South Conroe, Texas 77304 | Exterior walls are showing stress and damage at the MVT Garage. Recommend professional structure analysis to determine condition and repair of exterior wall and implement repairs. | General Revenue (Fund 0001) | 185000 | 185000 | TBD by TFC | 0% | 0% | 0 | 185000 | 0 |  | 0 | No
37 | HQ-L-17-62634 | Austin HQ (Building L) Car Wash Replacement 5710 Guadalupe Austin, Texas 78752 | Replace car wash at Fleet Operations - Building L | General Revenue (Fund 0001) | 100000 | 100000 | 2017-08-31 | 100% | 100% |  |  |  | 172458 | -72458 | No
38 | 4-ODE-17-62847 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Terminal & Package Units (Building Automation System) (Combined with project 4-ODE-17-62615) seven RTUs and 1 exhaust fan on the roof | General Revenue (Fund 0001) | 234000 | 234000 | 2017-05-30 | 100% | 100% | 0 | 78595 | 0 |  | 155405 | No
39 | 4-ODE-17-62754 | Odessa Area Office (Reg 4) Roof Replacement 1910 IH-20 West Odessa, Texas 79762 | Roof Coverings/openings-built-up roofing replacement | General Revenue (Fund 0001) | 249600 | 249600 | 2017-11-08 | 100% | 100% |  | 169950 |  |  | 79650 | No
40 | ST-FUEL-16-62739 | Statewide Fuel System Maintenance/Removal | UST/AST fueling systems repairs/maintenance/removal | General Revenue (Fund 0001) | 250000 | 250000 | 2018-02-01 | 100% | 100% |  | 413199.87 |  |  | -163199.87 | No
41 | 5-AMA-17-62740 | Amarillo District Office (Reg 5) Exterior Door/Window Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Exterior doors replacement/Window replacement | General Revenue (Fund 0001) | 167666.72 | 167667 | TBD by TFC | 0% | 0% | 0 | 167667 | 0 |  | 0 | No
42 | 6-ADO-17-62741 | Austin District Office (Reg 6) HVAC Replacement 9000 IH-35 North Austin, Texas 78753 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | General Revenue (Fund 0001) | 192294.48 | 192294 | 2017-05-10 | 100% | 100% |  | 234157 |  |  | -41863 | No
43 | 6-ADO-17-62742 | Austin District Office (Reg 6) Roof Replacement 9000 IH-35 North Austin, Texas 78753 | Roof Coverings built-up roofing replacement | General Revenue (Fund 0001) | 338000 | 338000 | 2019-02-28 | 100% | 99% | 61799.25 | 188997.75 |  |  | 87203 | No
44 | 2-HHQ-17-62743 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Chiller replacement | General Revenue (Fund 0001) | 312000 | 312000 | 2018-03-21 | 100% | 100% |  | 0 | 900 | 322000 | -10900 | No
45 | 4-SAN-17-62744 | San Angelo Sub-District Office (Reg 4) HVAC Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | General Revenue (Fund 0001) | 633900.8 | 633900.8 | TBD by TFC | 0% | 0% | 0 | 633901 | 0 |  | -0.2 | No
46 | 4-SAN-17-62745 | San Angelo Sub-District Office (Reg 4) Roof Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | Roof Coverings built-up roofing replacement | General Revenue (Fund 0001) | 325000 | 325000 | 2018-01-11 | 100% | 100% |  | 296592 |  |  | 28408 | No
47 | 1-HUR-17-62746 | Hurst Sub-District Office (Reg 1) Roof Replacement 624 NE Loop 820 Hurst, Texas 76053 | Roof Coverings built-up roofing replacement (Including roof openings) | General Revenue (Fund 0001) | 430981.2 | 430981.2 | TBD by TFC | 0% | 0% | 0 | 430981 | 0 |  | 0.2 | No
48 | 3-EAG-17-62787 | Eagle Pass Area Office (Reg 3) HVAC Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Terminal & package units replacement/upgrade (Add BAS as needed) | General Revenue (Fund 0001) | 10000 | 10000 | TBD by TFC | 0% | 0% |  | 10000 |  |  | 0 | No
49 | 3-HAR-17-62748 | Harlingen Area Office (Reg 3) Roof Repairs 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Roof repairs | General Revenue (Fund 0001) | 325000 | 325000 | 2016-10-20 | 100% | 100% | 0 | 2000 | 0 |  | 323000 | No
50 | 3-BEE-17-62749 | Beeville Area Office (Reg 3) HVAC Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Terminal & package units replacement/upgrade (Add BAS as needed) | General Revenue (Fund 0001) | 10000 | 10000 | 2017-12-15 | 100% | 100% | 245 | 12255 |  |  | -2500 | No
51 | 3-BEE-17-62750 | Beeville Area Office (Reg 3) Roof Repairs 400 S. Hillside Drive Beeville, Texas 78102 | Roof repairs | General Revenue (Fund 0001) | 150000 | 150000 | 2016-10-18 | 100% | 100% | 0 | 1950 | 0 |  | 148050 | No
52 | 4-BIG-17-62751 | Big Spring Area Office (Reg 4) HVAC Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Terminal & package units replacement/upgrade - including split DX (Add BAS as needed) | General Revenue (Fund 0001) | 2954.64 | 2954.64 | 2017-08-21 | 100% | 100% |  | 91500 |  |  | -88545.36 | No
53 | ST-PM-17-62635 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | General Revenue (Fund 0001) | 616800 | 616800 | TBD by TFC | NA | NA | 0 | 757500 | 0 |  | -140700 | No
54 | HQ-C-16-62904 | Austin HQ (Building C) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Boiler replacement (two boilers supporting original building) | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 100000 | 2016-12-13 | 100% | 100% | 0 | 80949 | 0 |  | 19051 | No
55 | 2-BRE-17-62752 | Brenham Area Office (Reg 2) HVAC Controls Replacement 975 Hwy 290 West. Brenham, Texas 77834 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | G.O. Bond savings from 80th Legislative $200M bond package. | 168720.24 | 168720 | 2017-03-03 | 100% | 100% |  | 23719 |  |  | 145001 | No
56 | 2-BRE-17-62753 | Brenham Area Office (Reg 2) Roof Replacement 975 Hwy 290 West. Brenham, Texas 77834 | Roof Coverings built-up roofing replacement and access ladder | G.O. Bond savings from 80th Legislative $200M bond package. | 130000 | 130000 | 2017-06-06 | 100% | 100% |  | 77611 |  |  | 52389 | No
57 | 2-ORA-17-62755 | Orange Area Office (Reg 2) Roof Replacement 711 South Hwy 87 Orange, Texas 77630 | Roof Coverings built-up roofing replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 182000 | 182000 | 2017-06-15 | 100% | 100% |  | 79460 |  |  | 102540 | No
58 | 4-OZO-16-62756 | Ozona Area Office (Reg 4) HVAC Replacement 1503 Monterey St Ozona, Texas 76943 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance (Project was completed from other funding) | G.O. Bond savings from 80th Legislative $200M bond package. | 132242.24 | 132242.24 | Project completed in prior fiscal year using other funding. | 100% | 100% | 0 | 0 | 0 | 0 | 132242.24 | No
59 | 4-Pec-18-62757 | Pecos Area Office (Reg 4) HVAC Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Terminal & package units replacement/upgrade (Add BAS as needed), Distribution systems, controls and instrumentation replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 117413.92 | 117414 | 2018-10-11 | 100% | 100% |  | 0 | 108400 | 0 | 9014 | No
60 | 4-Pec-17-62758 | Pecos Area Office (Reg 4) Roof Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Roof Coverings built-up roofing replacement/roof openings | G.O. Bond savings from 80th Legislative $200M bond package. | 133023.28 | 133023.28 | 2019-04-30 | 100% | 0% | 84796 | 10005.57 |  | 0 | 38221.71 | Yes
61 | 3-UVA-17-62759 | Uvalde Area Office (Reg 3) Roof Replacement 2901 E. Main Uvalde, Texas 78801 | Roof Coverings built-up roofing replacement/roof openings | G.O. Bond savings from 80th Legislative $200M bond package. | 102397.2 | 102397.2 | 2017-08-02 | 100% | 100% |  | 63500 |  |  | 38897.2 | No
62 | 1-GAR-18-62760 | Garland Regional Headquarters Site (Reg 1) Communication & Security 350 West IH-30 Garland, Texas 75043 | Site Comm & Security (i.e.: fencing, gate access control, etc.). Project converted to update interior access controls | G.O. Bond savings from 80th Legislative $200M bond package. | 49042.24 | 49042.24 | 2018-06-22 | 100% | 100% | 0 | 0 | 1742.11 | 33151 | 14149.13 | No
63 | 1-GAR-17-62761 | Garland Regional Headquarters Site (Reg 1) Landscaping Upgrade 350 West IH-30 Garland, Texas 75043 | Landscaping (xeriscape) upgrade | G.O. Bond savings from 80th Legislative $200M bond package. | 98962.24 | 98962 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 98962 | Yes
64 | 1-GAR-17-62761 | Garland Regional Headquarters Site (Reg 1) Parking Lot Replacement 350 West IH-30 Garland, Texas 75043 | Parking lot/pedestrian paving/driveways replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 789058.4 | 789058.4 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 789058.4 | Yes
65 | 1-GAR-17-62761 | Garland Regional Headquarters Site (Reg 1) Sanitary Sewer Replacement 350 West IH-30 Garland, Texas 75043 | Sanitary sewer replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 24553.36 | 24553.36 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 24553.36 | Yes
66 | 1-GAR-17-62761 | Garland Regional Headquarters Site (Reg 1) Site Development 350 West IH-30 Garland, Texas 75043 | Site Development (i.e.: Storm water system, etc.) | G.O. Bond savings from 80th Legislative $200M bond package. | 287119.04 | 287119.04 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 287119.04 | Yes
67 | 1-GAR-17-62761 | Garland Regional Headquarters Site (Reg 1) Water Supply Upgrade 350 West IH-30 Garland, Texas 75043 | Water Supply upgrade/replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 67370.16 | 67370.16 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 67370.16 | Yes
68 | 2-PIE-18-62766 | Pierce Sub-District Office (Reg 2) Ductwork Replacement 19692 US Hwy 59 El Campo, Texas 77437 | Duct work and insulation replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 62400 | 62400 | 2018-02-20 | 100% | 100% | 0 | 0 |  | 60000 | 2400 | No
69 | 2-BRE-17-62767 | Brenham Area Office (Reg 2) Exterior Wall Repair 975 Hwy 290 West. Brenham, Texas 77834 | Exterior walls repair | G.O. Bond savings from 80th Legislative $200M bond package. | 10773.36 | 10773.36 | 2017-07-31 | 100% | 100% |  | 50920 |  |  | -40146.64 | No
70 | 2-HHQ-17-62768 | Houston Regional Headquarters (West Road) (Reg 2) Security System Replacement 12230 West Road Jersey Village, Texas 77065 | Security system replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 208000 | 208000 | 2017-07-11 | 100% | 100% | 0 | 99302 | 0 |  | 108698 | No
71 | 4-MID-17-62769 | Midland Sub District Office (Reg 4) Vacant DL Remodel/Refresh 2405 S. Loop 250 West Midland, Texas 79703 | Remodel vacant DL area including to replacing deteriorated finishes and MEP systems | G.O. Bond savings from 80th Legislative $200M bond package. | 442000 | 442000 | TBD by TFC | 0% | 0% | 17600 | 0 |  |  | 424400 | No
72 | 5-AMA-18-62770 | Amarillo District Office (Reg 5) Security System Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Security system replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 343698.16 | 343698.16 | 2018-06-11 | 100% | 100% | 0 | 0 | 858.56 | 27962.2 | 314877.4 | No
73 | 5-AMA-18-62771 | Amarillo District Office (Reg 5) Sprinkler System 4200 Canyon Dr. Amarillo, Texas 79109 | Sprinkler system | G.O. Bond savings from 80th Legislative $200M bond package. | 153180.56 | 153181 | 8-31-19 - Phased project. Upon completion of TFC's portion, DPS will begin. | 0% | 0% | 0 | 0 | 0 | 0 | 153181 | Yes
74 | 5-AMA-18-62772 | Amarillo District Office (Reg 5) Foundation Study/Repair 4200 Canyon Dr. Amarillo, Texas 79109 | Standard foundations | G.O. Bond savings from 80th Legislative $200M bond package. | 40278.16 | 40278.16 | 8-31-19 - Phased project. Upon completion of TFC's portion, DPS will begin. | 0% | 0% | 0 | 0 | 0 | 0 | 40278.16 | Yes
75 | 5-AMA-17-62773 | Amarillo District Office (Reg 5) Interior Finishes Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Ceiling, wall, floor finishes replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 575051.36 | 575051.36 | 8-31-19 - Phased project. Upon completion of TFC's portion, DPS will begin. | 0% | 0% | 17500 | 0 | 0 | 0 | 557551.36 | Yes
76 | 5-AMA-18-62774 | Amarillo District Office (Reg 5) Fittings Pipe 4200 Canyon Dr. Amarillo, Texas 79109 | Pipe Fittings | G.O. Bond savings from 80th Legislative $200M bond package. | 17077.84 | 17077.84 | 8-31-19 - Phased project. Upon completion of TFC's portion, DPS will begin. | 0% | 0% | 0 | 0 | 0 | 0 | 17077.84 | Yes
77 | 6-ADO-17-62775 | Austin District Office Site (Reg 6) Parking Lot Replacement 9000 IH-35 North Austin, Texas 78753 | Parking lot replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 260000 | 260000 | 2017-09-11 | 100% | 100% |  | 87000 |  |  | 173000 | No
78 | 6-ADO-17-62776 | Austin District Office Site (Reg 6) Site Lighting Replacement/Upgrade 9000 IH-35 North Austin, Texas 78753 | Site Lighting | G.O. Bond savings from 80th Legislative $200M bond package. | 57117.84 | 57117.84 | 2017-07-17 | 100% | 100% |  | 15080 |  |  | 42037.84 | No
79 | 6-ADO-18-62777 | Austin District Office Site (Reg 6) Communication & Security 9000 IH-35 North Austin, Texas 78753 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | G.O. Bond savings from 80th Legislative $200M bond package. | 22046.96 | 22046.96 | 2018-05-03 | 100% | 100% |  | 0 | 8511 | 14579 | -1043.04 | No
80 | 6-ADO-18-62778 | Austin District Office Storage Hwy Patrol (Reg 6) Special Structures 9000 IH-35 North Austin, Texas 78753 | Special Structures - Storage Bldg. < 1000sf - Roof replacement, paint/waterproof exterior | G.O. Bond savings from 80th Legislative $200M bond package. | 12728.56 | 12728.56 | 2018-02-11 | 100% | 100% | 0 | 11480 | 0 | 0 | 1248.56 | No
81 | 5-ABI-18-62779 | Abilene District Office (Reg 5) Security/Site System Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security system replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 220581.92 | 220581.92 | 2018-06-11 | 100% | 100% | 0 | 0 | 1770.74 | 29717.83 | 189093.35 | No
82 | 3-LAR-18-62780 | Laredo District Office (Reg 3) Ceiling Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Ceiling/wall finishes replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 389896.32 | 389896.32 | 2018-12-31 | 100% | 40% | 0 | 0 | 115251.25 | 129948.75 | 144696.32 | No
83 | 3-LAR-18-62781 | Laredo District Office (Reg 3) Security System Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Security system replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 373251.84 | 373251.84 | 2018-07-09 | 100% | 100% |  |  |  | 34545.82 | 338706.02 | No
84 | 6-WAC-17-62782 | Waco District Office (Reg 6) Interior Finishes Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Ceiling, wall, floor finishes replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 567938.8 | 567938.8 | 2019-03-31 | 100% | 0% | 0 | 0 | 247419 | 0 | 320519.8 | No
85 | 6-WAC-18-62783 | Waco District Office (Reg 6) Fixed Furnishings Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Fixed furnishings replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 137846.8 | 137847 | 2019-03-31 | 100% | 0% | 0 | 0 | 0 | 0 | 137847 | No
86 | 3-EAG-17-62787 | Eagle Pass Area Office (Reg 3) Interior Finishes Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Ceiling, wall, floor finishes replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 186283.86 | 186283.86 | TBD by TFC | 10% | 0% | 0 | 0 |  | 0 | 186283.86 | Yes
87 | 3-EAG-17-62787 | Eagle Pass Area Office (Reg 3) Electrical Systems 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Other Electrical Systems (Repair illuminated exit signs throughout the facility and add emergency lighting where needed.) | G.O. Bond savings from 80th Legislative $200M bond package. | 150000 | 150000 | TBD by TFC | 10% | 0% | 0 | 0 | 0 | 0 | 150000 | Yes
88 | 3-EAG-18-62787 | Eagle Pass Area Office (Reg 3) Security System Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Security system replacement Include gate access control | G.O. Bond savings from 80th Legislative $200M bond package. | 125000 | 125000 | 2018-08-31 | 100% | 100% |  | 0 | 23044.89 | 13526.29 | 88428.82 | Yes
89 | 3-EAG-17-62787 | Eagle Pass Area Office (Reg 3) Sprinkler System 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Sprinkler System | G.O. Bond savings from 80th Legislative $200M bond package. | 49622.56 | 49622.56 | TBD by TFC | 10% | 0% | 0 | 0 | 0 | 0 | 49622.56 | Yes
90 | 3-EAG-17-62787 | Eagle Pass Site (Reg 3) Communication & Security 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Comm & Security (i.e.: fencing, etc.) | G.O. Bond savings from 80th Legislative $200M bond package. | 9984 | 9984 | TBD by TFC | 10% | 0% | 0 | 0 | 0 | 0 | 9984 | Yes
91 | 3-EAG-17-62787 | Eagle Pass Site (Reg 3) Landscaping Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Landscaping (xeriscape) upgrade | G.O. Bond savings from 80th Legislative $200M bond package. | 4285.84 | 4285.84 | TBD by TFC | 10% | 0% | 0 | 0 | 0 | 0 | 4285.84 | Yes
92 | 3-EAG-17-62787 | Eagle Pass Site (Reg 3) Site Lighting Replacement/Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Lighting | G.O. Bond savings from 80th Legislative $200M bond package. | 20368.4 | 20368.4 | TBD by TFC | 10% | 0% | 0 | 0 | 0 | 0 | 20368.4 | Yes
93 | 5-AMA-17-62791 | Amarillo MVT Building (Reg 5) Electrical Systems 4200 Canyon Dr. Amarillo, Texas 79109 | Other Electrical Systems (Add illuminated exit signs throughout the facility and add emergency lighting where needed.) | General Revenue (Fund 0001) | 260 | 260 | 2016-06-14 | 100% | 100% | 0 | 0 | 0 | 260 | 0 | No
94 | 5-AMA-18-62792 | Amarillo Site (Reg 6) Communication & Security 4200 Canyon Dr. Amarillo, Texas 79109 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | G.O. Bond savings from 80th Legislative $200M bond package. | 25084.8 | 25084.8 | 12/31/2018 Phased project. Upon completion of TFC's portion, DPS will begin. | 100% | 0% | 0 | 0 | 0 | 0 | 25084.8 | Yes
95 | 5-AMA-17-62793 | Amarillo Site (Reg 5) Fuel Distribution Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fuel distribution replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 46800 | 46800 | 2018-01-23 | 100% | 100% |  | 46651 |  |  | 149 | No
96 | 5-AMA-17-62794 | Amarillo Site (Reg 5) Parking Lot/Pedestrian Paving 4200 Canyon Dr. Amarillo, Texas 79109 | Parking lot/pedestrian paving replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 291766.8 | 291766.8 | 2018-08-24 | 100% | 100% | 14630 | 214065 |  |  | 63071.8 | No
97 | 5-AMA-18-62795 | Amarillo Site (Reg 5) Site Lighting Replacement/Upgrade 4200 Canyon Dr. Amarillo, Texas 79109 | Site Lighting | G.O. Bond savings from 80th Legislative $200M bond package. | 65007.28 | 65007.28 | 2018-08-13 | 100% | 100% | 0 | 0 |  | 18771 | 46236.28 | No
98 | 5-AMA-18-62795 | Amarillo Region Office (Reg 5) Renovations 4200 Canyon Dr. Amarillo, Texas 79109 | Building Remodel Multiple Project | G.O. Bond savings from 80th Legislative $200M bond package. |  | 600000 | TBD | 75% | 0% | 0 | 0 |  | 0 | 600000 | No
99 | HQ-A-17-62796 | Austin HQ (Building A) AHU/FCU Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - replace all AHU and FCUs not already in process/completed | G.O. Bond savings from 80th Legislative $200M bond package. | 520000 | 520000 | TBD by TFC | 100% | 0% | 0 | 0 | 0 | 0 | 520000 | No
100 | HQ-A-18-62797 | Austin HQ (Building A) DDC Retrofit 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - retrofit existing pneumatic controls to DDC | G.O. Bond savings from 80th Legislative $200M bond package. | 62400 | 62400 | 2018-10-31 | 100% | 100% |  | 0 | 18680.6 | 51219.4 | -7500 | No
101 | 2-BRY-17-62769 | Bryan District Office (Reg 2) Foundation/Drainage Modifications 2571 North Earl Rudder Freeway Bryan, Texas 77805 | Foundation/site drainage modifications | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 650000 | TBD by TFC | 65% | 0% | 0 | 0 | 0 |  | 650000 | No
102 | 6-WTR-18-62924 | Waco Texas Rangers Headquarters and Education Center (Reg 6) HVAC Replacement 102 Texas Ranger Trail Waco, Texas 76705 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 350000 | 2019-03-31 | 100% | 0% | 0 | 0 | 16700 | 38100 | 295200 | No
103 | 1-TER-17-62917 | Terrell Area Office (Reg 1) Drainage Repairs 111 Tejas Drive Terrell, Texas 75160 | Site drainage repairs | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 100000 | 2017-08-25 | 100% | 100% |  | 21309.18 |  |  | 78690.82 | No
104 | 3-EAG-17-62787 | Eagle Pass Area Office (Reg 3) Foundation/Drainage Modifications 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Foundation/site drainage modifications | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 100000 | TBD by TFC | 100% | 0% | 0 | 0 | 0 | 0 | 100000 | Yes
105 | 6-ANW-17-XXXXX | Austin Northwest Area Office (Reg 6) Interior Finish Replacement 13730 Research Boulevard Austin, Texas 78750 | Ceiling, wall, floor finishes replacement | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 50000 | 12/7/17 | 100% | 100% | 0 | 0 | 0 | 0 | 50000 | Yes
106 | HQ-L-17-62903 | Austin HQ (Building L) Car Lift Replacement 5710 Guadalupe Austin, Texas 78752 | Replace 18 original car lifts that are no longer functioning, leaking hydraulic oil, or not operating effectively. | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 100000 | 2018-07-13 | 100% | 100% |  | 0 | 77941 | 25749 | -3690 | No
107 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | General Revenue (Fund 0001) | 1868101.16 | -670039.26 | Duration of projects. | NA | NA | 0 |  | 0 |  | -670039.26 | Yes
108 | ST-CONB-17-62894 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. May also include any addition project expenses such as TFC fees | G.O. Bond savings from 80th Legislative $200M bond package. |  | -2108359.79 | Duration of projects | NA | NA | 0 | 0 | 0 | 0 | -2108359.79 | Yes
109 | ST-CON-16-62461 | Childress Area Office (Reg 5) Roof Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Statewide Unexpected DM repairs/Project Contingency: Replace Childress radio shop roof (Roof is leaking and contains asbestos) 3/24/16 - entered req. | General Revenue (Fund 0001) | 0 | 59800 | 2017-04-01 | 100% | 100% |  | 59800 |  |  | 0 | No
110 | 4-ALP-16-62461 | Alpine Area Office (Reg 4) Energy Efficiency Project 3500 North Highway 118 Alpine, Texas 79830 | Statewide Unexpected DM repairs/Project Contingency: Add ceiling insulation to increase energy efficiency to assist HVAC system to better control temperature in open ceiling area. | General Revenue (Fund 0001) | 0 | 49750 | 2016-11-27 | 100% | 100% | 0 | 49750 | 0 |  | 0 | No
111 | 2-Gal-16-62441 | Galveston Driver License Office (Reg 2) Replace Failed RTU 6802 Broadway Galveston, Texas 77554 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 10-ton RTU | General Revenue (Fund 0001) |  | 16313 | 2016-04-04 | 100% | 100% | 0 | 16313 | 0 |  | 0 | No
112 | 4-EHQ-16-62441 | El Paso Regional Headquarters (Reg 4) RTU Replacement 11612 Scott Simpson El Paso, Texas 79936 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 2.5 Ton RTU (Commander's area) | General Revenue (Fund 0001) |  | 6982.51 | 2016-12-01 | 100% | 100% | 0 | 6982.51 | 0 |  | 0 | No
113 | 1-Min-16-62441 | Mineral Wells Area Office (Reg 1) RTU Replacement 600 FM 1821 North Mineral Wells, Texas 76067 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 5 ton RTU. | General Revenue (Fund 0001) |  | 9100 | 2015-11-27 | 100% | 100% | 0 | 9100 | 0 |  | 0 | No
114 | 2-BAY-16-62441 | Baytown Area Office (Reg 2) RTU Replacement 5420 Decker Drive Baytown, Texas 77520 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 3 ton RTU | General Revenue (Fund 0001) |  | 10534 | 2016-03-10 | 100% | 100% | 0 | 10534 | 0 |  | 0 | No
115 | HQ-TTC-16-62441 | Tactical Training Center (HQ) RTU Replacement 810 County Road 240 Florence, Texas 76527 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 2 ton RTU | General Revenue (Fund 0001) |  | 9850.5 | 2016-02-22 | 100% | 100% | 0 | 9850.5 | 0 |  | 0 | No
116 | 3-DEL-16-62431 | Del Rio Sub District Office (Reg 3) Water Heater Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Statewide Unexpected DM repairs/Project Contingency: Replace failed water heater | General Revenue (Fund 0001) |  | 3310 | 2015-12-16 | 100% | 100% | 0 | 3310 | 0 |  | 0 | No
117 | HQ-L-16-62441 | Austin HQ (Building L) Shop Heaters Replacement 5710 Guadalupe Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace 6 outdated gas fired shop heaters (Labor only) and install 5 natural gas shop heaters. | General Revenue (Fund 0001) |  | 3971 | 2015-12-08 | 100% | 100% | 0 | 3971 | 0 |  | 0 | No
118 | 2-ROS-16-62481 | Rosenberg Area Office (Reg 2) Water Line Replacement 5505 Avenue N. Rosenberg, TX 77471-5640 | Statewide Unexpected DM repairs/Project Contingency: Water Line Replacement due to line breakage | General Revenue (Fund 0001) |  | 20362 | 2016-01-06 | 100% | 100% | 0 | 20362 | 0 |  | 0 | No
119 | 2-ANG-16-62441 | Angleton Driver License Office (Reg 2) RTU Replacement 501 South Velasco Angleton, Texas 77515 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 5 ton RTU. | General Revenue (Fund 0001) |  | 14833 | 2016-02-12 | 100% | 100% | 0 | 14833 | 0 |  | 0 | No
120 | 1-GCL-16-62441 | Garland Crime Laboratory (Reg 1) BTU Boiler Replacement 402 West IH-30 Garland, Texas 75043 | Statewide Unexpected DM repairs/Project Contingency: Replace 2 failed BTU boilers and appurtenances | General Revenue (Fund 0001) |  | 22950 | 2016-03-18 | 100% | 100% | 0 | 22950 | 0 |  | 0 | No
121 | 3-WES-16-62441 | Weslaco Regional Headquarters (Reg 3) VFD Replacement 2525 N. International Blvd Weslaco, TX 78596 | Statewide Unexpected DM repairs/Project Contingency: Replace failed VFD | General Revenue (Fund 0001) |  | 4550.85 | 2016-03-08 | 100% | 100% | 0 | 4550.85 | 0 |  | 0 | No
122 | 2-LUF-16-62441 | Lufkin Sub-District Office (Reg 2) Replace cooling system 2809 South John Redditt Drive Lufkin, TX 75904 | Statewide Unexpected DM repairs/Project Contingency: Replace split cooling system with a gas furnace | General Revenue (Fund 0001) |  | 11676 | 2016-04-21 | 100% | 100% | 0 | 11676 | 0 |  | 0 | No
123 | 2-BCA-16-62431 | Bay City Area Office (Reg 2) 510 Avenue F Bay City, TX 77414 | Statewide Unexpected DM repairs/Project Contingency: Replace failed gas water heater | General Revenue (Fund 0001) |  | 2105 | 2015-11-18 | 100% | 100% | 0 | 2105 |  |  | 0 | No
124 | HQ-C-16-62431 | Austin HQ (Building C&E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Building E Waterproofing Elev#16. & Bldg. E-Rm. E001. | General Revenue (Fund 0001) |  | 33750 | 2016-05-10 | 100% | 100% | 0 | 33750 | 0 |  | 0 | No
125 | HQ-CA-16-62451 | Austin HQ (Building C Annex) Floor Finish Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Corridor C (basement) Annex Flooring. | General Revenue (Fund 0001) |  | 4516.4 | 2016-08-20 | 100% | 100% | 0 | 4516.4 | 0 |  | 0 | No
126 | HQ-CA-16-62451 | Austin HQ (Building C Annex) Wall Finish Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Corridor C (basement) Annex wall covering. | General Revenue (Fund 0001) |  | 1400 | 2016-08-20 | 100% | 100% | 0 | 1400 | 0 |  | 0 | No
127 | 4-EHQ-16-62441 | Houston Regional Headquarters (Reg 2) Chiller Compressor Replacement 12230 West Road Jersey Village, Texas 77065 | Statewide Unexpected DM repairs/Project Contingency: Replace failed refrigerant compressor on Chiller #1, Circuit #2 at Region II HQ facility | General Revenue (Fund 0001) |  | 33901 | 2017-04-10 | 100% | 100% | 0 | 33901 | 0 |  | 0 | No
128 | HQ-CA-16-62421 | Austin HQ (Complex) Security Repairs 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Security System Repairs | General Revenue (Fund 0001) |  | 10348.35 | 2018-04-04 | 100% | 100% |  | 10348.35 |  |  | 0 | No
129 | 6-SAN-17-62441 | San Antonio Regional HQ (Reg 6) RTU Replacement 6502 South New Braunfels Ave San Antonio, Texas 78223 | Statewide Unexpected DM repairs/Project Contingency: Replace two failed RTU. (17.5 ton and 5 ton) | General Revenue (Fund 0001) |  | 27444.72 | 2016-12-31 | 100% | 100% | 0 | 27444.72 | 0 |  | 0 | No
130 | 2-BRY-17-62431 | Bryan District Office (Reg 2) Generator Repair 2571 North Earl Rudder Freeway Bryan, Texas 77805 | Statewide Unexpected DM repairs/Project Contingency: Replace failed water pump and perform annual maintenance. | General Revenue (Fund 0001) |  | 15951.73 | 2017-04-01 | 100% | 100% |  | 15951.73 |  |  | 0 | No
131 | HQ-A-17-62431 | Austin HQ (Complex) Generator Repair 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: TDEM Generator internal repair. | General Revenue (Fund 0001) |  | 19420.55 | 2017-04-10 | 100% | 100% | 0 | 19420.55 | 0 |  | 0 | No
132 | 4-BIG-17-62461 | Big Spring Area Office (Reg 4) Roof Repair 5725 W. IH-20 Big Spring, Texas 79720 | Statewide Unexpected DM repairs/Project Contingency: Roof repair | General Revenue (Fund 0001) |  | 15366 | 2017-06-30 | 100% | 100% | 0 | 15366 | 0 |  | 0 | No
133 | HQ-U-17-62441 | Austin HQ (U) Upgrade DDC 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Upgrade DDC in Building U and also include exterior lighting controls. | General Revenue (Fund 0001) |  | 39448 | 2018-05-25 | 100% | 100% |  |  | 4921.45 | 34526 | 0.55 | No
134 | 6-Wac-17-62910 | Waco District Office (Reg 6) DM Multi-system project 1617 E. Crest Dr. Waco, Texas 76705 | Statewide Unexpected DM repairs/Project Contingency: Complete ongoing DM projects (HVAC, roof, Electrical, Etc.) | General Revenue (Fund 0001) |  | 350000 | 2019-03-31 | 100% | 0% | 0 | 350000 | 0 |  | 0 | No
135 | 4-MID-17-62909 | Midland Sub District Office (Reg 4) DM Multi-system project 2405 S. Loop 250 West Midland, Texas 79703 | Statewide Unexpected DM repairs/Project Contingency: Complete ongoing DM projects (Roof, HVAC, Etc.) | General Revenue (Fund 0001) |  | 350000 | TBD by TFC | 100% | 0% | 0 | 350000 | 0 |  | 0 | No
136 | HQ-A-17-62481 | Austin HQ (Complex) Exterior Lighting Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Upgrade lighting fixtures, floodlights, yard lights, at the HQ complex | General Revenue (Fund 0001) |  | 15359.5 | 2017-12-14 | 100% | 100% |  | 15359.5 |  |  | 0 | No
137 | 1-SHE-17-62461 | Sherman Sub district Office (Reg 1) Roof Replacement 1413 Texoma Parkway Sherman, Texas 75090 | Roof Replacement (approx. 5,160 sf - main/storage) | General Revenue (Fund 0001) |  | 176500 | 2018-03-23 | 100% | 100% | 86762.5 | 88250 |  |  | 1487.5 | No
138 | HQ-A-17-62431 | Austin HQ (Complex) Old Dormitory Lighting Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Upgrade lighting fixtures in floors 2 and 3 in the old dormitory | General Revenue (Fund 0001) |  | 22698.52 | 2018-01-05 | 100% | 100% |  | 22698.52 |  |  | 0 | No
139 | 2-CON-17-62913 | Brenham Area Office (Reg 2) Site Work Upgrade 975 Hwy 290 West. Brenham, Texas 77834 | Repair drainage issues that is causing flooding into the building. | General Revenue (Fund 0001) |  | 36750 | 2017-07-31 | 100% | 100% | 0 | 36750 | 0 |  | 0 | No
140 | 1-IRV-17-62461 | Irving Waiver Facility (Reg 1) 1613 W Irving Blvd Irving, Texas | Metal Roof Repair | General Revenue (Fund 0001) |  | 28875 | 2017-08-01 | 100% | 100% | 0 | 28875 | 0 |  | 0 | No
141 | 3-COR-17-62421 | Corpus Christi District Office (Reg 3) Access Control System Upgrade 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Statewide Unexpected DM repairs/Project Contingency: Upgrade Access Control system for the District Office | General Revenue (Fund 0001) |  | 48159.63 | 2018-06-08 | 100% | 100% |  |  | 4922 | 43238.09 | -0.46 | No
142 | 1-FTW-17-62481 | Fort Worth DL Office (Reg 1) Sewer System Repairs 6413 Woodway Drive Fort Worth, Texas 76133 | Statewide Unexpected DM repairs/Project Contingency: Repair sewer system. | General Revenue (Fund 0001) |  | 14690 | 2017-01-12 | 100% | 100% | 0 | 14690 | 0 |  | 0 | No
143 | 1-SUL-17-62461 | Sulphur Springs Area Office (Reg 1) Roof Replacement 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Statewide Unexpected DM repairs/Project Contingency: Roof Replacement. Roof is leaking and beyond repair. Install metal roof | General Revenue (Fund 0001) |  | 105000 | TBD by TFC | 0% | 0% | 0 | 105000 | 0 |  | 0 | No
144 | 2-HUN-17-62481 | Huntsville Area Office (Reg 2) Sewer System Upgrade 523 South Highway 75 North Huntsville, Texas 77320 | Statewide Unexpected DM repairs/Project Contingency: Repair and upgrade sewer system to tie into new city line and remove septic tanks. | General Revenue (Fund 0001) |  | 9585 | 2017-05-04 | 100% | 100% | 0 | 9585 | 0 |  | 0 | No
145 | 6-WCL-17-62441 | Waco Crime Lab (Reg 6) Replace Split System 1617 E. Crest Dr. Waco, Texas 76705 | Statewide Unexpected DM repairs/Project Contingency: Replace Split System. | General Revenue (Fund 0001) |  | 12720 | 2017-10-03 | 100% | 100% |  | 12720 |  |  | 0 | No
146 | 6-WAC-17-62421 | Waco District Office (Reg 6) Security Access System Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Statewide Unexpected DM repairs/Project Contingency: Replace old security card access system. | General Revenue (Fund 0001) |  | 42580.61 | 2018-04-12 | 100% | 100% |  | 42580.61 |  |  | 0 | No
147 | 6-Aus-17-62431 | Austin North DL Office (Reg 6) Automatic Door Opener 6121 North Lamar Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Install automatic door openers for the public entrance to the DL office. | General Revenue (Fund 0001) |  | 3000 | 2017-08-29 | 100% | 100% | 0 | 2257.5 | 0 |  | 742.5 | No
148 | 6-SAN-17-62441 | San Antonio Regional HQ (Reg 6) RTU Replacement 6502 South New Braunfels Ave San Antonio, Texas 78223 | Statewide Unexpected DM repairs/Project Contingency: Replace failed RTU. (50 ton) | General Revenue (Fund 0001) |  | 51900 | 2018-03-01 | 100% | 100% |  |  |  | 51900 | 0 | No
149 | HQ-A-17-62431 | Austin HQ (Complex) Building A Procurement Lighting Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Upgrade existing lighting in the procurement area, building A to LED lighting | General Revenue (Fund 0001) |  | 17386.93 | 2018-04-27 | 100% | 100% |  | 29891.32 |  |  | -12504.39 | No
150 | HQ-A-17-62441 | Austin HQ (Complex) Building K Replacement of AHU 5805 North Lamar Blvd Austin, Texas 78752 | Replace existing AHU which is end of life. | General Revenue (Fund 0001) |  | 9534 | 2017-08-30 | 100% | 100% |  | 9534 |  |  | 0 | No
151 | 1-GAR-17-62441 | Garland Regional Headquarters (Reg 1) Chiller Replacement 350 West IH-30 Garland, Texas 75043 | Statewide Unexpected DM repairs/Project Contingency: Replace 60 ton air cooled chiller | General Revenue (Fund 0001) |  | 52000 | 2017-10-12 | 100% | 100% |  | 52000 |  |  | 0 | No
152 | 4-EHQ-16-62441 | Houston Regional Headquarters (Reg 2) Chiller Repair 12230 West Road Jersey Village, Texas 77065 | Statewide Unexpected DM repairs/Project Contingency: Chiller #1 Repair at Region II HQ facility | General Revenue (Fund 0001) |  | 10330 | 2016-01-20 | 100% | 100% |  |  |  | 10330 | 0 | No
153 | 4-EHQ-16-62441 | Houston Regional Headquarters (Reg 2) Boiler Repair 12230 West Road Jersey Village, Texas 77065 | Statewide Unexpected DM repairs/Project Contingency: Boiler #1 Repair at Region II HQ facility | General Revenue (Fund 0001) |  | 5000 | 2017-08-08 | 100% | 100% |  | 5000 |  |  | 0 | No
154 | 6-VIC-16-62441 | Victoria sub district Office (Reg 6) CID HVAC Replacement 8802 North Navarro Victoria, Texas 77904 | Statewide Unexpected DM repairs/Project Contingency: HVAC in CID building Replacement | General Revenue (Fund 0001) |  | 13550 | 2016-09-28 | 100% | 100% |  |  |  | 13550 | 0 | No
155 | ST-BAS-17-62341 | Statewide Building Automation Systems | Add Building Automation Systems as needed statewide. TFC has been delegated this funding | General Revenue (Fund 0001) |  | 100000 | TBD by TFC | 0% | 0% |  | 100000 |  |  | 0 | No
156 | ST-TFC-17 - 62636 | TFC Contingency | Added contingency TFC's projects | General Revenue (Fund 0001) |  | 240373 | TBD by TFC | NA | NA |  | 240373 |  |  | 0 | No
157 | 3-CONB-17-62907 | Alice Area Office (Reg 3) Roof Replacement 300 South Johnson Alice, Texas 78332 | Statewide Unexpected DM repairs/Project Contingency-Bond: Inspected roof due to reported leaks, replace deteriorated roof system. | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 65000 | 2017-04-28 | 100% | 100% | 0 | 65000 | 0 |  | 0 | No
158 | HQ-A-17-62911 | Austin HQ (Bldg. G) Chiller Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: emergency replacement of Chiller at Building G, HQ | G.O. Bond savings from 80th Legislative $200M bond package. |  | 243395 | 2017-08-31 | 100% | 100% |  | 228995 |  |  | 14400 | No
159 | 2-CONB-17-62912 | Houston Dacoma DL Office (Reg 2) Exterior Lighting Upgrade 4545 Dacoma Road Houston, Texas 77092 | Statewide Unexpected DM repairs/Project Contingency-Bond: Replace exterior wall packs, 4 pole lights and under canopy lighting with LED. | G.O. Bond savings from 80th Legislative $200M bond package. |  | 13260 | 4/31/17 | 100% | 100% | 0 | 13260 | 0 |  | 0 | No
160 | 5-CONB-17-62916 | Sweetwater Area Office (Reg 5) Roof Replacement 600 Northwest Georgia Sweetwater, Texas 79556 | Statewide Unexpected DM repairs/Project Contingency: Roof Replacement | G.O. Bond savings from 80th Legislative $200M bond package. |  | 60685.45 | 2017-07-27 | 100% | 100% | 0 | 60685.45 | 0 |  | 0 | No
161 | 4-CONB-17- 62919 | Midland Sub District Office (Reg 4) Generator Replacement 2405 S. Loop 250 West Midland, Texas 79703 | Statewide Unexpected DM repairs/Project Contingency: Generator Replacement and upgrade emergency power distribution | G.O. Bond savings from 80th Legislative $200M bond package. |  | 350000 | TBD by TFC | 0% | 0% | 0 | 0 | 0 | 0 | 350000 | No
162 | HQ-CONB | Tactical Training Center (HQ) Asphalt Remedy 810 County Road 240 Florence, Texas 76527 | Statewide Unexpected DM repairs/Project Contingency. Asphalt Remedy | G.O. Bond savings from 80th Legislative $200M bond package. |  | 200000 | 2019-01-31 | 0% | 0% |  |  |  |  | 200000 | No
163 | HQ-CONB-17-62918 | Tactical Training Center (HQ) Security Replacement 810 County Road 240 Florence, Texas 76527 | Statewide Unexpected DM repairs/Project Contingency: Replace and upgrade security system | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 106447.76 | 2019-08-31 | 25% | 0% | 0 |  | 0 |  | 106447.76 | No
164 | HQ-CONB | Houston Regional Headquarters Crime Lab (Reg 2) Boiler Repair 12230 West Road Jersey Village, Texas 77065 | Statewide Unexpected DM repairs/Project Contingency: Houston Crime Laboratory | G.O. Bond savings from 80th Legislative $200M bond package. |  | 105100 | TBD | 100% | 0% |  |  |  |  | 105100 | No
165 | 3-LAR-18-62919 | Laredo Crime Laboratory (Reg 3) Retro Commissioning & Verification Study 1901 Bob Bullock Loop Laredo, Texas 78043 | Statewide Unexpected DM repairs/Project Contingency: Laredo Crime Laboratory continues to experience HVAC control issues. Retro commissioning and verification study will be conducted by an engineer. | G.O. Bond savings from 80th Legislative $200M bond package. |  | 100000 | TBD by TFC | 0% | 0% |  |  |  |  | 100000 | No
166 | 4-MID-18-62931 | Midland District Office (Reg 4) Multi-Trade DM Project 2405 S. Loop 250 West Midland, Texas 79703 | Multi-trade deferred maintenance project | G.O. Bond savings from 80th Legislative $200M bond package. |  | 1600000 | TBD by TFC | [6 empty] | 1600000 | Yes
167 | HQ-B-17-62972 | Austin HQ (Building B) Building B Renovation 5805 North Lamar Blvd Austin, Texas 78752 | Complete renovations to vacated crime laboratory area and DM upgrades. | G.O. Bond savings from 80th Legislative $200M bond package. | 0 | 5100000 | 2020-03-31 | 100% | 30% | 0 | 0 | 537815 | 151785 | 4410400 | No
| Consolidated | Projects not funded | Summary of projects not funded that were originally submitted 9-15-15 to the JOC |  | 13267625.66 |  |  | NA | NA |  |  |  |  | 0
|  |  |  | Totals: | 38778877 | 38778876.8 |  |  |  | 505768.39 | 21746736.54 | 1168877.6 | 1292817.38 | 14064676.89
Returned to correct line item. CORRECTED REQ
Note on L57: Duecker, Lisa: Went to 62753
Note on N57: Duecker, Lisa: Went to 62753
Note on K58: Duecker, Lisa: Issued in E-pro PO18901, $9,500 not in usas
Note on M58: Duecker, Lisa: Issued in E-pro PO18901, $9,500 not in usas
Note on L146: tw08469: 9/15/17 Lisa showed $12,812.59 enc and $14,324.58 Exp
Note on N146: tw08469: 9/15/17 Lisa showed $12,812.59 enc and $14,324.58 Exp
Note on G169: tw08469: Why is this amount lower on this report? I think we are sending the total $350k to TFC.

## DPS Sup.
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2018-12-15
| Prepared by: | Tavia Wendlandt
Project Priority | SUPPLMENTAL NOTES
DM84 SUPPLEMENTAL NOTES
60 | Vendor withdrew from Project. In the process of Rebidding.
63-67 | TFC will handle the listed various site components as one project in Garland. If approved, next JOC report will combine these lines into one project.
73-76, 94 | DM84 Amarillo project to be combined into one line with JOC approval for next report.
86,87, 89-92, 104 | TFC will handle the listed various site components as one project in Eagle Pass. If approved, next JOC report will combine these lines into one project.
106 | DM84 Austin interior finish upgrade was funded through other sources.
107 (Cont.) | 84th Leg - Rider 40 appropriations ($17.7M) - project savings will offset contingency negative balance.
108 (Bond Cont.) | 84th Leg - No appropriated funds. Used Bond savings to fund part of $21M authorized projects. Primary Bond Project savings will offset bond contingency negative balance.
166 | The Midland District Office multi- DM project originally funded in 83rd session, required additional funding to award to general contractor. Utilizing bond project savings from closed projects.

## TMD
| Agency: | Texas Military Department - Agency 401
| Date: | 2018-11-30 | [9 empty] | 2018-11-30
Prepared by:
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 48150090 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | The project will repair 69,029 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 25%, Federal Funds 75% | 2000000 | 1346642.33 | 2018-01-16 | 100% | 100% | 0 | 1346642.33 | 0 | yes
2 | 48140070 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | The project will repair an existing 19,064 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 1500000 | 1545910.65 | 2017-12-14 | 100% | 100% | 0 | 1545910.65 | 0 | yes
3 | 48140040 | San Marcos Readiness Center 201 City Park, San Marcos 78666 | The project will repair an existing 10,776 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 1125000 | 981594.53 | 2017-10-25 | 100% | 76% | 63030.46 | 918564.07 | 0 | yes
4 | 48150110 | Grand Prairie 1013 Lake Crest Drive Grand Prairie 75051 | The project will repair 60,943 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 3875000 | 3951827.68 | 2018-02-26 | 100% | 99% | 6289.29 | 3945538.39 | 0 | yes
5 | 48160100 | Fairview Readiness Center 4601 Fairview Drive Austin 78731 | The project will repair an existing 50,603 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 25%, Federal Funds 75% | 1375000 | 1748580.54 | 2018-11-30 | 100% | 83% | 26733.03 | 1721847.51 | 0 | yes
6 | 48130053 | Camp Mabry Readiness Center (Bldg 75) 2200 West 35th Street Austin, 78703 | The project will repair an existing 72,358 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 4000000 | 3231320 | 2017-11-28 | 100% | 82% | 8257.5 | 3223062.5 | 0 | yes
7 | 48150060 | El Paso Hondo Pass Readiness Center 9100 Gateway North El Paso 79924 | The project will repair an existing 44,555 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2875000 | 3343712.85 | 2018-11-30 | 100% | 92% | 38725.7 | 3304987.15 | 0 | yes
8 | 48170090 | Temple Readiness Center 8502 Airport Road. Temple 76502 | The project will repair an existing 46,058 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 25%, Federal Funds 75% | 1437500 | 1785430.97 | 2019-01-18 | 100% | 84% | 19750 | 1765680.97 | 0 | yes
9 | 48140061 | Denison Readiness Center 1700 Loy Lake Denison 75020 | The project will repair an existing 18,541 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 1375000 | 1624161.47 | 2018-11-30 | 100% | 86% | 6959.6 | 1617201.87 | 0 | yes
|  |  |  | Totals: | 19562500 | 19559181.02 |  |  |  | 169745.58 | 19389435.44 | 0
-3318.98
3318.98

## TMD Sup.
| Agency: | Texas Military Department - Agency 401
| Date: | 2018-11-30
Prepared by:
Project Priority | Supplemental Information
| Project Name & Location | Total Estimated Project Budget | Federal Share | Federal Share Encumbered | Federal Share Expended | Remaining Federal Share | Comments
1 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | 8000000 | 6201532 | 0 | 6201532 | 0 | Project Complete
2 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | 3000000 | 1733565.64 | 0 | 1733565.64 | 0 | Project Complete
3 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | 2250000 | 1227859.34 | 389873.74 | 837985.6 | 0 | Project in Construction
4 | Grand Prairie, 1013 Lake Crest Drive, Grand Prairie 75051 | 7750000 | 3136001.74 | 709.8 | 3135291.94 | 0 | Project in Construction
5 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | 5500000 | 6748986.87 | 1234027.58 | 5514959.29 | 0 | Project in Construction
6 | Camp Mabry Readiness Center (Bldg 75) 2200 West 35th Street Austin, 78703 | 8000000 | 3567478.58 | 1171434.96 | 2396043.62 | 0 | Project in Construction
7 | El Paso Hondo Pass Readiness Center 9100 Gateway North El Paso 79924 | 5750000 | 3059740.26 | 250744.12 | 2808996.14 | 0 | Project in Construction
8 | Temple Readiness Center 8502 Airport Road. Temple 76502 | 5750000 | 5546216.04 | 1037181.15 | 4509034.89 | 0 | Project in Construction
9 | Denison Readiness Center 1700 Loy Lake Denison 75020 | 2750000 | 1717867.31 | 331339.93 | 1386527.38 | 0 | Project in Construction
|  |  | 32939247.78 | 4415311.28 | 28523936.5 | 0

## TPWD
| Agency: | Texas Parks and Wildlife Department
| Date: | 2018-12-15 | [12 empty] | 2018-12-15
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Current Estimated Project Budget Q1 | Estimated Substantial Completion Date | % Design Completion | % Design Completion | % Const. Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, TX,77571 (Harris County) | Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | 5166 - General Revenue Dedicated | 25000000 | 23943608.59 | 23943707.43 | 2019-02-25 | 100% | 100.00% | 76% | 82% | 660043 | 23283664.43 | 0
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 200000 | 189755.87 | 189755.87 | 2020-09-03 17:00 | 95% | 95% | 0% | 0% | 30430.88 | 159324.99 | 0
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Planning and design costs to upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | 5166 - General Revenue Dedicated | 1000000 | 565745.79 | 565756.85 | 2020-02-18 17:00 | 95% | 95% | 36% | 52% | 131788.47 | 433968.38 | 0
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | 5166 - General Revenue Dedicated | 225000 | 147389.81 | 147389.81 | 2020-04-08 | 60% | 60% | 0% | 0% | 36527.88 | 110861.93 | 0
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Planning and design costs to Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 533000 | 558685.85 | 548413.14 | 2018-03-23 17:00 | 100% | 100% | 100% | 100% | -6.8106e-11 | 548413.14 | 0
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | 5166 - General Revenue Dedicated | 1200000 | 5978845.61 | 5978880.23 | 2019-02-12 | 100% | 100% | 57% | 65% | 1762684.52 | 4216195.71 | 0.25
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 2000000 | 1187243.32 | 1187243.32 | 2018-10-05 17:00 | 100% | 100% | 88% | 99% | 22969.4 | 1164273.92 | 0
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Planning and design costs to renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | 5166 - General Revenue Dedicated | 500000 | 253026.94 | 253108.72 | 2022-04-20 12:00 | 30% | 60% | 0% | 0% | 26060.92 | 227047.8 | 0
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning and design costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | 5166 - General Revenue Dedicated | 250000 | 332829.52 | 332829.52 | 2023-02-08 | 60% | 60% | 0% | 0% | 100499.66 | 232329.86 | 0
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Preliminary engineering costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | 5166 - General Revenue Dedicated | 400000 | 223183.89 | 223183.89 | 2020-07-24 17:00 | 60% | 95% | 0% | 0% | 7055.06 | 216128.83 | 0
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 650000 | 771292.64 | 771292.64 | 2018-09-26 17:00 | 100% | 100% | 98% | 99% | 43493.52 | 727799.12 | 0
12 | 117505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 3677658.63 | 3677658.63 | 2019-03-05 17:00 | 100% | 100% | 29% | 64% | 2416992.1 | 1260666.53 | 0
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 1000000 | 909932.79 | 909932.97 | 2018-10-17 17:00 | 100% | 100% | 92% | 93% | 67425.41 | 842507.56 | -0.18
14 | 124729 | San Jacinto Battleground SHS - Residence Replacements 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Replace two residences and remove from a sensitive archaeological site. | 5166 - General Revenue Dedicated | 830000 | 73125.71 | 73125.71 | N/A | 100% | 100% | 0% | 0% | -1.8021e-12 | 73125.71 | 0
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 480000 | 484173.83 | 484174.19 | 2018-10-04 17:00 | 100% | 100% | 73% | 98% | 25435.51 | 458738.68 | -0.36
16 | 127358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 2713100 | 1805318.19 | 1805318.19 | 2018-09-11 | 100% | 100% | 95% | 95% | 15779.32 | 1789538.87 | 0
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | 5166 - General Revenue Dedicated | 413600 | 760358.18 | 760358.18 | 2018-07-02 17:00 | 100% | 100% | 100% | 100% | 13334.96 | 747023.22 | 0
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace multiple obsolete septic systems to meet TCEQ requirements. | 5166 - General Revenue Dedicated | 306800 | 323341.3 | 323341.3 | 2018-02-26 | 100% | 100% | 100% | 100% | -6.35e-12 | 323341.3 | 0
19 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and design costs for replacement of the under-sized and damaged ponds, hatchery buildings, infrastructure, and jetty pump intake. | 5166 - General Revenue Dedicated (SWFS) | 4131500 | 2203974.07 | 2203974.07 | 2023-05-10 | 10% | 10% | 0% | 0% | 1724507.91 | 479466.16 | 0
20 | 127436 | Galveston Island SP - Beachside Redevelopment 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Design costs to redevelop Galveston Island State Park's beachside in accordance with the GISP Redevelopment Master Plan. Construction plans include one restroom, one RV dump station, one boardwalk, multiple tent platforms, 30 multiple use campsites with electrical / water service, three group shelters, and 20 day-use picnic shelters. | 5166 - General Revenue Dedicated | 350000 | 413824.15 | 413824.15 | 2021-12-08 17:00 | 15% | 30% | 0% | 0% | 249799.23 | 164024.92 | 0
21 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Planning and design costs to renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. | 5166 - General Revenue Dedicated | 1500000 | 263414.73 | 263414.73 | 2019-10-08 17:00 | 10% | 60% | 0% | 0% | 100856.94 | 162557.79 | 0
22 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | 5166 - General Revenue Dedicated (SWFS) | 1027000 | 656699.2 | 656699.2 | 2018-12-10 | 100% | 100% | 100% | 100% | -6.5647e-11 | 656699.2 | 0
23 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | 5166 - General Revenue Dedicated (SWFS) | 968500 | 896786.3 | 896786.3 | 2018-11-20 17:00 | 100% | 100% | 72% | 95% | 97692.64 | 799093.66 | 0
24 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | 5166 - General Revenue Dedicated | 150000 | 97309.33 | 97309.33 | 2020-01-17 17:00 | 30% | 95% | 0% | 0% | 23765 | 73544.33 | 0
25 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | 5166 - General Revenue Dedicated (SWFS) | 507000 | 443717.63 | 443717.63 | 2018-07-13 17:00 | 100% | 100% | 100% | 100% | 14405.59 | 429312.04 | 0
26 | 117507 | Garner SP - Dining Halls and Barracks Remodel US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to remodel Group Dining Hall at Shady Meadows and Cypress Springs camping areas to include electrical and HVAC system upgrades, kitchen remodels, insulation for walls and ceilings, window and door repairs or replacements, roof and fascia replacement and interior wall and ceiling finish-out. Remodel Cypress Springs Barracks to include new roofs, electrical upgrades, HVAC installation, door and window repairs and replacements, and interior finish upgrades. Renovations will enhance visitors' experiences and increase revenue. | 5166 - General Revenue Dedicated | 325000 | 46396.83 | 46396.83 | N/A | 30% | 100% | 0% | 0% | -2.907e-12 | 46396.83 | 0
27 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Preliminary engineering and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | 5166 - General Revenue Dedicated | 106000 | 1114420.41 | 1114420.41 | 2021-12-30 17:00 | 30% | 60% | 0% | 0% | 680732.52 | 433687.89 | 0
28 | 117260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | 5166 - General Revenue Dedicated | 834600 | 565039.12 | 565039.12 | 2018-03-09 17:00 | 100% | 100% | 100% | 100% | -3.4788e-11 | 565039.12 | 0
29 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | 5166 - General Revenue Dedicated | 390000 | 240164.49 | 240164.49 | 2020-08-17 17:00 | 30% | 60% | 0% | 0% | 4801.02 | 235363.47 | 0
30 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Advance planning costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | 5166 - General Revenue Dedicated | 587500 | 521380.82 | 521380.82 | 2023-02-03 | 10% | 10% | 0% | 0% | 456036.18 | 65344.64 | -1.6007e-10
31 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 859800 | 191681.35 | 191681 | 2019-04-03 | 100% | 100% | 0% | 0% | 61804.39 | 129876.96 | 0
32 | 116769 | Bastrop SP - Dam Replacement 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning and design costs to replace the breached dam due to the 2015 memorial day flooding. | 5166 - General Revenue Dedicated | 1000000 | 1180657.87 | 1179713.17 | 2021-09-20 | 30% | 60% | 0% | 0% | 695609.46 | 484103.71 | 0
32-A | 118102 | Bastrop SP - Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilization of shoreline adjacent to Cabins #1 and #12. | 5166 - General Revenue Dedicated | 0 | 1068075.81 | 1037454.8 | 2018-01-11 17:00 | 100% | 100% | 100% | 100% | -6.9232e-11 | 1037454.8 | 0
33 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | 5166 - General Revenue Dedicated | 978400 | 2030390.78 | 2030390.78 | 2018-09-11 | 100% | 100% | 100% | 100% | 34486.75 | 1995904.03 | 0
34 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace one restroom complex and renovate the day-use restroom with facilities to include replacement of obsolete mechanical systems and damaged structures. Renovations will include shower and restroom accommodations, accessible parking routes, utility upgrades and connections, a new lift station and force main, a temporary shower and restroom facility, and associated site work, in order to meet current and projected visitor demand. | 5166 - General Revenue Dedicated | 2444000 | 2818716.65 | 2818717.06 | 2018-10-10 17:00 | 100% | 100% | 23% | 62% | 1229410.64 | 1589306.42 | 0
35 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | 5166 - General Revenue Dedicated | 250000 | 153619.9 | 153619.9 | 2019-08-05 17:00 | 0% | 100% | 0% | 0% | 1392.78 | 152227.12 | 0
36 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | 5166 - General Revenue Dedicated | 598000 | 1721720.24 | 1721720.24 | 2018-10-17 17:00 | 100% | 100% | 94% | 94% | 220977.64 | 1500742.6 | 0
37 | NA | Statewide - Unspecified State Park Boat Ramp Repairs - Statewide | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 1300000 | 0 | 0 | N/A | 100% | 100% | 0% | 0% | 0 | 0 | 0
37-A | 115356 | Choke Canyon State Park (South Shore Unit) - Boat Ramp 358 Recreation Rd 8 Calliham, TX 78007 (Live Oak County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 401146.6 | 392935.57 | 2018-03-05 17:00 | 100% | 100% | 100% | 100% | 9.0948e-13 | 392935.57 | 0
37-B | 115389 | Fort Parker State Park - Boat Ramp 194 Park Rd 28 Mexia, Tx 76667 (Limestone County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 830089.77 | 830089.77 | 2018-08-17 | 100% | 100% | 100% | 100% | 3.1818e-11 | 830089.77 | 0
37-C | 116036 | Inks Lake State Park - Boat Ramp 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 112765.89 | 112765.89 | 2019-05-06 17:00 | 100% | 100% | 0% | 0% | 21492.12 | 91273.77 | 0
37-D | 117036 | Ray Roberts Lake SP - Isle du Bois Unit - Boat Ramp 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 115000.17 | 115000.17 | 2018-06-29 | 100% | 100% | 100% | 100% | 3.4461e-13 | 115000.17 | 0
38 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 2564191.31 | 2564191.31 | 2019-01-09 17:00 | 100% | 100% | 57% | 72% | 288337.36 | 2275853.95 | 0
39 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Advance planning costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | 5166 - General Revenue Dedicated | 588000 | 79659.61 | 79659.61 | 2023-06-14 17:00 | 10% | 10% | 0% | 0% | 208.84 | 79450.77 | 0
40 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Planning and design costs to install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | 5166 - General Revenue Dedicated | 240400 | 70798.73 | 70798.73 | 2019-12-30 17:00 | 60% | 60% | 0% | 0% | 6862.65 | 63936.08 | 0
41 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | 5166 - General Revenue Dedicated (SWFS) | 1710000 | 2925883.62 | 2925883.62 | 2019-01-11 17:00 | 100% | 100% | 50% | 73% | 1043431.08 | 1882452.54 | 0
42 | 115922 | Abilene SP - Swimming Pool and CCC Bathhouse Repairs FM 89, 150 Park Rd 32 Tuscola, TX 79562 (Taylor County) | (Project Postponed) Planning and design costs to repair and renovate the swimming pool and CCC bathhouse. | 5166 - General Revenue Dedicated | 850000 | 250.39 | 250.39 | N/A | 0% | 0% | 0% | 0% | 0 | 250.39 | 1.7337e-12
43 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | 5166 - General Revenue Dedicated | 478800 | 325548.7 | 325548.7 | 2018-07-18 | 100% | 100% | 100% | 100% | -2.9095e-11 | 325548.7 | 0
44 | 114906 | Austin Headquarters Complex - Heating Ventilation Air-Conditioning (HVAC) Units Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | (Project Cancelled) Replace two deteriorating, independent Liebert HVAC units in the Computer Room that houses the server at the TPWD Austin Headquarters Complex. | 5166 - General Revenue Dedicated | 144348 | 0 | 0 | N/A | 0% | 0% | 0% | 0% | 0 | 0 | 0
45 | 117417 | Austin Headquarters Complex - Fire Escape and Storage Building 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | 5166 - General Revenue Dedicated | 73152 | 58984 | 58984 | 2017-11-14 | 100% | 100% | 100% | 100% | 92 | 58892 | 0
46 | TBD | Statewide - Unspecified State Park2015 Flood Damage Repairs | Funding reserved to address statewide 2015 flood damages. A comprehensive damage assessment has not yet been completed due to high-water levels and site inaccessibility. | 5166 - General Revenue Dedicated | 8058550 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | 0 | 0 | 0
46-A | 136507 | Bastrop SP - Boundary Fence Replacement - Flood Recovery 130 HWY 21E Bastrop, TX 78602-0518 (Bastrop County) | Replace approximately 27 miles of a four-strand barbed wire boundary fence and cedar and metal posts around Bastrop State Park and Park Road 1C, which sustained sufficient fire damage in 2011. | 5166 - General Revenue Dedicated | 0 | 76222.15 | 76222.15 | 2018-02-15 | 100% | 100% | 100% | 100% | 0 | 76222.15 | 0
46-B | 118450 | Buescher SP - Boundary Fence Replacement - Fire Recovery 100 Park Road 1E Smithville, TX 78957-0075 (Bastrop County) | Replace approximately 7.5 miles of boundary fence around Buescher State Park and along Park Road 1-C, a majority of which sustained significant damage or was totally destroyed in a wildfire that began mid October 2015. | 5166 - General Revenue Dedicated | 0 | 646938.59 | 646938.59 | 2018-10-05 17:00 | 100% | 100% | 93% | 98% | -3.6088e-11 | 646938.59 | 0
46-C | 190059 | Cedar Hill SP - State Park Managed Repairs - Flood Recovery 1570 FM 1382 Cedar Hill, TX 75104 (Dallas County) | Parks temporary repairs for; tree removal, temporary repairs to damaged comfort stations (6 ea), utility repairs for comfort station operations, rinse and clean showers and minor site work around structures. | 5166 - General Revenue Dedicated | 0 | 325436.95 | 325436.95 | N/A | N/A | N/A | 100% | 100% | -2.909e-11 | 325436.95 | 0
46-D | 128269 | Cedar Hill SP - Facility Repairs - Flood Recovery 1570 FM 1382 Cedar Hill, TX 75104 (Dallas County) | Planning and design costs to repair the Day Use Swim Beach, replacement of multiple restrooms, a pavilion and overall shoreline reinforcement which were damaged by the multiple flooding events in 2015 and 2016. | 5166 - General Revenue Dedicated | 0 | 533147.5 | 533147.5 | 2020-09-25 | 30% | 60% | 0% | 0% | 67800 | 465347.5 | 0
46-E | 190061 | Lake Somerville SP & Trailway- State Park Managed - Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | Park operations to repair multiple lift station controls; replace park signage, handrails and lighting; repair site paving, erosion and culvert cleaning; dead tree removal; replace campfire rings and tables; restore campsite utility fixtures and pavilion HVAC units. | 5166 - General Revenue Dedicated | 0 | 302500.58 | 302500.58 | N/A | N/A | NA | 100% | 100% | 4.2011e-12 | 302500.58 | 0
46-F | 128301 | Lake Somerville SP - Birch Creek Unit - Facility Repairs - Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | Planning and design costs to repair facilities in the day use area, the Cedar Elm camping area, the Old Hickory and Bucktail bridge(s) which were damaged by multiple flooding events in 2015 and 2016. | 5166 - General Revenue Dedicated | 0 | 247778.73 | 247778.73 | 2020-08-07 | 30% | 60% | 0% | 0% | 1421.34 | 246357.39 | 0
46-G | 128323 | Lake Somerville SP - Trailway - Bridge Repairs- Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | Planning and design costs to repair multiple bridges, culverts, and access ways along the Somerville Trailway that were damaged by multiple flooding events in 2015 and 2016. | 5166 - General Revenue Dedicated | 0 | 130268.8 | 130268.8 | 2020-06-01 | 60% | 100% | 0% | 0% | -1.2733e-11 | 130268.8 | 0
46-H | 128322 | Lake Somerville SP - Nails Creek Unit - Facility Repairs - Flood Recovery 6280 FM 180 Ledbetter, TX 78946-9512 (Lee County) | Planning and design costs to repair facilities in the day use area, the Cedar Creek camping area, and the Boat Ramp camping area which were damaged by the multiple flooding events in 2015 and 2016. | 5166 - General Revenue Dedicated | 0 | 65778.72 | 65778.72 | 2019-11-14 | 10% | 100% | 0% | 0% | 1150 | 64628.72 | 0
46-I | 190063 | Lake Whitney SP - State Park Managed - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Park operations to repair park wide electrical systems, replace fire rings and grills. General debris cleanup, facilities cleanup, and fish cleaning station repairs. | 5166 - General Revenue Dedicated | 0 | 219854.99 | 219854.99 | N/A | N/A | N/A | 100% | 100% | 4.5475e-13 | 219854.99 | 0
46-J | 118414 | Lake Whitney SP - Camp Loop Restroom - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Restore Restroom #5 at Area E's interior finishes and critical structural components prior to re-opening the facility which was damaged in the 2016 Flood. | 5166 - General Revenue Dedicated | 0 | 441933.19 | 441933.19 | 2018-05-30 | 100% | 100% | 100% | 100% | 3676.09 | 438257.1 | 0
46-K | 118476 | Lake Whitney SP - Facilities Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Planning and design costs to repair multiple facilities throughout the park damaged during multiple 2016 flood events. Impacted areas include the Towash shelter loop, day use area, the group camp & dinning hall, restroom #3, restoom #4, and parkwide shade shelter replacements. | 5166 - General Revenue Dedicated | 0 | 272329.53 | 272329.53 | 2018-10-09 | 30% | 100% | 91% | 100% | 1.549e-12 | 272329.53 | 2.6193e-10
46-L | 118477 | Lake Whitney SP - Erosion Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Planning and design costs to repair errosion damage, a boat ramp, and address soil stabilization that resulted from the multiple 2016 flood events. | 5166 - General Revenue Dedicated | 0 | 407291.52 | 407291.52 | 2021-05-17 | 30% | 60% | 0% | 0% | 269899.88 | 137391.64 | 0
46-M | 137395 | McKinney Falls SP - Restroom #4 Upper Falls North - Flood Recovery 5808 McKinney Falls Pkwy Austin, TX 78744 (Travis County) | Repair interior and exterior finishes damaged by the flood. Work will also address major mechanical, electrical and plumbing systems needed to restore full function of the restroom facility. | 5166 - General Revenue Dedicated | 0 | 177189.66 | 177189.66 | 2017-11-15 17:00 | 100% | 100% | 100% | 100% | 4457.73 | 172731.93 | 0
46-N | 190056 | Mother Neff SP - Clear Log Jam and Remove Debris - Flood Recovery 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | Park operations to clear the log jam debris build up at the bridge crossing that is causing major erosion and river flooding of adjacent properties due to the waters diverted from the river banks. | 5166 - General Revenue Dedicated | 0 | 19392.89 | 19392.89 | N/A | N/A | N/A | 100% | 100% | 7.276e-12 | 19392.89 | 0
46-O | 190060 | Ray Roberts Lake SP - Complex Wide- Hazardous Tree Removal - Flood Recovery 100 PW 4137 Pilot Point, TX 76258-8944 (Denton County) | Park operations to remove dead and hazardous trees as a result of the severe flooding in 2015 and 2016 | 5166 - General Revenue Dedicated | 0 | 24014.79 | 24014.79 | N/A | N/A | N/A | 100% | 100% | 0 | 24014.79 | 0
46-P | 128302 | Ray Roberts Lake SP - Complex Wide- Site Repairs - Flood Recovery 100 PW 4137 Pilot Point, TX 76258-8944 (Denton County) | Planning and design costs to repair concrete walks, shoreline stabilization, playground areas, and the green belt trail which was damaged during the multiple flooding events in 2015 and 2016. | 5166 - General Revenue Dedicated | 0 | 357044.51 | 357044.51 | 2019-12-23 | 60% | 100% | 0% | 0% | 37223.4 | 319821.11 | 0
46-Q | 190062 | Stephen F Austin SHS - State Park Managed Repairs - Flood Recovery 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Park operations to repair MEP utilities, building and office furnishings; dead tree removal, trail repairs, exhibit replacements, fence line repairs; camp loop pedestal repairs, picnic table replacements, playground repairs and fire ring replacement. | 5166 - General Revenue Dedicated | 0 | 355779.15 | 355779.15 | N/A | N/A | N/A | 74% | 74.39% | 91115.01 | 264664.14 | 0
46-R | 128406 | Stephen F Austin SHS - Facility Repairs - Flood Recovery 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Planning and design costs to repair mini cabin(s), screen shelter(s), group dining hall(s), staff residences, the Bullinger Creek bunkhouse, the Nature Center, and multiple restrooms that were damaged during the 2016 flood. | 5166 - General Revenue Dedicated | 0 | 334993.49 | 334993.49 | 2020-04-23 | 10% | 60% | 0% | 0% | 160529.5 | 174463.99 | 0
47 | 128233 | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Pressure wash and repaint elevated water tank per TCEQ regulations. | 5166 - General Revenue Dedicated | 300000 | 425693.13 | 425693.13 | 2018-09-14 | 100% | 100% | 0% | 100% | -1.3637e-11 | 425693.13 | 0
48 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | 5166 - General Revenue Dedicated | 4380000 | 4369347.28 | 4369347.28 | 2018-04-17 10:00 | 100% | 100% | 100% | 100% | 0.01 | 4369347.27 | 0
49 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | 5166 - General Revenue Dedicated | 3558000 | 3303772.44 | 3303772.44 | 2018-10-10 17:00 | 100% | 100% | 92% | 95% | 283634.58 | 3020137.83 | 0
50 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | 5166 - General Revenue Dedicated | 279950 | 450262.62 | 450262.62 | 2018-01-17 17:00 | 100% | 100% | 100% | 100% | -6.0214e-11 | 450262.62 | 0
51 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | 5166 - General Revenue Dedicated | 170000 | 165202.99 | 165202.99 | 2018-08-14 17:00 | 100% | 100% | 100% | 100% | 9460 | 155742.99 | 0
52 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | 5166 - General Revenue Dedicated | 365000 | 509898.34 | 509898.34 | 2019-01-30 12:00 | 100% | 100% | 85% | 85% | 70671.13 | 439227.21 | 0
53 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | 5166 - General Revenue Dedicated | 485000 | 681824.87 | 681824.87 | 2019-02-13 17:00 | 100% | 100% | 87% | 87% | 71688.29 | 610136.58 | 0
54 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | 5166 - General Revenue Dedicated | 570000 | 844774.83 | 844774.83 | 2019-04-22 17:00 | 100% | 100% | 42% | 42% | 228776.65 | 615998.18 | 0
55 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | 5166 - General Revenue Dedicated | 317000 | 0 | 0 | 2020-01-20 17:00 | 6% | 30% | 0% | 0% | 0 | 0 | 0
56 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Planning and design cost for replacing the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | 5166 - General Revenue Dedicated | 3000000 | 605326.79 | 605326.79 | 2023-09-04 12:00 | 30% | 30% | 0% | 0% | 457826.37 | 147500.42 | 0
57 | 127872 | Mustang Island SP - Foundation repairs for (2) residences 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Repair two residences' pilings and beams, which are degraded due to rot. | 5166 - General Revenue Dedicated | 225000 | 58572.12 | 58572.12 | 2020-06-15 17:00 | 100% | 100% | 0% | 0% | 13682.77 | 44889.35 | 0
58 | 8213 | Mother Neff SP - CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | (Project Postponed) - Stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. | 5166 - General Revenue Dedicated | 350000 | 0 | 0 | N/A | 100% | 100% | 0% | 0% | 0 | 0 | 0
59 | 118540 | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. The development plan includes a small site headquarters building for visitor check-in and the remodeling of the existing lodge to include staff offices and interpretive space. The development plan is still pending TNC approval. | 5166 - General Revenue Dedicated | 150000 | 852768.53 | 852768.53 | 2022-09-29 | 5% | 30% | 0% | 0% | 550055.54 | 302712.99 | 0
60 | 126107 | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | 5166 - General Revenue Dedicated | 100000 | 115956.21 | 115956.21 | 2019-10-01 | 60% | 60% | 0% | 0% | 591.7 | 115364.51 | 0
61 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, TX 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife intrusion. | 5166 - General Revenue Dedicated (SWFS) | 598000 | 526536.05 | 526536.05 | 2018-10-25 17:00 | 100% | 100% | 92% | 99% | 24857.44 | 501678.61 | 0
62 | 192540 | Buescher State Park - Erosion mitigation and habitat stabilization (Flood Repair) 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilize the soil and mitigate erosion caused by flooding. | 5166 - General Revenue Dedicated | 0 | 386949.83 | 386949.83 | N/A | N/A | N/A | 100% | 100% | 2.9101e-11 | 386949.83 | 0
63 | 125873 | Dickinson Marine Lab - Roof Replacement 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Replace deteriorated office building roof. | 5166 - General Revenue Dedicated (SWFS) | 0 | 413172 | 413172 | 2019-01-10 17:00 | 100% | 100% | 68% | 99% | 104961.68 | 308210.32 | 0
64 | 128535 | CCA Marine Development Center - Repairs to Ponds 1-10 Harvest Kettles 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Repair damaged concrete harvest kettles at Ponds 1-10. These ten ponds are original to the site and are in a stage of decay. Repairs would include structural concrete work and efforts to minimize existing leaks. | 5166 - General Revenue Dedicated (SWFS) | 0 | 108850.85 | 108850.85 | 2018-02-16 | 95% | 100% | 100% | 100% | 0 | 108850.85 | 0
65 | 115897 | Palo Duro Canyon SP - Repairs to Juniper Camp Loop 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Repairs to existing facilities and address storm water drainage issues around the buildings. | 5166 - General Revenue Dedicated | 0 | 25730.68 | 25730.68 | 2017-10-13 | 100% | 100% | 100% | 100% | 0 | 25730.68 | -2.9104e-11
66 | 115900 | Caddo Lake SP - Restroom Replacement 245 Park Rd 2 Karnack, TX (Harrison county) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 0 | 841713.35 | 841713.35 | 2018-11-17 17:00 | 100% | 100% | 87% | 95% | -1.8627e-11 | 841713.35 | 0
67 | 117585 | Statewide - Unspecified Radio Tower Assessments | Perform repairs on the 35 remotely-located, active TPWD radio tower sites, towers, and building structures supporting the radio equipment. Repairs will maintain Federal Communications Commission compliance and will meet obligations to maintain the towers and sites as part of lease agreements. | 5166 - General Revenue Dedicated | 0 | 432530 | 432530 | 2018-06-25 17:00 | 100% | 100% | 100% | 100% | 0.01 | 432529.99 | 0
68 | 118669 | Austin Headquarters Complex - Multiple HVAC System Upgrades 4200 Smith School Road Austin, TX 78744 (Travis County) | Planning and design costs to upgrade and/or replace aging HVAC system(s) at the Austin HQ facilities. | 5166 - General Revenue Dedicated | 0 | 196997.37 | 196997.37 | 2019-07-22 | 60% | 60% | 0% | 0% | 0 | 196997.37 | 0
69 | 127570 | Brownsville Field Station - Replace Storage Building 95 Fish Hatchery Road, Brownsville, TX 78520 (Cameron County) | Construct building addition to the Main Boat and Truck storage facility to increase secure storage capacity from five to twelve vehicles. | 5166 - General Revenue Dedicated (SWFS) | 0 | 761904.12 | 761904.12 | 2018-11-13 17:00 | 100% | 100% | 83% | 83% | 144414.19 | 617489.93 | 0
70 | 128106 | Palmetto SP - Group Camp Area Erosion Control 78 Park Road 11 South Gonzales, TX 78629 (Gonzalez County) | Planning and assessment needed to prepare a Preliminary Engineering Report (PER) of riverbank erosion and stabilization recommendations and final repairs below the Group Camp Area. Planning and Design will be funded with 18/19 funds. | 5166 - General Revenue Dedicated | 0 | 46410 | 46410 | 2022-10-17 17:00 | 30% | 30% | 0% | 0% | 46410 | 0 | 0
71 | 128197 | Galveston Island SP - Repair Historical Residences 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Repairs and upgrades to the historic Stewart House and Ranch House. | 5166 - General Revenue Dedicated | 0 | 68747.25 | 68747.25 | 2018-05-17 17:00 | 100% | 100% | 100% | 100% | -7.276e-12 | 68747.25 | 0
72 | 132416 | Hill Country SNA - Water System Replacement and Distribution 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Replace existing water facilities with a new water distribution network. Add a water treatment system to the main existing well, creating a Public Water System. | 5166 - General Revenue Dedicated | 0 | 140000 | 140000 | 2019-01-30 17:00 | 100% | 100% | 92% | 95% | 19068.98 | 120931.02 | 0
73 | 134236 | Garner SP - Wastewater Treatment Plant Replacement US 83 N Concan, TX 78838 (Uvalde County) | Replace the undersized, leaking wastewater treatment plant with a modernized and efficient system. | 5166 - General Revenue Dedicated | 0 | 45000 | 45000 | 2017-05-30 17:00 | 100% | 100% | 100% | 100% | 0 | 45000 | 0
74 | 137357 | Balmorhea SP - Repair Motel Roofs and Replace Laundry Facility 9207 H. 17S Toyahvale, TX (Reeves County) | Replace the CCC motel building's damaged clay tile roof, and repair critical structural, mechanical, electrical and plumbing systems concealed in the attic space. | 5166 - General Revenue Dedicated | 0 | 1581141.42 | 1581142 | 2019-05-01 | 100% | 100% | 67% | 76% | 360885.2 | 1220256.22 | 0
|  |  |  | Totals: | 91000000 | 89194803.74 | 89144981.77 | [5 empty] | 15341480.84 | 73803500.67 | -0.29

## TDCJ
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2018-12-14 | [9 empty] | 2018-12-14
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 04215005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 | 0 | 51856.38 | 2017-09-14 | N/A | 100% | 0 | 51856.38 | 0
2 | 09915001 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Support Operations | Deferred Maintenance Account No. 5166 | 0 | 60818.03 | 2015-11-23 | N/A | 100% | 0 | 60818.03 | 0
3 | 05014007 | Roach Unit, Childress | Roofing: Repair Roof - ISF | Deferred Maintenance Account No. 5166 | 75600 | 49064.46 | 2016-07-27 | N/A | 100% | 0 | 49064.46 | 0
4 | 00512006 | Clemens Unit, Brazoria | Facility Repair: Resurface Floor - Main Building Kitchen | Deferred Maintenance Account No. 5166 | 40400 | 15535.3 | 2017-05-11 | 100% | 100% | 0 | 15535.3 | 0
5 | 10510005 | Murray Unit, Gatesville | Facility Repair: Install Handicap Accessible Shower - Offender Dorms | Deferred Maintenance Account No. 5166 | 37400 | 29322.32 | 2016-07-19 | 100% | 100% | 0 | 29322.32 | 0
6 | 01015016 | Ellis Unit, Huntsville | Safety: Replace Generator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 71864.49 | 2016-07-27 | 100% | 100% | 0 | 71864.49 | 0
7 | 06913002 | Allred Unit, Iowa Park | Roofing: Resurface Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 88800 | 58531.89 | 2016-09-08 | 100% | 100% | 0 | 58531.89 | 0
8 | 10815003 | Sanchez Unit, El Paso | Infrastructure: Refurbish Lift Station - Front Administration Building | Deferred Maintenance Account No. 5166 | 0 | 225544.48 | 2016-08-16 | N/A | 100% | 0 | 225544.48 | 0
9 | 08212003 | Havins Unit, Brownwood | Facility Repair: Install Fiberglass Wall Panels - Multiple Buildings | Deferred Maintenance Account No. 5166 | 47900 | 38793.44 | 2016-11-15 | 100% | 100% | 0 | 38793.44 | 0
10 | 06715022 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Infirmary | Deferred Maintenance Account No. 5166 | 0 | 91234.96 | 2017-05-03 | N/A | 100% | 0 | 91234.96 | 0
11 | 03615005 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Lift Station | Deferred Maintenance Account No. 5166 | 0 | 46544.39 | 2016-08-22 | 100% | 100% | 0 | 46544.39 | 0
12 | 09413001 | Gurney Unit, Tennessee Colony | Facility Repair: Renovate Maintenance Shop | Deferred Maintenance Account No. 5166 | 46400 | 28310.26 | 2016-08-11 | 100% | 100% | 0 | 28310.26 | 0
13 | 06716001 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 | 0 | 70655 | 2016-12-06 | N/A | 100% | 0 | 70655 | 0
14 | 08015001 | Sayle Unit, Breckenridge | Facility Repair: Replace Feed Water Tank - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 59307.45 | 2016-09-16 | 100% | 100% | 0 | 59307.45 | 0
15 | 06211002 | Ft. Stockton Unit, Fort Stockton | Facility Repair: Replace Showers - Offender Dorms | Deferred Maintenance Account No. 5166 | 374900 | 245329.64 | 2018-09-17 | 100% | 100% | 81.37 | 245248.27 | 0 | Yes
16 | 01313007 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Repair Shop | Deferred Maintenance Account No. 5166 | 45200 | 44550.11 | 2016-12-13 | 100% | 100% | 0 | 44550.11 | 0
17 | 04505002 | Estes Unit, Venus | Security: Install Concrete Footer - Perimeter Fence | Deferred Maintenance Account No. 5166 | 37700 | 28038.02 | 2016-04-05 | N/A | 100% | 0 | 28038.02 | 0
18 | 08915001 | Johnston Unit, Winnsboro | Facility Repair: Replace Steam Boiler - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 74655.25 | 2016-07-01 | 100% | 100% | 0 | 74655.25 | 0
19 | 08416002 | Halbert Unit, Burnet | Facility Repair: Replace Refrigeration Equipment - Food Service | Deferred Maintenance Account No. 5166 | 0 | 62975.69 | 2017-02-16 | N/A | 100% | 0 | 62975.69 | 0
20 | 02215006 | Beto Unit, Tennessee Colony | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 103659.57 | 2017-02-02 | 100% | 100% | 0 | 103659.57 | 0
21 | 12913004 | Young Unit, Dickinson | Infrastructure: Replace/Refurbish Cooling Tower - Central Plant | Deferred Maintenance Account No. 5166 | 0 | 165900 | 2018-08-07 | 100% | 100% | 11767.06 | 154132.94 | 0
22 | 10014001 | Lychner Unit, Humble | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 | 0 | 394700 | 2018-05-11 | 100% | 100% | 4249.54 | 390450.46 | 0
23 | 03015002 | Jester III Unit, Richmond | Facility Repair: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room | Deferred Maintenance Account No. 5166 | 0 | 117722.98 | 2017-07-01 | 100% | 100% | 0 | 117722.98 | 0
24 | 07815004 | Segovia Unit, Edinburg | Facility Repair: Replace Water Softener - Multiple Dorms | Deferred Maintenance Account No. 5166 | 0 | 37576.66 | 2016-10-13 | 100% | 100% | 0 | 37576.66 | 0
25 | 09915002 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 62837.16 | 2016-08-30 | N/A | 100% | 0 | 62837.16 | 0
26 | 01711010 | Ramsey Unit, Rosharon | Security: Replace Locking System | Deferred Maintenance Account No. 5166 | 2073900 | 1933752.13 | 2016-11-23 | 100% | 100% | 0 | 1933752.13 | 0
27 | 02802006 | Powledge Unit, Palestine | Roofing: Repair/Replace Roof on Metal Fab Factory Building | Deferred Maintenance Account No. 5166 | 1477100 | 1381351.68 | 2017-01-03 | 100% | 100% | 0 | 1381351.68 | 0
28 | 02909007 | Luther Unit, Navasota | Safety: Install Fire Alarm System - Multiple Locations | Deferred Maintenance Account No. 5166 | 1313200 | 523384.8 | 2016-12-19 | 100% | 100% | 0 | 523384.8 | 0
29 | 04301001 | Kyle Unit, Kyle | Safety: Repair/Replace Fire Alarm System - Multiple Buildings | Deferred Maintenance Account No. 5166 | 324044.62 | 336871.41 | 2017-03-02 | 100% | 100% | 0 | 336871.41 | 0
30 | 04404002 | Bridgeport Unit, Bridgeport | Security: Replace Control System Electric Door Locks & Intercom System | Deferred Maintenance Account No. 5166 | 1616900 | 1523228.71 | 2016-10-06 | 100% | 100% | 0 | 1523228.71 | 0
31 | 03711006 | Clements Unit, Amarillo | Roofing: Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7461800 | 7393532.13 | 2018-11-15 | 100% | 100% | 643246.06 | 6750286.07 | 0 | Yes
32 | 03608012 | Michael Unit, Tennessee Colony | Security: Replace Door Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 | 5494300 | 5349316.89 | 2017-11-02 | 100% | 100% | 0 | 5349316.89 | 0
33 | 01802005 | Stringfellow Unit, Rosharon | Security: Replace Cell Door Locks - Offender Dorm Wing | Deferred Maintenance Account No. 5166 | 839916 | 773894.02 | 2016-07-06 | 100% | 100% | 0 | 773894.02 | 0
34 | 02004006 | Wynne Unit, Huntsville | Facility Repair: Extending Covered Area - Transportation Repair Shop | Deferred Maintenance Account No. 5166 | 484400 | 484400 | 2018-07-16 | 100% | 100% | 166371.76 | 318028.24 | 0
35 | 02413007 | Crain Unit, Gatesville | Roofing: Replace Roof - Dorm Building | Deferred Maintenance Account No. 5166 | 107300 | 119770 | 2016-04-26 | 100% | 100% | 0 | 119770 | 0
36 | 03111006 | Hilltop Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank | Deferred Maintenance Account No. 5166 | 747200 | 730358.77 | 2016-06-27 | 100% | 100% | 0 | 730358.77 | 0
37 | 01410011 | Jester I Unit, Richmond | Infrastructure: Replace Ground Storage Water Tanks #1 & #2 | Deferred Maintenance Account No. 5166 | 461800 | 317886.63 | 2016-05-31 | 100% | 100% | 0 | 317886.63 | 0
38 | 11812001 | Travis Co. Unit, Austin | Infrastructure: Replace Grease Trap - Kitchen | Deferred Maintenance Account No. 5166 | 148700 | 184681.21 | 2016-08-04 | 100% | 100% | 0 | 184681.21 | 0
39 | 05410010 | Polunsky Unit, Livingston | Security: Install High Mast Lighting - Offender Dorm Building & Perimeter Fence | Deferred Maintenance Account No. 5166 | 121200 | 196600 | 2016-10-26 | 100% | 100% | 0 | 196600 | 0
40 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Sale of Land Proceeds Account No. 0543 | 0 | 397772 | 2018-01-09 | 100% | 100% | 0 | 397772 | 0
40 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Deferred Maintenance Account No. 5166 | 156400 | 2127.41 | 2018-01-09 | 100% | 100% | 0 | 2127.41 | 0
41 | 00513004 | Clemens Unit, Brazoria | Roofing: Replace Roof - Main Building | Deferred Maintenance Account No. 5166 | 347200 | 355474.56 | 2016-06-21 | 100% | 100% | 0 | 355474.56 | 0
42 | 04710001 | Robertson Unit, Abilene | Roofing: Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7891200 | 8387779.92 | 2019-02-25 | 100% | 89% | 1266211.96 | 7121567.96 | 0
43 | 02911013 | Luther Unit, Navasota | Infrastructure: Replace Ground Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 626900 | 617981.86 | 2016-09-08 | 100% | 100% | 0 | 617981.86 | 0
44 | 01113002 | Ferguson Unit, Midway | Infrastructure: Refurbish Elevated Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 337800 | 488483.25 | 2016-08-16 | 100% | 100% | 0 | 488483.25 | 0
45 | 11106003 | Moore Unit, Bonham | Security: Replace Security Control System | Deferred Maintenance Account No. 5166 | 3304198 | 1826177.65 | 2017-01-31 | 100% | 100% | 0 | 1826177.65 | 0
46 | 03708003 | Clements Unit, Amarillo | Safety: DESIGN ONLY - Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 85797.39 | 2018-03-13 | 100% | N/A | 0 | 85797.39 | 0 | Yes
47 | 03608011 | Michael Unit, Tennessee Colony | Safety: DESIGN ONLY - Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 87827.23 | 2017-12-28 | 100% | N/A | 0 | 87827.23 | 0
48 | 02210005 | Beto Unit, Tennessee Colony | Facility Repair: Replace Flooring - Main Kitchen & Scullery | Deferred Maintenance Account No. 5166 | 407000 | 637.39 | N/A | N/A | N/A | 0 | 637.39 | 0
49 | 01915001 | Scott Unit, Angleton | Infrastructure: Replace Lift Station and Bar Screen - Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 1881800 | 528299.42 | 2018-07-20 | 100% | 100% | 0 | 528299.42 | 0 | Yes
50 | 02212005 | Beto Unit, Tennessee Colony | Safety: Install Standby Generator & Transfer Switch - Trusty Camp | Deferred Maintenance Account No. 5166 | 110100 | 116428.53 | 2016-10-06 | 100% | 100% | 0 | 116428.53 | 0
51 | 00512007 | Clemens Unit, Brazoria | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 109200 | 108613.32 | 2017-07-28 | 100% | 100% | 0 | 108613.32 | 0
52 | 01714002 | Ramsey Unit, Rosharon | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 106700 | 104676.96 | 2017-05-25 | 100% | 100% | 0 | 104676.96 | 0
53 | 02215011 | Beto Unit, Tennessee Colony | Facility Repair: Install Electrical to Cells - Infirmary | Deferred Maintenance Account No. 5166 | 19300 | 19300 | 2018-10-17 | 100% | 100% | 1585.32 | 17714.68 | 0 | Yes
54 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate 3 & 4 Pickets | Deferred Maintenance Account No. 5166 | 65700 | 0 | N/A | N/A | N/A | 0 | 0 | 0
55 | 02212017 | Beto Unit, Tennessee Colony | Infrastructure: Replace Hot Water Lines - Main Building | Deferred Maintenance Account No. 5166 | 49600 | 46138.97 | 2016-07-28 | 100% | 100% | 0 | 46138.97 | 0
56 | 10814001 | Sanchez Unit, El Paso | Infrastructure: Renovate Elevated Water Storage Tank | Deferred Maintenance Account No. 5166 | 17700 | 332.62 | N/A | N/A | N/A | 0 | 332.62 | 0
57 | 03913005 | Hobby Unit, Marlin | Roofing: Replace Roof - Kitchen/Commissary | Deferred Maintenance Account No. 5166 | 153100 | 149285.4 | 2017-05-09 | 100% | 100% | 0 | 149285.4 | 0
58 | 02012008 | Wynne Unit, Huntsville | Facility Repair: Replace Flooring - Kitchen | Deferred Maintenance Account No. 5166 | 92900 | 79142.43 | 2017-11-30 | 100% | 100% | 0 | 79142.43 | 0
59 | 03616019 | Michael Unit, Tennessee Colony | Infrastructure: Replace Transformer - Packing Plant | Deferred Maintenance Account No. 5166 | 0 | 39200 | 2016-05-08 | N/A | 100% | 0 | 39200 | 0
60 | 00609001 | Coffield Unit, Tennessee Colony | Facility Repair: Renovate Commissary Space | Deferred Maintenance Account No. 5166 | 55800 | 60770.67 | 2017-04-04 | 100% | 100% | 0 | 60770.67 | 0
61 | 01713045 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 35100 | 66028.32 | 2017-12-14 | 100% | 100% | 0 | 66028.32 | 0
62 | 03813007 | Daniel Unit, Snyder | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 203979 | 2017-08-03 | 100% | 100% | 0 | 203979 | 0
63 | 04012003 | Lewis Unit, Woodville | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 153098.75 | 2017-07-13 | 100% | 100% | 0 | 153098.75 | 0
64 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Deferred Maintenance Account No. 5166 | 101300 | 0 | N/A | N/A | N/A | 0 | 0 | 0
65 | 02615001 | Pack Unit, Navasota | Infrastructure: Replace Filtration System - Storage Tank | Deferred Maintenance Account No. 5166 | 1432383 | 3191876.85 | 2017-04-20 | 100% | 100% | 0 | 3191876.85 | 0
66 | 02813001 | Powledge Unit, Palestine | Infrastructure: DESIGN ONLY - Repair Washout - Outfall Line Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 4200 | 0 | N/A | N/A | N/A | 0 | 0 | 0
67 | 01313008 | Huntsville Unit, Huntsville | Roofing: Repair/Replace Roof - Mechanical Department | Deferred Maintenance Account No. 5166 | 0 | 745.11 | N/A | N/A | N/A | 75.5 | 669.61 | 0
68 | 03312003 | Jester IV Unit, Richmond | Roofing: DESIGN ONLY - Replace Roof - Psychiatric Facility | Deferred Maintenance Account No. 5166 | 443700 | 244924.35 | 2018-03-19 | 100% | N/A | 0 | 244924.35 | 0
69 | 03613004 | Michael Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 858400 | 169457.41 | 2018-06-11 | 100% | N/A | 0 | 169457.41 | 0
70 | 01914001 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Replace Plumbing - Multiple Cell Blocks | Deferred Maintenance Account No. 5166 | 261000 | 49702.67 | 2016-12-29 | 100% | N/A | 0 | 49702.67 | 0
71 | 01913004 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 | 530700 | 34808.62 | 2019-07-15 | N/A | N/A | 0 | 34808.62 | 0
72 | 02702010 | Terrell Unit, Rosharon | Facility Repair: Renovate Exhaust System - Vocational Shop | Deferred Maintenance Account No. 5166 | 164700 | 3263.47 | 2017-01-15 | N/A | N/A | 0 | 3263.47 | 0
73 | 01912007 | Scott Unit, Angleton | Security: DESIGN ONLY - Replace Locking System - Multiple Wings | Deferred Maintenance Account No. 5166 | 267800 | 125252.02 | 2017-05-15 | 100% | N/A | 0 | 125252.02 | 0
74 | 01205010 | Goree Unit, Huntsville | Facility Repair: Renovate Showers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 126900 | 127435.01 | 2017-09-19 | 100% | 100% | 0 | 127435.01 | 0
75 | 01300042 | Huntsville Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 521900 | 255963.44 | 2016-12-22 | 100% | N/A | 0 | 255963.44 | 0
76 | 04813003 | McConnell Unit, Beeville | Infrastructure: DESIGN ONLY - Replace Steam & Condensate Lines - Kitchen/Laundry Building | Deferred Maintenance Account No. 5166 | 164600 | 94355.44 | 2017-07-12 | 100% | N/A | 0 | 94355.44 | 0
77 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: DESIGN ONLY - Correct Drainage - Multiple Buildings | Deferred Maintenance Account No. 5166 | 6300 | 0 | N/A | N/A | N/A | 0 | 0 | 0
78 | 01000010 | Ellis Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System - Unit Wide | Deferred Maintenance Account No. 5166 | 378000 | 256346.85 | 2017-04-17 | 100% | N/A | 0 | 256346.85 | 0
79 | 08116009 | Rudd Unit, Brownfield | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 65790.62 | 2017-08-01 | N/A | 100% | 0 | 65790.62 | 0
80 | 05402015 | Polunsky Unit, Livingston | Roofing: Repair / Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 6619584.87 | 2019-01-15 | 100% | 99% | 429308.85 | 6190276.02 | 0 | Yes
81 | 09216001 | Holliday Unit, Huntsville | Safety: Add Wheelchair Accessibility - Multiple Dorms | Deferred Maintenance Account No. 5166 | 0 | 20493.25 | 2017-01-13 | 100% | 100% | 0 | 20493.25 | 0
82 | 06517001 | San Saba Unit, San Saba | Facility Repair: Replace Boilers | Deferred Maintenance Account No. 5166 |  | 33629.14 | 2017-08-21 | 100% | 100% | 0 | 33629.14 | 0
83 | 04716003 | Robertson Unit, Abilene | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 127134.47 | 2017-01-25 | 100% | 100% | 0 | 127134.47 | 0
84 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: DESIGN ONLY - Replace Elevated Storage Tank & Storage Tank Well #4 | Deferred Maintenance Account No. 5166 | 4693942 | 69458.62 | 2018-05-17 | 100% | N/A | 0 | 69458.62 | 0
85 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: DESIGN ONLY - Replace Ground Water Storage Tank, Boost Station and Replace Water Lines | Deferred Maintenance Account No. 5166 | 4947317 | 125187.42 | 2018-06-05 | 100% | N/A | 0 | 125187.42 | 0
86 | 00715005 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Intake Housing | Deferred Maintenance Account No. 5166 | 0 | 296800 | 2018-06-27 | 100% | 100% | 0 | 296800 | 0
87 | 09215009 | Holliday Unit, Huntsville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 143440.92 | 2017-04-03 | N/A | 100% | 0 | 143440.92 | 0
88 | 02212024 | Beto Unit, Tennessee Colony | Infrastructure: Reline Manholes | Deferred Maintenance Account No. 5166 | 0 | 57871.1 | 2017-09-18 | 100% | 100% | 0 | 57871.1 | 0
89 | 10316007 | Lopez Unit, Edinburg | Facility Repair: Replace Air Handler - Administrative Segregation | Deferred Maintenance Account No. 5166 | 0 | 65167 | 2018-08-15 | N/A | 100% | 0 | 65167 | 0 | Yes
90 | 09816005 | Dominguez Unit, San Antonio | Facility Repair: Replace HVAC Unit - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 59980 | 2018-01-08 | 100% | 100% | 0 | 59980 | 0
91 | 01200043 | Goree Unit, Huntsville | Safety: Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 0 | 1131380 | 2019-04-12 | 100% | 79% | 330735.58 | 800644.42 | 0 | Yes
92 | 03211005 | Estelle Unit, Huntsville | Security: Replace Exterior Lighting | Deferred Maintenance Account No. 5166 | 0 | 623726.37 | 2019-02-01 | 100% | 94% | 39180.85 | 584545.52 | 0
92 | 03211005 | Estelle Unit, Huntsville | Security: Replace Exterior Lighting | Sale of Land Proceeds Account No. 0543 | 0 | 1573540.35 | 2019-02-01 | 100% | 94% | 51500 | 1522040.35 | 0
93 | 01910013 | Scott Unit, Angleton | Infrastructure: Replace Gas and Water Lines | Deferred Maintenance Account No. 5166 | 0 | 1225357.57 | 2019-06-28 | 100% | 67% | 1095611.93 | 129745.64 | 0 | Yes
93 | 01910013 | Scott Unit, Angleton | Infrastructure: Replace Gas and Water Lines | Sale of Land Proceeds Account No. 0543 | 0 | 1885231 | 2019-06-28 | 100% | 67% | 88864.15 | 1796366.85 | 0
94 | 06816007 | Connally Unit, Kenedy | Facility Repair: Replace HVAC Units - Education and Medical | Deferred Maintenance Account No. 5166 | 0 | 236296 | 2018-03-23 | 100% | 100% | 0 | 236296 | 0
95 | 00716001 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Warehouse | Deferred Maintenance Account No. 5166 | 0 | 126261.14 | 2018-07-24 | 100% | 100% | 0 | 126261.14 | 0 | Yes
96 | 03115003 | Hilltop Unit, Gatesville | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 50868.06 | 2016-10-23 | 100% | 100% | 0 | 50868.06 | 0
97 | 07916001 | Moore Unit, Bonham | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 44162.76 | 2016-10-13 | 100% | 100% | 0 | 44162.76 | 0
98 | 01015008 | Ellis Unit, Huntsville | Infrastructure: Replace Service Entrance Switchgear - Back Gate | Deferred Maintenance Account No. 5166 | 0 | 221482.4 | 2017-05-16 | 100% | 100% | 0 | 221482.4 | 0
99 | 07009003 | Neal Unit, Amarillo | Facility Repair: Renovate Mechanical Room and Replace Showers | Deferred Maintenance Account No. 5166 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0
100 | 05216006 | Briscoe Unit, Dilley | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 179275 | 2017-04-01 | 100% | 100% | 0 | 179275 | 0
101 | 09012004 | Montford Unit, Lubbock | Infrastructure: Install Backflow Preventer | Deferred Maintenance Account No. 5166 | 0 | 179228.49 | 2017-02-15 | 100% | 100% | 0 | 179228.49 | 0
102 | 09116022 | Chasefield Unit, Beeville | Facility Repair: Replace Chiller | Deferred Maintenance Account No. 5166 | 0 | 47273.25 | 2018-02-09 | N/A | 100% | 0 | 47273.25 | 0
103 | 03216017 | Estelle Unit, Huntsville | Facility Repair: Replace Air Handler - High Security Kitchen Roof | Deferred Maintenance Account No. 5166 | 0 | 101601.14 | 2018-04-03 | 100% | 100% | 0 | 101601.14 | 0
104 | 03616021 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 43907.13 | 2017-05-04 | 100% | 100% | 0 | 43907.13 | 0
105 | 01916004 | Scott Unit, Angleton | Infrastructure: Refurbish Wastewater Tank | Deferred Maintenance Account No. 5166 | 0 | 49111.68 | 2017-10-09 | 100% | 100% | 0 | 49111.68 | 0
106 | 00116002 | Administrative Complex, Huntsville | Facility Repair: Replace Cooling Tower - Warehouse | Deferred Maintenance Account No. 5166 | 0 | 299950 | 2018-02-21 | 100% | 100% | 0 | 299950 | 0
107 | 00716002 | Darrington Unit, Rosharon | Facility Repair: Provide Electrical Feed to Outside Gym | Deferred Maintenance Account No. 5166 | 0 | 28704.61 | 2017-05-19 | 100% | 100% | 0 | 28704.61 | 0
108 | 05216001 | Briscoe Unit, Dilley | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 65798.27 | 2017-03-23 | N/A | 100% | 0 | 65798.27 | 0
109 | 06816006 | Connally Unit, Kenedy | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 162982.72 | 2017-08-30 | N/A | 100% | 0 | 162982.72 | 0
110 | 07716003 | Hamilton Unit, Bryan | Facility Repair: Refurbish Chiller - Food Service | Deferred Maintenance Account No. 5166 | 0 | 151200 | 2017-03-28 | N/A | 100% | 0 | 151200 | 0
111 | 07716009 | Hamilton Unit, Bryan | Facility Repair: Replace Condenser and Compressor Rack - Food Service | Deferred Maintenance Account No. 5166 | 0 | 59331.52 | 2017-07-30 | N/A | 100% | 0 | 59331.52 | 0
112 | 04816015 | McConnell Unit, Beeville | Facility Repair: Replace Air Handlers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 146900 | 2018-02-15 | N/A | 100% | 0 | 146900 | 0
113 | 07916002 | Moore Unit, Bonham | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 4167.83 | 2017-02-09 | 100% | 100% | 0 | 4167.83 | 0
114 | 10816001 | Sanchez Unit, El Paso | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 65384.53 | 2017-06-22 | N/A | 100% | 0 | 65384.53 | 0
115 | 12913011 | Young Unit, Dickinson | Facility Repair: Replace Hot Water Storage Tank - Central Plant | Deferred Maintenance Account No. 5166 |  | 59955 | 2017-07-06 | 100% | 100% | 0 | 59955 | 0
116 | 00616025 | Coffield Unit, Tennessee Colony | Safety: Replace Emergency Generator - Water Well #3 | Deferred Maintenance Account No. 5166 | 0 | 48730.51 | 2017-05-11 | 100% | 100% | 0 | 48730.51 | 0
117 | 02616030 | Pack Unit, Navasota | Safety: Replace Emergency Generator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 59291.88 | 2017-09-06 | N/A | 100% | 0 | 59291.88 | 0
118 | 02916006 | Luther Unit, Navasota | Facility Repair: Kitchen Repairs | Deferred Maintenance Account No. 5166 | 0 | 9875.92 | 2017-02-09 | N/A | 100% | 0 | 9875.92 | 0
119 | 10016002 | Lychner Unit, Humble | Facility Repair: Replace Plumbing Systems - Multiple Locations | Deferred Maintenance Account No. 5166 | 0 | 427352.77 | 2018-04-18 | 100% | 100% | 0 | 427352.77 | 0
120 | 00616011 | Coffield Unit, Tennessee Colony | Facility Repair: Replace Chiller - Outside Main Building | Deferred Maintenance Account No. 5166 | 0 | 80444.41 | 2017-11-29 | N/A | 100% | 0 | 80444.41 | 0
121 | 06816009 | Connally Unit, Kenedy | Facility Repair: Replace HVAC Units - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 291824 | 2018-04-03 | N/A | 100% | 0 | 291824 | 0
122 | 09816002 | Dominguez Unit, San Antonio | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 117918.05 | 2018-02-07 | N/A | 100% | 0 | 117918.05 | 0
123 | 09516005 | Garza West, Beeville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 126363.89 | 2018-01-10 | N/A | 100% | 0 | 126363.89 | 0
124 | 07717001 | Hamilton Unit, Bryan | Facility Repair: Replace Chiller - Food Service | Deferred Maintenance Account No. 5166 | 0 | 86153.13 | 2017-07-19 | N/A | 100% | 0 | 86153.13 | 0
125 | 10316002 | Lopez Unit, Edinburg | Facility Repair: Replace Air Handling Unit - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 202070 | 2018-08-15 | N/A | 100% | 0 | 202070 | 0 | Yes
126 | 10316004 | Lopez Unit, Edinburg | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 52581.13 | 2018-01-03 | N/A | 100% | 0 | 52581.13 | 0
127 | 07316003 | Lynaugh Unit, Ft. Stockton | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 62798.12 | 2017-10-11 | N/A | 100% | 0 | 62798.12 | 0
128 | 04816010 | McConnell Unit, Beeville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 143310.91 | 2018-05-02 | N/A | 100% | 0 | 143310.91 | 0 | Yes
129 | 08516001 | Ney Unit, Hondo | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 59806.12 | 2018-07-27 | N/A | 100% | 0 | 59806.12 | 0
130 | 10815005 | Sanchez Unit, El Paso | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 | 0 | 55385.89 | 2017-07-10 | N/A | 100% | 0 | 55385.89 | 0
131 | 07816001 | Segovia Unit, Edinburg | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 63999.23 | 2017-12-20 | N/A | 100% | 0 | 63999.23 | 0
132 | 07116001 | Stevenson Unit, Cuero | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 61005.95 | 2017-12-14 | N/A | 100% | 0 | 61005.95 | 0
133 | 06716013 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Main Building | Deferred Maintenance Account No. 5166 | 0 | 123249.01 | 2018-09-13 | N/A | 100% | 0 | 123249.01 | 0 | Yes
134 | 05516001 | Torres Unit, Hondo | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 64566.56 | 2017-08-28 | N/A | 100% | 0 | 64566.56 | 0
135 | 06816011 | Connally Unit, Kenedy | Facility Repair: Replace Air Handling Units - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 350188.8 | 2018-04-03 | N/A | 100% | 0 | 350188.8 | 0
136 | 06816020 | Connally Unit, Kenedy | Facility Repair: Replace Air Handling Units - Multiple Buildings | Deferred Maintenance Account No. 5166 | 0 | 233459.2 | 2018-04-03 | N/A | 100% | 0 | 233459.2 | 0
137 | 09616003 | Garza East Unit, Beeville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 | 0 | 139089.25 | 2018-03-14 | N/A | 100% | 0 | 139089.25 | 0
138 | 11715001 | Kegans Unit, Houston | Facility Repair: Replace Ceiling - Multiple Locations | Deferred Maintenance Account No. 5166 | 0 | 18898.6 | 2019-01-30 | 100% | 49% | 1082.04 | 17816.56 | 0
139 | 03615004 | Michael Unit, Tennessee Colony | Facility Repair: Replace Ceiling - Main Building | Deferred Maintenance Account No. 5166 | 0 | 42904.01 | 2018-02-26 | 100% | 100% | 0 | 42904.01 | 0 | Yes
140 | 10114004 | Plane Unit, Dayton | Facility Repair: Renovate Kitchen - Scullery | Deferred Maintenance Account No. 5166 |  | 9640.31 | 2017-06-23 | 100% | 100% | 0 | 9640.31 | 0
141 | 11810001 | Travis Co. Unit, Austin | Facility Repair: Renovate Shower Area | Deferred Maintenance Account No. 5166 |  | 98770.64 | 2017-10-03 | 100% | 100% | 0 | 98770.64 | 0
142 | 11815001 | Travis Co. Unit, Austin | Facility Repair: Replace Ceiling - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 31795.74 | 2017-10-03 | 100% | 100% | 0 | 31795.74 | 0
143 | 02217002 | Beto Unit, Tennessee Colony | Security: Install Video Surveillance Cameras - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 11917.11 | 2017-02-13 | N/A | 100% | 0 | 11917.11 | 0
144 | 02017009 | Wynne Unit, Huntsville | Security: Install Video Surveillance Cameras - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 15026.46 | 2016-12-15 | N/A | 100% | 0 | 15026.46 | 0
145 | 02717002 | Terrell Unit, Rosharon | Facility Repair: Construct Temporary Sally Port | Deferred Maintenance Account No. 5166 |  | 46107.74 | 2017-12-13 | 100% | 100% | 0 | 46107.74 | 0
146 | 09917001 | Hutchins Unit, Dallas | Facility Repair: Replace Water Heaters - Multiple Buildings | Deferred Maintenance Account No. 5166 |  | 45088.2 | 2018-05-09 | 100% | 100% | 0 | 45088.2 | 0
147 | 05417004 | Polunsky Unit, Livingston | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 58220.1 | 2017-12-11 | 100% | 100% | 0 | 58220.1 | 0
148 | 815018 | Byrd Unit, Huntsville | Security: DESIGN ONLY - Replace Locking System | Deferred Maintenance Account No. 5166 |  | 0 | 2018-07-10 | 100% | N/A | 0 | 0 | 0
148 | 00815018 | Byrd Unit, Huntsville | Security: DESIGN ONLY - Replace Locking System | Sale of Land Proceeds Account No. 0543 |  | 139336.9 | 2018-07-10 | 100% | N/A | 0 | 139336.9 | 0
149 | 00514005 | Clemens Unit, Brazoria | Security: DESIGN ONLY - Replace Locking System | Sale of Land Proceeds Account No. 0543 |  | 141688.09 | 2018-07-31 | 100% | N/A | 0 | 141688.09 | 0
150 | 00615010 | Coffield Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roofs | Sale of Land Proceeds Account No. 0543 |  | 98310 | 2018-07-25 | 100% | N/A | 0 | 98310 | 0
151 | 00715006 | Darrington Unit, Rosharon | Facility Repair: DESIGN ONLY - Replace Electrical | Sale of Land Proceeds Account No. 0543 |  | 757100 | 2019-02-01 | 78% | N/A | 280854.44 | 476245.56 | 0 | Yes
152 | 01114013 | Ferguson Unit, Midway | Security: DESIGN ONLY - Install High Mast Lighting | Sale of Land Proceeds Account No. 0543 |  | 76689.32 | 2018-03-14 | 100% | N/A | 0 | 76689.32 | 0
153 | 12113002 | Lindsey Unit, Jacksboro | Security: DESIGN ONLY - Replace Door Controls | Sale of Land Proceeds Account No. 0543 |  | 18342.3 | 2018-06-11 | 100% | N/A | 0 | 18342.3 | 0
154 | 09015005 | Montford Unit, Lubbock | Roofing: DESIGN ONLY - Replace Roofs | Sale of Land Proceeds Account No. 0543 |  | 497200 | 2018-09-12 | 100% | N/A | 317889.16 | 179310.84 | 0 | Yes
155 | 02814003 | Powledge Unit, Palestine | Roofing: DESIGN ONLY - Replace Roof - Main Building | Deferred Maintenance Account No. 5166 |  | 0 | 2018-08-07 | 100% | N/A | 0 | 0 | 0
155 | 02814003 | Powledge Unit, Palestine | Roofing: DESIGN ONLY - Replace Roof - Main Building | Sale of Land Proceeds Account No. 0543 |  | 255334.77 | 2018-08-07 | 100% | N/A | 0 | 255334.77 | 0
156 | 02715002 | Terrell Unit, Rosharon | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 |  | 246063.41 | 2018-12-28 | 98% | N/A | 0 | 246063.41 | 0 | Yes
156 | 02715002 | Terrell Unit, Rosharon | Facility Repair: DESIGN ONLY - Kitchen Renovation | Sale of Land Proceeds Account No. 0543 |  | 476636.59 | 2018-12-28 | 98% | N/A | 48574.94 | 428061.65 | 0 | Yes
157 | 02015013 | Wynne Unit, Huntsville | Facility Repair: DESIGN ONLY - Replace Underground Wiring | Sale of Land Proceeds Account No. 0543 |  | 356123.04 | 2018-08-17 | 100% | N/A | 0 | 356123.04 | 0 | Yes
158 | 01714008 | Ramsey Unit, Rosharon | Roofing: DESIGN ONLY - Replace Roofs | Sale of Land Proceeds Account No. 0543 |  | 183780 | 2018-10-09 | 100% | N/A | 51215.31 | 132564.69 | 0 | Yes
159 | 12916001 | Young Unit, Dickinson | Roofing: DESIGN ONLY - Replace Roofs | Sale of Land Proceeds Account No. 0543 |  | 104640.73 | 2018-07-30 | 100% | N/A | 0 | 104640.73 | 0 | Yes
160 | 03015001 | Jester III Unit, Richmond | Roofing: DESIGN ONLY - Replace Roofs | Sale of Land Proceeds Account No. 0543 |  | 418848.91 | 2019-03-08 | 50% | N/A | 262042 | 156806.91 | 0 | Yes
161 | 02017011 | Wynne Unit, Huntsville | Facility Repair: Replace Chiller - Windham | Deferred Maintenance Account No. 5166 | 0 | 65768 | 2018-03-28 | 100% | 100% | 0 | 65768 | 0
162 | 06916001 | Allred Unit, Iowa Park | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 112700 | 2018-02-14 | 100% | 100% | 0 | 112700 | 0
163 | 07017001 | Neal Unit, Amarillo | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 60801.87 | 2017-11-07 | 100% | 100% | 0 | 60801.87 | 0
164 | 06515001 | San Saba Unit, San Saba | Facility Repair: Replace Water Lines - Offender Dorms | Deferred Maintenance Account No. 5166 |  | 58457.1 | 2017-11-30 | N/A | 100% | 0 | 58457.1 | 0
165 | 06715005 | Telford Unit, New Boston | Facility Repair: Replace Plumbing Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 |  | 39586.08 | 2017-11-22 | N/A | 100% | 0 | 39586.08 | 0
166 | 05317006 | Smith Unit, Lamesa | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 70472.38 | 2018-04-25 | 100% | 100% | 0 | 70472.38 | 0
167 | 05417012 | Polunsky Unit, Livingston | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 40664.76 | 2017-12-06 | 100% | 100% | 0 | 40664.76 | 0
168 | 01017024 | Ellis Unit, Huntsville | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 32575.58 | 2017-12-12 | 100% | 100% | 0 | 32575.58 | 0
169 | 01117018 | Ferguson Unit, Midway | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 36085.55 | 2018-01-23 | 100% | 100% | 0 | 36085.55 | 0
170 | 04217007 | Hughes Unit, Gatesville | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 42381.59 | 2018-02-27 | 100% | 100% | 0 | 42381.59 | 0
171 | 09317003 | Middleton Unit, Abilene | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 40157.1 | 2018-03-27 | 100% | 100% | 0 | 40157.1 | 0
172 | 09817006 | Dominguez Unit, San Antonio | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 41621.42 | 2018-01-10 | 100% | 100% | 0 | 41621.42 | 0
173 | 09517004 | Garza West, Beeville | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 40745.64 | 2018-01-22 | 100% | 100% | 0 | 40745.64 | 0
174 | 03617016 | Michael Unit, Tennessee Colony | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 45155.45 | 2018-06-27 | 100% | 100% | 0 | 45155.45 | 0
175 | 09017001 | Montford Unit, Lubbock | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 46783.53 | 2018-01-22 | 100% | 100% | 0 | 46783.53 | 0
176 | 07015008 | Neal Unit, Amarillo | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 53169.83 | 2018-01-22 | 100% | 100% | 0 | 53169.83 | 0
177 | 05017005 | Roach Unit, Childress | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 44335.17 | 2018-02-27 | 100% | 100% | 0 | 44335.17 | 0
178 | 02213008 | Beto Unit, Tennessee Colony | Facility Repair: Upgrade Electrical System - Agriculture Building | Deferred Maintenance Account No. 5166 | 0 | 68847.59 | 2018-04-18 | 100% | 100% | 0 | 68847.59 | 0
179 | 09016001 | Montford Unit, Lubbock | Facility Repair: Replace Chillers - Medical | Deferred Maintenance Account No. 5166 |  | 286451.1 | 2018-05-17 | 100% | 100% | 0 | 286451.1 | 0
180 | 08516008 | Ney Unit, Hondo | Facility Repair: Replace HVAC Unit | Deferred Maintenance Account No. 5166 |  | 30721.5 | 2018-04-02 | 100% | 100% | 0 | 30721.5 | 0
181 | 03714005 | Clements Unit, Amarillo | Security: Reinforce Expansion Cell Block Recreation Yards | Deferred Maintenance Account No. 5166 |  | 38907.07 | 2018-03-07 | N/A | 100% | 0 | 38907.07 | 0
182 | 09417003 | Gurney Unit, Tennessee Colony | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 52218.05 | 2018-05-07 | 100% | 100% | 0 | 52218.05 | 0
183 | 04217004 | Hughes Unit, Gatesville | Safety: Replace Emergency Generator | Deferred Maintenance Account No. 5166 |  | 48226.98 | 2018-05-24 | 100% | 100% | 0 | 48226.98 | 0
184 | 07116009 | Stevenson Unit, Cuero | Facility Repair: Replace HVAC Units - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 61006.5 | 2018-06-01 | N/A | 100% | 1665.16 | 59341.34 | 0
185 | 04217006 | Hughes Unit, Gatesville | Safety: Replace Emergency Generator | Deferred Maintenance Account No. 5166 |  | 49258.72 | 2018-05-24 | 100% | 100% | 0 | 49258.72 | 0
186 | 03617008 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generators - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 75800 | 2018-09-13 | 100% | 100% | 1790.03 | 74009.97 | 0 | Yes
187 | 03217025 | Estelle Unit, Huntsville | Safety: Replace Generator - High Security | Deferred Maintenance Account No. 5166 |  | 0 | N/A | N/A | N/A | 0 | 0 | 0
189 | 01217004 | Goree Unit, Huntsville | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 34348.28 | 2018-05-30 | 100% | 100% | 0 | 34348.28 | 0
190 | 00917008 | Eastham, Lovelady | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 33784.44 | 2018-05-21 | 100% | 100% | 0 | 33784.44 | 0
191 | 04017006 | Lewis Unit, Woodville | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 44237.94 | 2018-04-23 | 100% | 100% | 0 | 44237.94 | 0
192 | 06917008 | Allred Unit, Iowa Park | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 45842.04 | 2018-05-07 | 100% | 100% | 0 | 45842.04 | 0
193 | 05617004 | Jordan Unit, Pampa | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 47152.04 | 2018-04-19 | 100% | 100% | 0 | 47152.04 | 0
194 | 04917010 | Stiles Unit, Beaumont | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 46415.4 | 2018-05-10 | 100% | 100% | 0 | 46415.4 | 0
195 | 06717012 | Telford Unit, New Boston | Facility Repair: Replace Water Heaters - Multiple Locations | Deferred Maintenance Account No. 5166 |  | 43211.78 | 2018-04-02 | 100% | 100% | 0 | 43211.78 | 0
196 | 09114009 | Chasefield Unit, Beeville | Safety: Demolish Building | Deferred Maintenance Account No. 5166 |  | 83300.99 | 2019-01-21 | N/A | 97% | 38505.38 | 44795.61 | 0 | Yes
N/A | 04911009 | Stiles Unit, Beaumont | Facility Repair: Replace Windows - Offender Housing | Deferred Maintenance Account No. 5166 | 107400 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 01313001 | Huntsville Unit, Huntsville | Roofing: DESIGN ONLY - Replace Roof/Repair Walls - Infirmary Building | Deferred Maintenance Account No. 5166 | 153600 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 01313004 | Huntsville Unit, Huntsville | Facility Repair: DESIGN ONLY - Repair/Replace South Wall - Perimeter | Deferred Maintenance Account No. 5166 | 461600 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 10907002 | Lockhart Unit, Lockhart | Safety: Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 118700 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 02707005 | Terrell Unit, Rosharon | Infrastructure: Renovate Sewer Line from Food Service | Deferred Maintenance Account No. 5166 | 48700 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 10313003 | Lopez Unit, Edinburg | Facility Repair: Replace/Rebuild Walls and Doors - Kitchen | Deferred Maintenance Account No. 5166 | 103700 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 09199005 | Chasefield Unit, Beeville | Safety: Repair/Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 98900 | 0 | N/A | N/A | N/A | 0 | 0 | 0
|  |  |  | Totals: | 56393900.62 | 67380574 |  |  |  | 5132408.39 | 62248165.61 | 0

## TDCJ Sup.
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2018-12-14
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
15 | TIMELINE: (original estimated completion date: 10/26/18; actual completion date: 9/17/18). Pending final expenditures to close project.
31 | TIMELINE: (original estimated completion date: 11/5/18; actual: 11/15/18). Pending final expenditures to close project.
46 | BUDGET: Adjusted to final expenditures.
49 | BUDGET: Project complete. Budget reduced to final expenditures.
53 | TIMELINE: (original estimated completion date: 10/26/18; actual: 10/17/18). Pending final expenditures to close project.
80 | TIMELINE: (original estimated completion date: 11/21/18; revised: 1/15/19).
89 | BUDGET: Project complete. Budget reduced to final expenditures.
91 | TIMELINE: (original estimated completion date: 10/23/18; revised: 4/12/19).
93 | BUDGET: Lowest qualified bidder higher than original estimate.
95 | BUDGET: Project complete. Budget reduced to final expenditures.
125 | BUDGET: Project complete. Budget reduced to final expenditures.
128 | BUDGET: Project complete. Budget reduced to final expenditures.
133 | TIMELINE: (original estimated completion date: 11/19/18; actual completion date: 9/13/18). BUDGET: Project complete. Budget reduced to final expenditures.
139 | BUDGET: Adjusted to final expenditures.
151 | TIMELINE: (original estimated completion date: 10/10/18; revised: 2/1/19).
154 | TIMELINE: (original estimated completion date: 9/26/18; actual completion date: 9/12/18). Pending final expenditures to close project.
156 | TIMELINE: (original estimated completion date: 10/26/18; revised: 12/28/18).
157 | BUDGET: Adjusted to final expenditures.
158 | TIMELINE: (original estimated completion date: 12/28/18; actual completion date: 10/09/18). Pending final expenditures to close project.
159 | BUDGET: Adjusted to final expenditures.
160 | TIMELINE: (original estimated completion date: 12/28/18; revised: 3/8/19). BUDGET: Lowest qualified bidder lower than original estimate.
186 | TIMELINE: (original estimated completion date: 9/28/18; revised: 9/13/18). Pending final expenditures to close project.
196 | TIMELINE: (original estimated completion date: 10/5/18; revised: 1/21/19).

## TFC
| Agency: | Texas Facilities Commission (303)
| Date: | 2018-12-14 | [9 empty] | 2018-12-14
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-18 Encumbered | FY 2016-18 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | Texas School for the Deaf (TSD) / Texas School for the Blind and Visually Impaired (TSBVI) Campus Wide Improvements, Austin TX | Repair/Replacement of fire protection, life safety, mechanical, plumbing and electrical systems and architectural improvements. | GR Funds | 39856898 | 40033856 | 2019-01-16 | 100% | 70% | 12907296 | 21974201 | 5152359 | Yes
2 | 303 | Lyndon B. Johnson Building (LBJ), Austin TX | Repairs to elevators, life safety, mechanical, plumbing and electrical systems. | GR Funds | 15000000 | 14650000 | 2019-02-28 | 100% | 69% | 6029221 | 8203920 | 416859 | Yes
3 | 303 | William B. Travis Building (WBT), Austin TX | Repairs to mechanical systems and enhancement to indoor air quality. | GR Funds | 16732708 | 16544412 | 2019-08-31 | 100% | 75% | 1574307 | 14732069 | 238036 | Yes
4 | 303 | Stephen F. Austin Building (SFA), Austin, TX | Repairs to mechanical and plumbing systems. | GR Funds | 13672475 | 13868617 | 2019-08-31 | 100% | 73% | 1806123 | 12041931 | 20563 | Yes
5 | 303 | 7-Building Improvements Project Austin TX Central Services Bldg. (CSB) Insurance Annex (INX) John H. Reagan Bldg. (JHR) Robert E. Johnson Bldg. (REJ) E.O. Thompson Bldg. (THO) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) | CSB- Repair to fire protection, mechanical systems, plumbing systems, paving, elevators and boilers. INX- Repairs to mechanical systems. JHR- Repairs to mechanical and electrical systems. REJ- Repairs to security, mechanical and electrical systems. THO- Repairs t security systems, enhancement to indoor air quality, mechanical systems and architectura systems. TJR- Repairs to security, elevators and mechanical systems. WPC- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 14478300 | 14300513 | 2019-08-31 | 100% | 64% | 3934515 | 8832357 | 1533641 | Yes
6 | 303 | William P. Hobby Complex (WPH), Austin TX | Repairs to mechanical, electrical and plumbing systems and fire protection. | GR Funds | 7621589 | 8537100 | 2020-02-28 | 100% | 60% | 5042009 | 2679726 | 815365 | Yes
7 | 303 | Brown Heatly Bldg. - Elevator, Austin TX | Repairs/Replace Elevators | GR Funds | 2514334 | 2486402 | 2017-01-21 | 100% | 68% | 177857 | 1560140 | 748405 | No
8 | 303 | 4-Building Elevator Project, Austin TX James Earl Rudder Bldg. (JER) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) William P. Hobby Complex (WPH) | Repair/Replace Elevators in buildings - JER, TJR, WPC, WPH | GR Funds | 16991013 | 16799811 | 2019-02-20 | 100% | 62% | 4513464 | 10788825 | 1497522 | Yes
9 | 303 | 5-Building Project, Austin TX Insurance Building (INS) Price Daniel Sr. Building (PDB) Supreme Court Building (SCB) Sam Houston Building (SHB) Thomas C. Clark Building (TCC) | INS- Repairs to security, life safety, mechanical systems, exterior windows, architectural finishes, rain water drainage and waterproofing systems. PDB- Repairs to mechanical systems and enhancement to indoor air quality. SCB- Enhancement to indoor air quality, repairs to security systems, elevators, mechanical and electrical systems. SHB- Repairs to mechanical systems. TCC- Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 16791914 | 16602952 | 2020-03-31 | 98% | 11% | 14363624 | 724187 | 1515141 | Yes
10 | 303 | John H. Winters Complex (JHW), Austin TX | Repairs to data center, life safety, accessibility, fire protection, mechanical, plumbing, electrical systems and architectural finishes. | GR Funds | 16157401 | 15975579 | 2019-06-30 | 100% | 65% | 11154354 | 2645897 | 2175328 | Yes
11 | 303 | DSHS - 4 Building Project, Austin TX Dept. of Health Bldg. F (DHF) Dept. of Health Records Bldg. (DHR) Dept. of Health Tower (DHT) Robert Beirnstein Bldg. (RBB) | DHF- Repairs to mechanical systems. DHR- Repairs to MEP systems, restrooms, paving and architectural finishes. DHT- Repairs to fire protection, MEP systems and architectural finishes. RBB- Repairs to elevators, MEP systems, security systems and enhancement of indoor air quality. | GR Funds | 14960012 | 14896051 | 2020-03-31 | 100% | 10% | 13001450 | 1497292 | 397309 | Yes
12 | 303 | Dept. of Health Old Plant (DHOP), Austin TX | DHOP- Repairs to MEP systems, fire protection and security systems. | GR Funds | 1507350 | 1498584 | 2017-02-01 | 100% | 100% | 6515 | 1423562 | 68507 | Yes
13 | 303 | TFC Portfolio Wide Facility Condition Assessment | To provide condition assessment for TFC to include 44 office buildings, 8 warehouse/storage facilities, 9 special use facilities, 47 Texas School for the Deaf buildings, 34 Texas School for the Blind and Visually Impaired campus buildings, 19 parking garages and 33 parking lots. | GR Funds | 0 | 2158150 | 2017-01-05 | 45% | 0% | 1777301 | 380849 | 0 | Yes
14 | 303 | 11-Building Project, Austin TX Brown Heatly Bldg. (BHB) Dept. of Assistive and Rehabilitative Services Admin. Bldg. (DARS) Dr. Bob Glaze Laboratory (DBGL) Dept. of Health Bldg. B (DHB) Dept. of Health Bldg. H (DHH) Dept. of Health Old Lab (DHOL) Dept. of Health Lab A600 (A600) Dept. of Health Service Bldg. (DHSB) Dept. of Health Annex (DHX) Disaster Recovery Operations Center (DROC) Human Services Warehouse (HSW) | BHB- Repairs to accessibility, electrical and mechanical systems. DARS- repairs to elevators. DBGL- Repairs to mechanical, roofing systems and enhancement to indoor air quality. DHB- Enhancement to indoor air quality. DHH- Repairs to mechanical and electrical systems. DHOL- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality. A600- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality DHSB- Repairs to mechanical and architectural finishes. DHX- Repairs to security systems, elevators, MEP systems and architectural finishes. DROC- Repairs to mechanical, electrical systems and enhancement of indoor air quality. HSW- Repairs to elevators, mechanical systems and enhancement of indoor air quality. | GR Funds | 9886584 | 9775736 | 4/31/2020 | 100% | 10% | 7310491 | 1594997 | 870248 | Yes
15 | 303 | 8-Building Project, Austin, TX Park 35 Bldg A (P35A) Park 35 Bldg B (P35B) Park 35 Bldg C (P35C) Park 35 Bldg D (P35D) Park 35 Bldg E (P35E) Promontory Point (PROM) State Records Center (SRC) Wheless Lane Laboratory (WLL) | P35A- Repairs to mechanical, architectural, and enhancement of indoor air quality. P35B- Repairs to roofing, mechanical, electrical and architectural finishes. P35C- Repairs to mechanical systems and inhancement of indoor air quality. P35D- Repairs of mechanical systems. P35E- Enhancement of indoor air quality. Prom- Enhancement to indoor air quality and renovate existing vacant officspace into warehouse/training space. SRC- Enhancement of indoor air quality and repairs to MEP systems. WLL- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 8131095 | 8064033.81 | 4/31/2020 | 100% | 12% | 6091285 | 666959 | 1305789.81 | Yes
16 | 303 | Fire Protection- Various Bldg. Austin TX | Repairs/Replacement of fire protection systems to various buildings as determined necessary from assessment. | GR Funds | 14152211 | 13992954 | 2019-06-15 | 75% | 0% | 11973166 | 224653 | 1795135 | Yes
17 | 303 | Parking Garage Elevator Project, Austin TX Parking Garage A (PKA) B, F, G, H, J, M, N and P | Repair/Replacement of elevators in PKA, PKB, PKF, PKG, PKH, PKJ, PKM, PKN, PKP | GR Funds | 5385467 | 5324864 | 2020-01-15 | 100% | 25% | 4397348 | 738706 | 188810 | Yes
18 | 303 | Waco Office Bldg. (WAC), Waco, TX | Repairs to chillers. | GR Funds | 42280 | 121004 | 2016-08-31 | 100% | 100% | 39115 | 78600 | 3289 | No
19 | 303 | GJ Sutton Building (GJS), San Antonio TX | Repairs to MEP systems, fire protection systems, architectural, and security. | GR Funds | 830694 | 251825 | 2019-03-31 | 0% | 0% | 0 | 0 | 251825
20 | 303 | El Paso Office Building (ELP), El Paso TX | Repairs to mechanical, electrical and security systems. | GR Funds | 814169 | 889169 | 2019-02-28 | 100% | 5% | 236913 | 164012 | 488244
21 | 303 | Elias Ramirez Bldg. (ERB), Houston TX | Repairs to ADA paving, mechanical systems and drainage pipes. | GR Funds | 112306 | 112306 | 2019-02-28 | 0% | 25% | 0 | 26070 | 86236
22 | 303 | Fort Worth Office Bldg. (FTW), Fort Worth TX | Repairs to electrical systems and electrical generator. | GR Funds | 209777 | 209777 | 2019-03-31 | 0% | 25% | 0 | 1720 | 208057
23 | 303 | Carlos F. Truan Natural Resource Center (TRC), Corpus Christi, TX | Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 1001586 | 62652 | 2020-01-31 | 0% | 0% | 20214 | 35788 | 6650 | Yes
24 | 303 | Tyler Office Bldg. (TYL), Tyler, TX | Repairs to roofing, plumbing and electrical systems. | GR Funds | 306185 | 0 | 2020-01-31 | 0% | 0% | 0 | 0 | 0 | Yes
|  |  |  | Totals: | 217156348 | 217156347.81 |  |  |  | 106356568 | 91016461 | 19783318.81

## TFC Sup.
| Agency: | Texas Facilities Commission (303)
| Date: | 2015-12-14
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
2 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
3 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
4 | 12/14/15: Prime Professional Service Provider has been selected. Contract award by Commission is pending.
5 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
7 | 12/14/15: Prime Professional Service Provider has been selected. Contract award by Commission is pending.
8 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
9 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
10 | 12/14/15: Prime Professional Service Provider has been selected. Professional Service provider evaluation and selection pending.

## TxDOT
[8 empty] | 2668 | Texas Department of Transportation #601
Priority Audit Trail | [8 empty] | 12/11/18 Final
[8 empty] | Prepared by: | Diana Miller, Facilities Business Operations Manager - Support Services Division
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (Q5 AY18-19) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Comment
FY16 Q1 JOC Priority | FY16 Q2 JOC Priority | FY16 Q3 JOC Priority | FY16 Q4 JOC Priority | FY17 Q5 JOC Priority | FY17 Q6 JOC Priority | FY17 Q7 JOC Priority | FY17 Q8 JOC Priority
N/A | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 15470402973 | Drainage Flume - NE Bexar MNT | Site Work | Highway Trans. Fund 6 | 0 | 24120 | 2015-12-23 | 100% | 100% | 0 | 24120 | 0
E4 | 3 | 3 | 2 | 2 | 2 | 2 | 2 | 03470402975 | Stairs & Handicap Ramp for Mod Building - Henrietta MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 24105 | 2016-03-07 | 100% | 100% | 0 | 24105 | 0
E1 | 4 | 4 | 3 | 3 | 3 | 3 | 3 | 20470402970 | Remove and Install 10 and 8.5 ton Roof Top HVAC Units - Beaumont District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 17650 | 2015-12-31 | 100% | 100% | 0 | 17650 | 0
11 | 7 | 5 | 4 | 4 | 4 | 4 | 4 | 04470401499 | Install Automatic Gate - Dumas MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12936 | 2016-04-01 | 100% | 100% | 0 | 12936 | 0 | Contract #5342 - combined 1499, 1513, 1510, & 1512
20 | 5 | 6 | 5 | 5 | 5 | 5 | 5 | 04470401510 | Install Automatic Gate - Darouzett MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12936 | 2016-04-01 | 100% | 100% | 0 | 12936 | 0 | Contract #5342 - combined 1499, 1513, 1510, & 1512
22 | 6 | 7 | 6 | 6 | 6 | 6 | 6 | 04470401512 | Install Automatic Gate - Gruver MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12936 | 2016-04-01 | 100% | 100% | 0 | 12936 | 0 | Contract #5342 - combined 1499, 1513, 1510, & 1512
23 | 8 | 8 | 7 | 7 | 7 | 7 | 7 | 04470401513 | Install Automatic Gate - Panhandle MNT | Safety/Security | Highway Trans. Fund 6 | 12000 | 12936 | 2016-04-01 | 100% | 100% | 0 | 12936 | 0 | Contract #5342 - combined 1499, 1513, 1510, & 1512
10 | 9 | 9 | 8 | 8 | 8 | 8 | 8 | 08470401498 | New Perimeter Fence - Jayton MNT | Safety/Security | Highway Trans. Fund 6 | 15000 | 22782 | 2016-05-16 | 100% | 100% | 0 | 22782 | 0
38 | 23 | 10 | 9 | 9 | 9 | 9 | 9 | 20470401541 | A/C Unit Replacement - Anahuac MNT | HVAC | Highway Trans. Fund 6 | 7500 | 7580 | 2016-01-25 | 100% | 100% | 0 | 7580 | 0
40 | 10 | 11 | 10 | 10 | 10 | 10 | 10 | 20470401543 | Replace Generator - Woodville MNT | Safety/Security | Highway Trans. Fund 6 | 40000 | 21178 | 2016-03-22 | 100% | 100% | 0 | 21178 | 0
N/A | 12 | 12 | 11 | 11 | 11 | 11 | 11 | 10470401428 | Replace Roof On Shop - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 500000 | 1046987 | 2018-09-21 | 100% | 100% | 105278 | 941709 | 0 | 3/2/18 change orders increased Contract Amt.
21 | 13 | 13 | 12 | 12 | 12 | 12 | 12 | 04470401511 | Replace Generator - Darouzett MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483 | 2016-03-18 | 100% | 100% | 0 | 11483 | 0 | Contract combined 1514,1511, &1540
24 | 14 | 14 | 13 | 13 | 13 | 13 | 13 | 04470401514 | Replace Generator - Panhandle MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483 | 2016-04-01 | 100% | 100% | 0 | 11483 | 0 | Contract combined 1514,1511, &1540
37 | 15 | 15 | 14 | 14 | 14 | 14 | 14 | 04470401540 | Replace Generator - Claude MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483 | 2016-04-01 | 100% | 100% | 0 | 11483 | 0 | Contract combined 1514,1511, &1540
N/A | 16 | 16 | 15 | 15 | 15 | 15 | 15 | 02470402980 | Replace Fuel Station Gas Pipeline - Fort Worth District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 31340 | 2015-12-30 | 100% | 100% | 0 | 31340 | 0
19 | 47 | 17 | 16 | 16 | 16 | 16 | 16 | 38470401508 | Upgrade Obsolete Johnson Control Panels - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 28310 | 2016-07-18 | 100% | 100% | 0 | 28310 | 0
N/A | 17 | 19 | 17 | 17 | 17 | 17 | 17 | 38470402984 | Upgrade Security (C-CURE) - Card Reader - Austin MNTs | Safety/Security | Highway Trans. Fund 6 | 0 | 96624 | 2016-05-12 | 100% | 100% | 0 | 96624 | 0
446 | 18 | 20 | 18 | 18 | 18 | 18 | 18 | 04470401935 | Replace Fuel Pumps - Pampa Area Engineer & MNT | Site Work | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 100% | 100% | 0 | 17000 | 0 | Combined RFC -w1939 *1-5-16 Approved to submit with 1939 as one RFC
450 | 19 | 21 | 19 | 19 | 19 | 19 | 19 | 04470401939 | Replace Fuel Pumps - Perryton MNT | Site Work | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 100% | 100% | 0 | 17000 | 0 | Combined RFC with 1935 *1-5-16 Approved to submit with 1936 as one RFC
230 | 20 | 22 | 20 | 20 | 20 | 20 | 20 | 14470401612 | Card Reader Pedestals for the Upgrade Security (C-CURE). - Austin MNTs | Safety/Security | Highway Trans. Fund 6 | 1120000 | 62304 | 2016-08-16 | 100% | 100% | 0 | 62304 | 0
34 | 22 | 23 | 21 | 21 | 21 | 21 | 21 | 16470401536 | Replace Existing Secuity Fence Around Perimeter Of Property - San Patricio Co | Safety/Security | Highway Trans. Fund 6 | 150000 | 47998 | 2016-04-26 | 100% | 100% | 0 | 47998 | 0
33 | 21 | 24 | 22 | 22 | 22 | 22 | 22 | 16470401535 | Replace Existing Secuity Fence Around Perimeter Of Property - Nueces East | Safety/Security | Highway Trans. Fund 6 | 125000 | 52399 | 2016-07-14 | 100% | 100% | 0 | 52399 | 0
31 | 25 | 25 | 23 | 23 | 23 | 23 | 23 | 16470401532 | Install Yard Illumination In Back Yard Area (Rebid) - Jim Wells Co. | Safety/Security | Highway Trans. Fund 6 | 40000 | 47600 | 2016-10-03 | 100% | 100% | 0 | 47600 | 0
32 | 26 | 26 | 24 | 24 | 24 | 24 | 24 | 16470401533 | Install Exterior Lighting In Back Yard Area (Rebid) - Live Oak Co. | Safety/Security | Highway Trans. Fund 6 | 40000 | 64800 | 2016-10-03 | 100% | 100% | 0 | 64800 | 0
185 | 27 | 27 | 25 | 25 | 25 | 25 | 25 | 18470401674 | Apply Ceramic Roof Coating (Rebid) - Rockwall MNT | Roofing | Highway Trans. Fund 6 | 120000 | 83327 | 2016-08-10 | 100% | 100% | 10397 | 72930 | 0
E2 | 24 | 28 | 26 | 26 | 26 | 26 | 26 | 01470402967 | Shop Floor Replacement (Project was rebid) - Paris District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 58029 | 2016-09-19 | 100% | 100% | 0 | 58029 | 0
52 | 28 | 29 | 27 | 27 | 27 | 27 | 27 | 15470401602 | Upgrade Security (C-CURE) - San Antonio District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 484572 | 2017-05-15 | 100% | 100% | 0 | 484572 | 0
51 | 29 | 30 | 28 | 28 | 28 | 28 | 28 | 06470401588 | Upgrade Security (C-CURE) - Odessa District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 217611 | 2016-11-18 | 100% | 100% | 0 | 217611 | 0
193 | 30 | 31 | 29 | 29 | 29 | 29 | 29 | 07470401686 | Upgrade Security (C-CURE) - San Angelo District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 133071 | 2016-09-26 | 100% | 100% | 0 | 133071 | 0
N/A | 31 | 32 | 30 | 30 | 30 | 30 | 30 | 18470402978 | Replace Chiller, provide temporary unit until work complete - Dallas District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 247496 | 2016-06-06 | 100% | 100% | 0 | 247496 | 0
14 | 32 | 33 | 31 | 31 | 31 | 31 | 31 | 08470401502 | AC Unit Needs Replacing (Old R22 Unit) - Gail MNT | HVAC | Highway Trans. Fund 6 | 7500 | 9701 | 2016-03-03 | 100% | 100% | 0 | 9701 | 0
180 | 33 | 34 | 32 | 32 | 32 | 32 | 32 | 18470401669 | HVAC - Split Unit (Meeting & Stock Rooms) - Waxahachie Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 10000 | 17241 | 2016-04-14 | 100% | 100% | 0 | 17241 | 0
188 | 34 | 35 | 33 | 33 | 33 | 33 | 33 | 18470401677 | HVAC - Upgrade Existing System - Rockwall MNT | HVAC | Highway Trans. Fund 6 | 15000 | 19795 | 2016-04-14 | 100% | 100% | 0 | 19795 | 0
N/A | 35 | 36 | 34 | 34 | 34 | 34 | 34 | 38470402989 | Riverside 150 Datacenter UPS –- Austin - Riverside Annex II | Safety/Security | Highway Trans. Fund 6 | 0 | 744720 | 2017-02-21 | 100% | 100% | 0 | 744720 | 0
118 | 36 | 37 | 35 | 35 | 35 | 35 | 35 | 07470401589 | New Roof - Junction Area Engineer & MNT | Roofing | Highway Trans. Fund 6 | 16200 | 64170 | 2016-11-16 | 100% | 100% | 0 | 64170 | 0
142 | 39 | 38 | 36 | 36 | 36 | 36 | 36 | 04470401619 | Install Automatic Gate - Canyon MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
144 | 40 | 39 | 37 | 37 | 37 | 37 | 37 | 04470401625 | Install Automatic Gate - Borger MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
61 | 51 | 40 | 38 | 38 | 38 | 38 | 38 | 04470401693 | Replace Generator - Hereford MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
72 | 37 | 41 | 39 | 39 | 39 | 39 | 39 | 04470401704 | Install Automatic Gate - Perryton MNT | Safety/Security | Highway Trans. Fund 6 | 15000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
73 | 49 | 42 | 40 | 40 | 40 | 40 | 40 | 04470401705 | Replace Generator - Perryton MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
84 | 53 | 43 | 41 | 41 | 41 | 41 | 41 | 04470401723 | Replace Generator - Groom MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
93 | 38 | 44 | 42 | 42 | 42 | 42 | 42 | 04470401734 | Install Automatic Gate - Dalhart MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
145 | 126 | 45 | 43 | 43 | 43 | 43 | 43 | 04470401626 | Replace Generator - Borger MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
146 | 42 | 46 | 44 | 44 | 44 | 44 | 44 | 04470401627 | Install Automatic Gate - Pampa Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
147 | 127 | 47 | 45 | 45 | 45 | 45 | 45 | 04470401628 | Replace Generator - Pampa Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
195 | 131 | 48 | 46 | 46 | 46 | 46 | 46 | 04470401691 | Replace Generator - Canadian MNT | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 0 | 10950 | 0 | Contract #5499 - combined with 1626, 1628, 1691, 1693, 1705, & 1723
196 | 41 | 49 | 47 | 47 | 47 | 47 | 47 | 04470401692 | Install Automatic Gate - Amarillo Area Engineer and Mainteannce Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 0 | 12867 | 0 | Contract # 5485 - combined with 1619, 1625, 1627, 1692, 1704, & 1734
N/A | 202 | 50 | 48 | 48 | 48 | 48 | 48 | 38470402988 | New Discharge air temp sensors and HVAC - Cedar Park | HVAC | Highway Trans. Fund 6 | 0 | 135601 | 2017-10-17 | 100% | 100% | 0 | 135601 | 0
717 | 212 | 51 | 49 | 49 | 49 | 49 | 49 | 15470402206 | Replace Windows - Seguin Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 24300 | 2016-04-18 | 100% | 100% | 0 | 24300 | 0
17 | 43 | 52 | 50 | 50 | 50 | 50 | 50 | 38470401506 | Replace Fence Along Mopac With Standard Fence - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 45000 | 97537 | 2016-08-22 | 100% | 100% | 0 | 97537 | 0
45 | 82 | 53 | 51 | 51 | 51 | 51 | 51 | 22470401549 | 3-Ton Standalone Unit (Duct Work, Vents, Air Handler, Etc) - Brackettville | HVAC | Highway Trans. Fund 6 | 8000 | 13046 | 2016-03-21 | 100% | 100% | 0 | 13046 | 0
64 | 75 | 54 | 52 | 52 | 52 | 52 | 52 | 20470401696 | Replace HVAC Units - Liberty Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 20000 | 22500 | 2016-04-08 | 100% | 100% | 0 | 22500 | 0
176 | 71 | 55 | 53 | 53 | 53 | 53 | 53 | 20470401663 | A/C Unit Replacement - Port Arthur Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 8000 | 10752 | 2016-06-13 | 100% | 100% | 0 | 10752 | 0
177 | 72 | 56 | 54 | 54 | 54 | 54 | 54 | 20470401664 | A/C Unit Replacement - Port Arthur Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 18000 | 16500 | 2016-04-05 | 100% | 100% | 0 | 16500 | 0
62 | 55 | 57 | 55 | 55 | 55 | 55 | 55 | 20470401694 | Replace Generator - Kountze MNT | Safety/Security | Highway Trans. Fund 6 | 40000 | 42458 | 2016-09-12 | 100% | 100% | 0 | 42458 | 0
150 | 89 | 58 | 56 | 56 | 56 | 56 | 56 | 20470401631 | A/C Unit Replacement - Beaumont District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 83940 | 2016-08-16 | 100% | 100% | 0 | 83940 | 0
149 | 56 | 59 | 57 | 57 | 57 | 57 | 57 | 20470401630 | Install Gates - Beaumont Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 16000 | 24999 | 2017-01-25 | 100% | 100% | 0 | 24999 | 0
137 | 145 | 60 | 58 | 58 | 58 | 58 | 58 | 14470401613 | New Generators/Upgrades - Georgetown AE/M, Bastrop AE/M, Mason MNT, Austin DHQ | Safety/Security | Highway Trans. Fund 6 | 425000 | 184921 | 2016-10-21 | 100% | 100% | 60900 | 124021 | 0
1095 | 1103 | 61 | 59 | 59 | 59 | 59 | 59 | 02470402586 | Replace Flooring - Decatur Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 7831 | 2016-06-17 | 100% | 100% | 0 | 7831 | 0
N/A | 50 | 64 | 60 | 60 | 60 | 60 | 60 | 15470402986 | SFMO - add door in cmu wall at the Bandera Maintenance Building - Bandera MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 23700 | 2016-05-31 | 100% | 100% | 0 | 23700 | 0
181 | 91 | 184 | 61 | 61 | 61 | 61 | 61 | 22470401670 | Replace HVAC For Sign Shop - Del Rio MNT | HVAC | Highway Trans. Fund 6 | 30000 | 12205 | 2016-04-18 | 100% | 100% | 0 | 12205 | 0
278 | 290 | 736 | 62 | 62 | 62 | 62 | 62 | 22470401766 | Replace Computer/Storage Room HVAC - Laredo Traffic | HVAC | Highway Trans. Fund 6 | 15000 | 12475 | 2016-04-18 | 100% | 100% | 0 | 12475 | 0
55 | 93 | 65 | 63 | 63 | 63 | 63 | 63 | 16470401655 | Upgrade Security (C-CURE) - Corpus Christi District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350222 | 2017-03-17 | 100% | 100% | 0 | 350222 | 0
100 | 79 | 66 | 64 | 64 | 64 | 64 | 64 | 17470402668 | Improve Lab Ventilation - Bryan District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 344774 | 2016-11-09 | 100% | 100% | 0 | 344774 | 0
111 | 66 | 67 | 65 | 65 | 65 | 65 | 65 | 08470401577 | Replace AC Unit (R22 Unit) - Colorado City MNT | HVAC | Highway Trans. Fund 6 | 10000 | 13074 | 2016-05-27 | 100% | 100% | 0 | 13074 | 0
178 | 58 | 68 | 66 | 66 | 66 | 66 | 66 | 20470401665 | Replace Generator - Port Arthur Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 80000 | 49375 | 2016-09-22 | 100% | 100% | 0 | 49375 | 0
7 | 61 | 69 | 67 | 67 | 67 | 67 | 67 | 11470401494 | Replace HVAC Units- - Lufkin District Headquarters | HVAC | Highway Trans. Fund 6 | 15000 | 78593 | 2016-10-28 | 100% | 100% | 0 | 78593 | 0 | COMBINED W/11-1671 1494
66 | 159 | 70 | 68 | 68 | 68 | 68 | 68 | 07470401698 | Replace 2 Penthouse Type HVAC Units - REBID first 2bidders disqual by HUB (6/20/16) - San Angelo District Headquarters | HVAC | Highway Trans. Fund 6 | 220000 | 200460 | 2016-08-26 | 100% | 100% | 0 | 200460 | 0
114 | 107 | 71 | 69 | 69 | 69 | 69 | 69 | 02470401581 | Chiller Replacement - Fort Worth District Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 103197 | 2016-08-11 | 100% | 100% | 0 | 103197 | 0
N/A | N/A | 72 | 70 | 70 | 70 | 70 | 70 | 12470402994 | Replace HVAC system - Galveston Area Office - LaMarque | HVAC | Highway Trans. Fund 6 | 0 | 16896 | 2016-06-28 | 100% | 100% | 0 | 16896 | 0
N/A | 208 | 73 | 71 | 71 | 71 | 71 | 71 | 15470402988 | Bandera MNT Building structure - foundation - Bandera MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 24999 | 2016-06-06 | 100% | 100% | 0 | 24999 | 0
292 | 304 | 76 | 72 | 72 | 72 | 72 | 72 | 16470401781 | Replace HVAC Unit At Vehicle Titles And Registration - Corpus Christi DHQ - District Headquarters | HVAC | Highway Trans. Fund 6 | 18000 | 21639 | 2016-05-19 | 100% | 100% | 0 | 21639 | 0
309 | 321 | 77 | 73 | 73 | 73 | 73 | 73 | 16470401798 | Install Mini Split Condenser, Air Handler - Beeville MNT | HVAC | Highway Trans. Fund 6 | 15000 | 19886 | 2016-04-27 | 100% | 100% | 0 | 19886 | 0
71 | 76 | 78 | 74 | 74 | 74 | 74 | 74 | 08470401703 | Replace AC Unit (Old R22 Unit) - Snyder MNT | HVAC | Highway Trans. Fund 6 | 7500 | 8338 | 2016-05-26 | 100% | 100% | 0 | 8338 | 0
92 | 95 | 79 | 75 | 75 | 75 | 75 | 75 | 08470401733 | Replace AC Unit (R22 Unit) - Aspermont MNT | HVAC | Highway Trans. Fund 6 | 7500 | 9306 | 2016-05-24 | 100% | 100% | 0 | 9306 | 0
257 | 269 | 80 | 76 | 76 | 76 | 76 | 76 | 04470401745 | Install Automatic Gate - Amarillo (East) Area Engineer and Maintenance Facility | Safety/Security | Highway Trans. Fund 6 | 10000 | 13200 | 2016-08-04 | 100% | 100% | 0 | 13200 | 0
955 | 963 | 81 | 77 | 77 | 77 | 77 | 77 | 03470402446 | Replace Flooring At Maintenance - Vernon Area Engineer And Maintenance - Vernon Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 22254 | 2016-12-12 | 100% | 100% | 0 | 22254 | 0
115 | 88 | 82 | 78 | 78 | 78 | 78 | 78 | 02470401582 | Exterior Lighting - Fort Worth District Headquarters | Safety/Security | Highway Trans. Fund 6 | 30000 | 37759 | 2016-08-19 | 100% | 100% | 0 | 37759 | 0 | Two phases one in March and one in July for Install.
170 | 98 | 83 | 79 | 79 | 79 | 79 | 79 | 05470401656 | New HVAC Relocate From Roof - Plains MNT | HVAC | Highway Trans. Fund 6 | 25000 | 8400 | 2016-06-09 | 100% | 100% | 0 | 8400 | 0
394 | 406 | 84 | 80 | 80 | 80 | 80 | 80 | 06470401883 | Repair/Replace ATG System On Above Ground Fuel Tanks - Odessa MNT | Site Work | Highway Trans. Fund 6 | 12000 | 10311 | 2016-06-27 | 100% | 100% | 0 | 10311 | 0
597 | 607 | 85 | 81 | 81 | 81 | 81 | 81 | 06470402086 | Repair/Replace ATG System On Above Ground Fuel Tanks - Stanton MNT | Capital Repairs | Highway Trans. Fund 6 | 12000 | 10646 | 2016-06-28 | 100% | 100% | 0 | 10646 | 0
905 | 913 | 86 | 82 | 82 | 82 | 82 | 82 | 06470402396 | Repair/Replace ATG System On Above Ground Fuel Tanks - Iraan MNT | Site Work | Highway Trans. Fund 6 | 12000 | 10321 | 2016-06-29 | 100% | 100% | 0 | 10321 | 0
13 | 86 | 87 | 83 | 83 | 83 | 83 | 83 | 03470401501 | New Fencing - Bowie MNT | Safety/Security | Highway Trans. Fund 6 | 50000 | 39750 | 2016-08-10 | 100% | 100% | 0 | 39750 | 0
83 | 77 | 88 | 84 | 84 | 84 | 84 | 84 | 04470401722 | HVAC Replacement - Groom MNT | HVAC | Highway Trans. Fund 6 | 8000 | 5485 | 2016-08-04 | 100% | 100% | 0 | 5485 | 0
186 | 92 | 89 | 85 | 85 | 85 | 85 | 85 | 18470401675 | Fence - Repair/Replace Chain Link/Rails - Rockwall MNT | Safety/Security | Highway Trans. Fund 6 | 25000 | 97668 | 2016-06-13 | 100% | 100% | 0 | 97668 | 0
1011 | 1019 | 90 | 86 | 86 | 86 | 86 | 86 | 18470402502 | Countertops - Restrooms (Solid Surface) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 23553 | 2016-06-17 | 100% | 100% | 0 | 23553 | 0
308 | 320 | 92 | 87 | 87 | 87 | 87 | 87 | 09470401797 | Install Gate and Controls - Hillsboro Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 17000 | 10994 | 2016-05-27 | 100% | 100% | 0 | 10994 | 0
N/A | 207 | 179 | 88 | 88 | 88 | 88 | 88 | 16470402987 | Roof Repairs - Port Aransas Ferry Landing | Capital Repairs | Highway Trans. Fund 6 | 0 | 226000 | 2016-09-22 | 100% | 100% | 2500 | 223500 | 0 | Change order since last report.
830 | 838 | 94 | 89 | 89 | 89 | 89 | 89 | 18470402320 | Siding - Partial Replacement - Rockwall MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 4777 | 2016-05-25 | 100% | 100% | 0 | 4777 | 0
N/A | N/A | 95 | 90 | 90 | 90 | 90 | 90 | 10470402998 | EMERGENCY HVAC Unit - Henderson MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 12953 | 2016-04-11 | 100% | 100% | 0 | 12953 | 0
260 | 272 | 96 | 91 | 91 | 91 | 91 | 91 | 18470401748 | Generator Replaced With Diesel - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 15000 | 24894 | 2016-07-29 | 100% | 100% | 0 | 24894 | 0
640 | 650 | 97 | 92 | 92 | 92 | 92 | 92 | 12470402129 | New Carpet/VCT - Angleton Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 9982 | 2016-07-13 | 100% | 100% | 0 | 9982 | 0
839 | 847 | 98 | 93 | 93 | 93 | 93 | 93 | 11470402329 | Renovate Bathrooms - Lufkin MNT | Capital Repairs | Highway Trans. Fund 6 | 40000 | 24248 | 2016-08-30 | 100% | 100% | 0 | 24248 | 0
N/A | N/A | 99 | 94 | 94 | 94 | 94 | 94 | 02470402997 | Air Handler Replacement - District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 8242 | 2016-05-25 | 100% | 100% | 0 | 8242 | 0
655 | 665 | 100 | 95 | 95 | 95 | 95 | 95 | 05470402144 | New VCT Floor - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 19883 | 2016-07-18 | 100% | 100% | 0 | 19883 | 0
652 | 662 | 101 | 96 | 96 | 96 | 96 | 96 | 18470402141 | Window - Ceramic Coating (Warehouse/Facilities/Shop) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 8785 | 2016-06-08 | 100% | 100% | 0 | 8785 | 0
828 | 836 | 102 | 97 | 97 | 97 | 97 | 97 | 18470402318 | Paint Exterior - Rockwall MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24690 | 2016-06-17 | 100% | 100% | 0 | 24690 | 0
25 | 96 | 103 | 98 | 98 | 98 | 98 | 98 | 09470401517 | Fence in Front of Facility - Waco District Headquarters | Safety/Security | Highway Trans. Fund 6 | 110000 | 150350 | 2016-12-22 | 100% | 100% | 29005 | 121345 | 0
1063 | 1071 | 104 | 99 | 99 | 99 | 99 | 99 | 24470402554 | Lab Dock Storage, Install Soffit Filler To Close Off Gap At Top. - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 2360 | 2016-05-23 | 100% | 100% | 0 | 2360 | 0
943 | 951 | 105 | 100 | 100 | 100 | 100 | 100 | 12470402434 | Replace Gutter System - Houston NE Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 8547 | 2016-08-11 | 100% | 100% | 0 | 8547 | 0
1064 | 1072 | 106 | 101 | 101 | 101 | 101 | 101 | 12470402555 | Replace Insulation (Laboratory) - Angleton Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 8000 | 4139 | 2016-05-26 | 100% | 100% | 0 | 4139 | 0
N/A | N/A | 107 | 102 | 102 | 102 | 102 | 102 | 04470402995 | Sewer Line Replacement - Amarillo District Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 18708 | 2016-07-18 | 100% | 100% | 0 | 18708 | 0
N/A | 200 | 108 | 103 | 103 | 103 | 103 | 103 | 15470402985 | Fencing, gate operators, preliminary asbestos testing. - Seguin Warehouse and Seguin Mantenance Office | Safety/Security | Highway Trans. Fund 6 | 0 | 189301 | 2016-12-01 | 100% | 100% | 0 | 189301 | 0
288 | 300 | 109 | 104 | 104 | 104 | 104 | 104 | 21470401777 | Replace HVAC Units - San Benito Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 12000 | 8588 | 2016-05-18 | 100% | 100% | 0 | 8588 | 0
306 | 318 | 110 | 105 | 105 | 105 | 105 | 105 | 10470401795 | Replace HVAC In Bldg. B - South Tyler Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 15000 | 6550 | 2016-06-02 | 100% | 100% | 0 | 6550 | 0
91 | 138 | 111 | 106 | 106 | 106 | 106 | 106 | 19470401731 | Replace HVAC Systems - Carthage MNT | HVAC | Highway Trans. Fund 6 | 16000 | 18733 | 2016-07-01 | 100% | 100% | 0 | 18733 | 0
N/A | N/A | 112 | 107 | 107 | 107 | 107 | 107 | 10470403005 | HVAC Replacement - Canton Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 6450 | 2016-07-01 | 100% | 100% | 0 | 6450 | 0
101 | 133 | 113 | 108 | 108 | 108 | 108 | 108 | 05470401554 | Upgrade Security (C-CURE) - Lubbock District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 210159 | 2017-01-19 | 100% | 100% | 0 | 210159 | 0
41 | 73 | 114 | 109 | 109 | 109 | 109 | 109 | 25470401544 | New Electronic Gate To Yard, Redesign Parking Area (Rebid) - Paducah MNT | Safety/Security | Highway Trans. Fund 6 | 35000 | 79900 | 2016-12-20 | 100% | 100% | 0 | 79900 | 0
313 | 325 | 115 | 110 | 110 | 110 | 110 | 110 | 22470401802 | Replace Two HVAC Units - La Pryor MNT | HVAC | Highway Trans. Fund 6 | 15000 | 12858 | 2016-06-16 | 100% | 100% | 0 | 12858 | 0
152 | 78 | 116 | 111 | 111 | 111 | 111 | 111 | 20470401633 | Install Gates & Install/Repair Fencing - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 24000 | 21848 | 2016-07-07 | 100% | 100% | 0 | 21848 | 0
539 | 549 | 117 | 112 | 112 | 112 | 112 | 112 | 11470402028 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23250 | 2016-06-03 | 100% | 100% | 0 | 23250 | 0
768 | 776 | 118 | 113 | 113 | 113 | 113 | 113 | 17470402257 | Paint Building - Brenham Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 4988 | 2016-06-16 | 100% | 100% | 0 | 4988 | 0
136 | 60 | 119 | 114 | 114 | 114 | 114 | 114 | 14470401611 | Upgrade Security (C-CURE) - Austin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 483534 | 2017-06-26 | 100% | 100% | 0 | 483534 | 0
N/A | 102 | 120 | 115 | 115 | 115 | 115 | 115 | 05470402987 | AE Office Mold Remediation - Lubbock District Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 44627 | 2016-11-21 | 100% | 100% | 0 | 44627 | 0
413 | 425 | 121 | 116 | 116 | 116 | 116 | 116 | 20470401902 | Replace Fuel Dispensers - District Headquarters | Site Work | Highway Trans. Fund 6 | 15000 | 14703 | 2016-06-24 | 100% | 100% | 0 | 14703 | 0
386 | 398 | 122 | 117 | 117 | 117 | 117 | 117 | 08470401875 | Sidewalks at the DMV Building Need to be Cut Out and Replaced in Various Areas - District Headquarters | Site Work | Highway Trans. Fund 6 | 7500 | 4950 | 2016-05-09 | 100% | 100% | 0 | 4950 | 0
619 | 629 | 123 | 118 | 118 | 118 | 118 | 118 | 04470402108 | New Overhead Doors - Claude MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 6450 | 2016-06-28 | 100% | 100% | 0 | 6450 | 0
620 | 630 | 124 | 119 | 119 | 119 | 119 | 119 | 04470402109 | Install Overhead Doors and Openers - Stratford MNT | Capital Repairs | Highway Trans. Fund 6 | 25000 | 8400 | 2016-06-23 | 100% | 100% | 0 | 8400 | 0
1083 | 1091 | 125 | 120 | 120 | 120 | 120 | 120 | 05470402574 | New VCT Floor - NE Special Crews | Capital Repairs | Highway Trans. Fund 6 | 10000 | 8890 | 2016-08-02 | 100% | 100% | 0 | 8890 | 0
1153 | 1161 | 126 | 121 | 121 | 121 | 121 | 121 | 17470402644 | Replace Sidewalk Lab To Area Office - Brenham Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 12500 | 3345 | 2016-06-16 | 100% | 100% | 0 | 3345 | 0
N/A | 211B | 127 | 122 | 122 | 122 | 122 | 122 | 02470402999 | Weatherford MNT gates 2. - MNTs | Safety/Security | Highway Trans. Fund 6 | 0 | 24143 | 2016-08-26 | 100% | 100% | 0 | 24143 | 0 | Parent Project #02470401548 split off $45,000 from total project for various locations listed. Child# 02470402999.
211 | 225 | 684 | 123 | 123 | 123 | 123 | 123 | 02470401548 | Phase I - Weatherford Gates (JOC211) - MNTs | Safety/Security | Highway Trans. Fund 6 | 0 | 24143 | 2016-09-12 | 100% | 100% | 0 | 24143 | 0 | Phase I - Weatherford Gates. Due to security issues project approved. Created child number to PARENT#02470401548 split off $45,000 from total project for various locations listed. CHILD# 02470402999.
30 | 52 | 128 | 124 | 124 | 124 | 124 | 124 | 19470401530 | Replace 1 HVAC System - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 10000 | 20363 | 2016-06-20 | 100% | 100% | 0 | 20363 | 0 | Let with 1530,1567,1644,1646
102 | 68 | 129 | 125 | 125 | 125 | 125 | 125 | 19470401567 | Replace 2 HVAC Systems - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20363 | 2016-06-20 | 100% | 100% | 0 | 20363 | 0 | Let with 1530,1567,1644,1646
163 | 67 | 130 | 126 | 126 | 126 | 126 | 126 | 19470401646 | Replace HVAC System - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 10000 | 20363 | 2016-06-20 | 100% | 100% | 0 | 20363 | 0 | Let with 1530,1567,1644,1646
161 | 90 | 131 | 127 | 127 | 127 | 127 | 127 | 19470401644 | Replace 3 HVAC Systems - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 20363 | 2016-06-20 | 100% | 100% | 0 | 20363 | 0 | Let with 1530,1567,1644,1646
130 | 110 | 132 | 128 | 128 | 128 | 128 | 128 | 15470401601 | Replace Roof Top Package HVAC 10 Ton System - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 15000 | 10983 | 2016-06-15 | 100% | 100% | 0 | 10983 | 0
80 | 112 | 133 | 129 | 129 | 129 | 129 | 129 | 19470401719 | Replaces HVAC System - Daingerfield MNT | HVAC | Highway Trans. Fund 6 | 16000 | 19500 | 2016-07-13 | 100% | 100% | 0 | 19500 | 0
184 | 111 | 134 | 130 | 130 | 130 | 130 | 130 | 19470401673 | Replace 1 HVAC System - Mt Pleasant Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 10000 | 21250 | 2016-07-01 | 100% | 100% | 0 | 21250 | 0
538 | 548 | 136 | 131 | 131 | 131 | 131 | 131 | 11470402027 | Install Vinyl Plank Flooring - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 20800 | 2016-08-23 | 100% | 100% | 0 | 20800 | 0
989 | 997 | 137 | 132 | 132 | 132 | 132 | 132 | 11470402480 | Upgrade Interior Lighting - Nacogdoches Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 22239 | 2016-06-17 | 100% | 100% | 0 | 22239 | 0
706 | 716 | 138 | 133 | 133 | 133 | 133 | 133 | 08470402195 | Replace Flooring At The Special Crews Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 16700 | 4949 | 2016-07-26 | 100% | 100% | 0 | 4949 | 0
N/A | N/A | 139 | 134 | 134 | 134 | 134 | 134 | 10470403004 | HVAC Replacement - Palestine Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 6350 | 2016-05-31 | 100% | 100% | 0 | 6350 | 0
N/A | N/A | 140 | 135 | 135 | 135 | 135 | 135 | 10470403006 | HVAC Replacement - Athens Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 6450 | 2016-06-06 | 100% | 100% | 0 | 6450 | 0
N/A | N/A | 141 | 136 | 136 | 136 | 136 | 136 | 02470401308 | HVAC Replacement - Stephenvill Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 0 | 24693 | 2016-06-30 | 100% | 100% | 0 | 24693 | 0
897 | 905 | 316 | 137 | 137 | 137 | 137 | 137 | 17470402388 | Repair Roof -RS submitted this as PROJ 2115 but we changed back to 2388 - Buffalo MNT | Capital Repairs | Highway Trans. Fund 6 | 7500 | 4500 | 2016-06-09 | 100% | 100% | 0 | 4500 | 0
153 | 108 | 142 | 138 | 138 | 138 | 138 | 138 | 20470401634 | Modifications/Upgrade Electrical - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 60000 | 29500 | 2016-08-01 | 100% | 100% | 0 | 29500 | 0
N/A | N/A | 143 | 139 | 139 | 139 | 139 | 139 | 13470403007 | Replace rusted Caged Safety Ladders - Port Lavaca MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 30500 | 2016-10-03 | 100% | 100% | 0 | 30500 | 0
658 | 668 | 144 | 140 | 140 | 140 | 140 | 140 | 05470402147 | Replace Stairs Going Into Maint. Office - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 12850 | 2016-08-31 | 100% | 100% | 0 | 12850 | 0
303 | 315 | 145 | 141 | 141 | 141 | 141 | 141 | 02470401792 | 9 Crac HVAC Units Transvision Building - District Headquarters | HVAC | Highway Trans. Fund 6 | 270000 | 292942 | 2016-12-05 | 100% | 100% | 0 | 292942 | 0
70 | 121 | 147 | 142 | 142 | 142 | 142 | 142 | 13470401702 | Install ADA Into Time Room - Wharton Cty Maint. | Safety/Security | Highway Trans. Fund 6 | 10000 | 24300 | 2016-08-09 | 100% | 100% | 0 | 24300 | 0
57 | 45 | 74 | 143 | 143 | 143 | 143 | 143 | 21470401684 | HVAC With Study/Assessment (rebid) - Pharr District Headquarters/Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 300000 | 522503 | 2017-08-01 | 100% | 100% | 99946 | 422557 | 0
N/A | R5 | 148 | 144 | 144 | 144 | 144 | 144 | 10470401503 | Replace Boilers at Administration Office - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 180000 | 88438 | 2017-03-30 | 100% | 100% | 0 | 88438 | 0 | Combined let 1503, 1571, 1572, & 1573
105 | 185 | 149 | 145 | 145 | 145 | 145 | 145 | 10470401571 | Modifications/Upgrade HVAC - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 180000 | 88438 | 2017-03-30 | 100% | 100% | 0 | 88438 | 0 | Combined let 1503, 1571, 1572, & 1573
106 | 186 | 150 | 146 | 146 | 146 | 146 | 146 | 10470401572 | Modifications/Upgrade HVAC - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 88438 | 2017-03-30 | 100% | 100% | 0 | 88438 | 0 | Combined let 1503, 1571, 1572, & 1573
107 | 187 | 151 | 147 | 147 | 147 | 147 | 147 | 10470401573 | Replace 5 Air Handler Units - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 88438 | 2017-03-30 | 100% | 100% | 0 | 88438 | 0 | Combined let 1503, 1571, 1572, & 1573
162 | 74 | 152 | 148 | 148 | 148 | 148 | 148 | 19470401645 | Replace Generator - Atlanta District Headquarters | Safety/Security | Highway Trans. Fund 6 | 250000 | 379500 | 2017-03-31 | 100% | 100% | 0 | 379500 | 0
43 | 11 | 153 | 149 | 149 | 149 | 149 | 149 | 18470401546 | Upgrade Security (C-CURE) - Dallas District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 214831 | 2017-01-23 | 100% | 100% | 0 | 214831 | 0
4 | 48 | 154 | 150 | 150 | 150 | 150 | 150 | 01470401491 | Upgrade Security (C-CURE) - Paris District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 181201 | 2017-02-28 | 100% | 100% | 0 | 181201 | 0
36 | 117 | 155 | 151 | 151 | 151 | 151 | 151 | 21470401539 | Security Fence - Zapata MNT Sub-Section | Safety/Security | Highway Trans. Fund 6 | 39800 | 59275 | 2016-09-15 | 100% | 100% | 0 | 59275 | 0
N/A | N/A | 156 | 152 | 152 | 152 | 152 | 152 | 09470402996 | Limestone County Fence Replacement - Limestone - Waco District | Safety/Security | Highway Trans. Fund 6 | 0 | 53710 | 2016-08-18 | 100% | 100% | 0 | 53710 | 0
9 | 141 | 205 | 153 | 153 | 153 | 153 | 153 | 16470401496 | Replace Roof - Rockport MNT | Roofing | Highway Trans. Fund 6 | 300000 | 235900 | 2016-11-23 | 100% | 100% | 0 | 235900 | 0
N/A | N/A | 157 | 154 | 154 | 154 | 154 | 154 | 17470403003 | Paint and Carpet - Madisonville MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 21594 | 2016-11-17 | 100% | 100% | 0 | 21594 | 0 | Note changed Proj ID from 09-4704 to 17-4704
194 | 154 | 158 | 155 | 155 | 155 | 155 | 155 | 15470401687 | Install Gate Operator & Exterior Lighting - Kerrville Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 45000 | 20517 | 2017-03-14 | 100% | 100% | 0 | 20517 | 0
821 | 829 | 159 | 156 | 156 | 156 | 156 | 156 | 11470402311 | Replace Fuel Dispensers - District Headquarters | Site Work | Highway Trans. Fund 6 | 15000 | 14980 | 2016-09-06 | 100% | 100% | 0 | 14980 | 0
426 | 438 | 160 | 157 | 157 | 157 | 157 | 157 | 11470401915 | Replace Bathroom Sewer Dainage System - Crockett MNT | Site Work | Highway Trans. Fund 6 | 15000 | 11840 | 2016-08-01 | 100% | 100% | 0 | 11840 | 0
76 | 123 | 161 | 158 | 158 | 158 | 158 | 158 | 21470401711 | Upgrade Fencing - Brownsville MNT | Safety/Security | Highway Trans. Fund 6 | 39000 | 75900 | 2016-11-22 | 100% | 100% | 0 | 75900 | 0
N/A | N/A | 162 | 159 | 159 | 159 | 159 | 159 | 13470403016 | Edna Caged Ladder Replacement - Edna Maintenance | Safety/Security | Highway Trans. Fund 6 | 0 | 15700 | 2016-09-06 | 100% | 100% | 0 | 15700 | 0
85 | 116 | 249 | 160 | 160 | 160 | 160 | 160 | 15470401724 | Replace Roof - Uvalde MNT | Roofing | Highway Trans. Fund 6 | 100000 | 344814 | 2017-04-24 | 100% | 100% | 0 | 344814 | 0
95 | 139 | 163 | 161 | 161 | 161 | 161 | 161 | 19470401736 | Replace HVAC - Jefferson MNT | HVAC | Highway Trans. Fund 6 | 8500 | 5395 | 2016-09-19 | 100% | 100% | 0 | 5395 | 0
68 | 113 | 164 | 162 | 162 | 162 | 162 | 162 | 07470401700 | Replace Roof (Project was rebid) - San Angelo District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 387525 | 2017-05-31 | 100% | 100% | 0 | 387525 | 0 | Let w 1685,1700 - Roof Replacement - Dist. Shop
266 | 278 | 166 | 163 | 163 | 163 | 163 | 163 | 12470401754 | Replace Emergency Generator - Brookshire MNT | Safety/Security | Highway Trans. Fund 6 | 20000 | 30300 | 2016-10-03 | 100% | 100% | 0 | 30300 | 0
259 | 271 | 168 | 164 | 164 | 164 | 164 | 164 | 19470401747 | Replace 2 HVAC Systems Add 1 HVAC For Shop - Linden MNT | HVAC | Highway Trans. Fund 6 | 30000 | 13595 | 2016-09-19 | 100% | 100% | 0 | 13595 | 0
556 | 566 | 169 | 165 | 165 | 165 | 165 | 165 | 20470402045 | Paint Interior of Facilities - Woodville MNT | Capital Repairs | Highway Trans. Fund 6 | 2500 | 18848 | 2016-07-08 | 100% | 100% | 0 | 18848 | 0
1032 | 1040 | 170 | 166 | 166 | 166 | 166 | 166 | 20470402523 | Interior Lighting - Jasper Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24694 | 2016-07-13 | 100% | 100% | 0 | 24694 | 0
1102 | 1110 | 171 | 167 | 167 | 167 | 167 | 167 | 20470402593 | Replace Electrical Panels - Liberty Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24801 | 2016-08-30 | 100% | 100% | 0 | 24801 | 0
28 | 136 | 172 | 168 | 168 | 168 | 168 | 168 | 21470401526 | Replace Existing Generator - San Isidro MNT Sub-Section | Safety/Security | Highway Trans. Fund 6 | 15000 | 23942 | 2016-10-04 | 100% | 100% | 0 | 23942 | 0
947 | 955 | 173 | 169 | 169 | 169 | 169 | 169 | 08470402438 | Install Overhead Door Openers and Push Buttons in all Bay Door Openings. Total of 10 Door Openers. - Roby MNT | Capital Repairs | Highway Trans. Fund 6 | 12000 | 9658 | 2016-07-07 | 100% | 100% | 0 | 9658 | 0
808 | 816 | 174 | 170 | 170 | 170 | 170 | 170 | 20470402297 | Replace Doors, Frames & Locksets - Port Arthur Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 6000 | 24895 | 2016-09-27 | 100% | 100% | 0 | 24895 | 0
657 | 667 | 212 | 171 | 171 | 171 | 171 | 171 | 05470402146 | Replace Stairs Going In To District Break Room - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 11400 | 2016-08-31 | 100% | 100% | 0 | 11400 | 0
889 | 897 | 213 | 172 | 172 | 172 | 172 | 172 | 08470402380 | New VCT Floor - Snyder MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24885 | 2016-10-07 | 100% | 100% | 0 | 24885 | 0
N/A | N/A | 214 | 173 | 173 | 173 | 173 | 173 | 03470403021 | Seymour Termite - Seymour | Capital Repairs | Highway Trans. Fund 6 | 0 | 18850 | 2016-08-12 | 100% | 100% | 0 | 18850 | 0
283 | 295 | 292 | 174 | 174 | 174 | 174 | 174 | 15470401771 | Replace Generator - Bexar Metro Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 45000 | 29100 | 2016-10-03 | 100% | 100% | 0 | 29100 | 0
798 | 806 | 1111 | 175 | 175 | 175 | 175 | 175 | 09470402287 | Upgrade Interior Lighting - Meridian MNT | Capital Repairs | Highway Trans. Fund 6 | 30000 | 42748 | 2016-07-08 | 100% | 100% | 0 | 42748 | 0
63 | 119 | 175 | 176 | 176 | 176 | 176 | 176 | 20470401695 | Replace Generator - Liberty Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 120000 | 67179 | 2017-01-03 | 100% | 100% | 0 | 67179 | 0
N/A | N/A | 176 | 177 | 177 | 177 | 177 | 177 | 01470403019 | Emory Generator - Emory Maintenance | Safety/Security | Highway Trans. Fund 6 | 0 | 18968 | 2016-09-12 | 100% | 100% | 0 | 18968 | 0
N/A | N/A | 660 | 178 | 178 | 178 | 178 | 178 | 12470403017 | Fuel System Repair (Rebid) - Angleton Area Engineer & Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 24600 | 2016-11-02 | 100% | 100% | 0 | 24600 | 0
18 | 149 | 206 | 181 | 181 | 181 | 181 | 179 | 38470401507 | Replace Roof (C.H. Bldg. 6) - Camp Hubbard State Headquarters | Roofing | Highway Trans. Fund 6 | 285000 | 484596 | 2017-06-07 | 100% | 100% | 0 | 484596 | 0
919 | 927 | 209 | 182 | 182 | 182 | 182 | 180 | 17470402410 | Replace Siding On A Wash Bay - Brenham Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 16900 | 2016-07-13 | 100% | 100% | 0 | 16900 | 0
1178 | 1186 | 217 | 183 | 183 | 183 | 183 | 181 | 17470402670 | New Canopy And Lights - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 12500 | 22020 | 2016-07-26 | 100% | 100% | 0 | 22020 | 0
6 | 64 | 216 | 184 | 184 | 184 | 184 | 182 | 38470401493 | Replace Or Rebuild Existing Generator - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 75000 | 289426 | 2017-05-01 | 100% | 100% | 0 | 289426 | 0
935 | 943 | 220 | 185 | 185 | 185 | 185 | 183 | 04470402426 | New Compressor/Relocate - Groom MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 8048 | 2016-07-07 | 100% | 100% | 0 | 8048 | 0
1140 | 1148 | 234 | 186 | 186 | 186 | 186 | 184 | 11470402631 | Upgrade Interior Lighting - Hemphill MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24474 | 2016-08-17 | 100% | 100% | 0 | 24474 | 0
1117 | 1125 | 167 | 187 | 187 | 187 | 187 | 185 | 10470402608 | Repaint Bldg. B - South Tyler Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 69200 | 2016-08-24 | 100% | 100% | 0 | 69200 | 0
54 | 118 | 199 | 188 | 188 | 188 | 188 | 186 | 16470401650 | Replace Roof - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 225000 | 277170 | 2018-05-01 | 100% | 100% | 30992 | 246178 | 0 | Let 1650, 1651, 1652 and 1653 together. Change order since last report.
166 | 129 | 200 | 189 | 189 | 189 | 189 | 187 | 16470401651 | Replace Roof On The District Hq Administration Bldg - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 300000 | 277170 | 2018-10-02 | 100% | 100% | 30992 | 246178 | 0 | Let 1650, 1651, 1652 and 1653 together
167 | 130 | 201 | 190 | 190 | 190 | 190 | 188 | 16470401652 | Replace Roof On The Lab Building - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 35000 | 277170 | 2018-02-14 | 100% | 100% | 30992 | 246178 | 0 | Let 1650, 1651, 1652 and 1653 together
168 | 135 | 202 | 191 | 191 | 191 | 191 | 189 | 16470401653 | Replace Roof On The Special Crews Office Building - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 350000 | 277170 | 2018-02-15 | 100% | 100% | 30992 | 246178 | 0 | Let 1650, 1651, 1652 and 1653 together
172 | 162 | 218 | 192 | 192 | 192 | 192 | 190 | 11470401658 | Replace Emergency Generator - Crockett MNT | Safety/Security | Highway Trans. Fund 6 | 38000 | 59530 | 2016-10-28 | 100% | 100% | 0 | 59530 | 0
694 | 704 | 91 | 193 | 193 | 193 | 193 | 191 | 02470402183 | Replace\New Windows At Laboratory - Fort Worth DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 81375 | 2016-07-27 | 100% | 100% | 0 | 81375 | 0
N/A | N/A | N/A | 194 | 194 | 194 | 194 | 192 | 10470403023 | Athens HVAC - Athens Maint. & Eng. Office | HVAC | Highway Trans. Fund 6 | 0 | 6350 | 2016-06-24 | 100% | 100% | 0 | 6350 | 0
923 | 931 | 193 | 195 | 195 | 195 | 195 | 193 | 06470402414 | Remove and Replace Existing Shower Floor Tile - Balmorhea MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 3845 | 2016-09-22 | 100% | 100% | 0 | 3845 | 0
924 | 932 | 194 | 196 | 196 | 196 | 196 | 194 | 06470402415 | Remove and Replace Floor Tile Main Office - Balmorhea MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 9540 | 2016-09-22 | 100% | 100% | 0 | 9540 | 0
996 | 1004 | 197 | 197 | 197 | 197 | 197 | 195 | 06470402487 | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection - Stanton MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 12400 | 2016-09-07 | 100% | 100% | 0 | 12400 | 0
727 | 735 | 225 | 198 | 198 | 198 | 198 | 196 | 05470402216 | Paint Exterior - Ralls MNT | Capital Repairs | Highway Trans. Fund 6 | 25000 | 21891 | 2016-09-28 | 100% | 100% | 0 | 21891 | 0
883 | 891 | 198 | 199 | 199 | 199 | 199 | 197 | 24470402374 | Repair / Replace Plumbing Lines Fro Meter To Houses - Terlingua Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 18000 | 8640 | 2016-11-09 | 100% | 100% | 0 | 8640 | 0
N/A | N/A | 662 | 200 | 200 | 200 | 200 | 198 | 15470403020 | Child of Proj ID#15470401560 New Braunfels Security Gate escalated 5-24-16 - New Braunfels | Safety/Security | Highway Trans. Fund 6 | 0 | 36300 | 2016-09-19 | 100% | 100% | 0 | 36300 | 0 | Child of Proj ID#15470401560
424 | 436 | 189 | 201 | 201 | 201 | 201 | 199 | 16470401913 | Replace 3 Existing Fuel Dispensers At The Fuel Station. Combined with 16-2012 and 16-2454 - District Headquarters | Site Work | Highway Trans. Fund 6 | 20000 | 43088 | 2016-10-06 | 100% | 100% | 0 | 43088 | 0
895 | 903 | 210 | 202 | 202 | 202 | 202 | 200 | 17470402386 | Paint Building - Huntsville Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 13800 | 2016-08-01 | 100% | 100% | 0 | 13800 | 0
994 | 1002 | 281 | 203 | 203 | 203 | 203 | 201 | 11470402485 | Upgrade Exterior Lighting - San Augustine Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24235 | 2016-07-28 | 100% | 100% | 0 | 24235 | 0
1139 | 1147 | 306 | 204 | 204 | 204 | 204 | 202 | 11470402630 | Replace Fuel Dispensers - Hemphill MNT | Site Work | Highway Trans. Fund 6 | 15000 | 15380 | 2016-09-30 | 100% | 100% | 0 | 15380 | 0
35 | 137 | 312 | 205 | 205 | 205 | 205 | 203 | 21470401538 | Replace Generators - combined with 21-1710 and 21-1712 - Zapata MNT Sub-Section | Safety/Security | Highway Trans. Fund 6 | 20000 | 71895 | 2016-11-17 | 100% | 100% | 0 | 71895 | 0
277 | 289 | 187 | 206 | 206 | 206 | 206 | 204 | 22470401765 | Replace 8 HVAC Units - Laredo Lab/FIN/Stratus | HVAC | Highway Trans. Fund 6 | 80000 | 86258 | 2016-08-30 | 100% | 100% | 0 | 86258 | 0
46 | 83 | 247 | 207 | 207 | 207 | 207 | 205 | 05470401553 | Replace Roof - Lubbock District Headquarters | Roofing | Highway Trans. Fund 6 | 50000 | 81888 | 2017-05-16 | 100% | 100% | 0 | 81888 | 0 | Aug 2018 - Last payment held until final docs produced. Combined Let w1553,1738,2343
50 | 147 | 248 | 208 | 208 | 208 | 208 | 206 | 06470401587 | Replace Roof - Odessa District Headquarters | Roofing | Highway Trans. Fund 6 | 300000 | 346622 | 2017-06-07 | 100% | 100% | 0 | 346622 | 0
86 | 148 | 250 | 209 | 209 | 209 | 209 | 207 | 06470401725 | Replace Roof - Midland Area Engineer & MNT | Roofing | Highway Trans. Fund 6 | 65000 | 346622 | 2017-03-09 | 100% | 100% | 0 | 346622 | 0
94 | 105 | 252 | 210 | 210 | 210 | 210 | 208 | 04470401735 | Roof - Dalhart MNT | Roofing | Highway Trans. Fund 6 | 175000 | 371000 | 2017-02-02 | 100% | 100% | 0 | 371000 | 0
97 | 97 | 253 | 211 | 211 | 211 | 211 | 209 | 05470401738 | Replace Roof - Lubbock District Headquarters | Roofing | Highway Trans. Fund 6 | 65000 | 81888 | 2017-05-15 | 100% | 100% | 0 | 81888 | 0 | Aug 2018 - Last payment held until final docs produced. Combined Let w1553,1738,2343
852 | 860 | 1149 | 212 | 212 | 212 | 212 | 210 | 05470402343 | Replace Roof - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 50000 | 81888 | 2017-05-15 | 100% | 100% | 0 | 81888 | 0 | Aug 2018 - Last payment held until final docs produced. Combined Let w1553,1738,2343
555 | 565 | 221 | 213 | 213 | 213 | 213 | 211 | 20470402044 | Install Additional Unit Heater - Woodville MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 24726 | 2016-07-18 | 100% | 100% | 0 | 24726 | 0
868 | 876 | 231 | 214 | 214 | 214 | 214 | 212 | 05470402359 | New VCT Floor - Tahoka MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 9770 | 2016-09-01 | 100% | 100% | 0 | 9770 | 0
1033 | 1041 | 232 | 215 | 215 | 215 | 215 | 213 | 20470402524 | Paint Office Interior - Jasper Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24812 | 2017-02-16 | 100% | 100% | 0 | 24812 | 0
981 | 989 | 242 | 216 | 216 | 216 | 216 | 214 | 11470402472 | Replace Fuel Dispensers - Livingston Area Engineer & MNT | Site Work | Highway Trans. Fund 6 | 20000 | 14990 | 2016-10-18 | 100% | 100% | 0 | 14990 | 0
990 | 998 | 280 | 217 | 217 | 217 | 217 | 215 | 11470402481 | Install Electric Baydoor Openers - San Augustine Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24948 | 2016-08-03 | 100% | 100% | 0 | 24948 | 0
626 | 636 | 135 | 218 | 218 | 218 | 218 | 216 | 17470402115 | Repair Roof - Huntsville Area Engineer & MNT | Roofing | Highway Trans. Fund 6 | 15000 | 6925 | 2016-08-11 | 100% | 100% | 0 | 6925 | 0
N/A | 199 | 211 | 219 | 219 | 219 | 219 | 217 | 14470402984 | New Generator/Upgrade - San Marcos MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 63227 | 2017-01-05 | 100% | 100% | 0 | 63227 | 0 | New Generator/Upgrade---Split off of 14470401613
843 | 851 | 279 | 220 | 220 | 220 | 220 | 218 | 11470402333 | Replace Windows - Lufkin MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24950 | 2016-10-11 | 100% | 100% | 0 | 24950 | 0
N/A | N/A | N/A | 221 | 221 | 221 | 221 | 219 | 12470403027 | Replace HVAC unit - EPO - Northeast Harris Co. MNT | HVAC | Highway Trans. Fund 6 | 0 | 39777 | 2016-06-27 | 100% | 100% | 0 | 39777 | 0
982 | 990 | 243 | 222 | 222 | 222 | 222 | 220 | 11470402473 | Replace Windows - Livingston Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24875 | 2017-03-23 | 100% | 100% | 0 | 24875 | 0
297 | 309 | 288 | 223 | 223 | 223 | 223 | 221 | 20470401786 | Install/Repair Fence - Liberty Area Engineer & MNT | Safety/Security | Highway Trans. Fund 6 | 7000 | 14049 | 2016-11-01 | 100% | 100% | 0 | 14049 | 0
807 | 815 | 392 | 224 | 224 | 224 | 224 | 222 | 20470402296 | Paint Interior Of Facility - Port Arthur Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24450 | 2017-03-28 | 100% | 100% | 0 | 24450 | 0
258 | 270 | 727 | 225 | 225 | 225 | 225 | 223 | 04470401746 | New Generator - Loop Maintenance | Safety/Security | Highway Trans. Fund 6 | 12500 | 13100 | 2016-08-04 | 100% | 100% | 0 | 13100 | 0
684 | 694 | 1021 | 226 | 226 | 226 | 226 | 224 | 17470402173 | Improve Lighting In Yard/Shed - Caldwell MNT | Safety/Security | Highway Trans. Fund 6 | 5000 | 8460 | 2016-08-23 | 100% | 100% | 0 | 8460 | 0
N/A | N/A | N/A | 227 | 227 | 227 | 227 | 225 | 01470403022 | Paris Fuel Station Generator - Paris | Safety/Security | Highway Trans. Fund 6 | 0 | 8618 | 2016-08-04 | 100% | 100% | 0 | 8618 | 0
542 | 552 | 230 | 228 | 228 | 228 | 228 | 226 | 11470402031 | Replace Flooring - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24789 | 2016-09-23 | 100% | 100% | 0 | 24789 | 0
148 | 106 | 255 | 229 | 229 | 229 | 229 | 227 | 04470401629 | Replace Roof - Pampa Area Engineer & MNT | Roofing | Highway Trans. Fund 6 | 175000 | 311100 | 2017-05-12 | 100% | 100% | 0 | 311100 | 0
1100 | 1108 | 282 | 230 | 230 | 230 | 230 | 228 | 20470402591 | Paint Office Interior - Liberty Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 15887 | 2016-08-04 | 100% | 100% | 0 | 15887 | 0
N/A | N/A | N/A | 231 | 231 | 231 | 231 | 229 | 23470403024 | Commanche Sewer Repair - Brownwood District Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 15500 | 2016-09-28 | 100% | 100% | 0 | 15500 | 0
724 | 732 | 237 | 232 | 232 | 232 | 232 | 230 | 05470402213 | New VCT Floor - Brownfield Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 22885 | 2016-08-24 | 100% | 100% | 0 | 22885 | 0
131 | 151 | 254 | 233 | 233 | 233 | 233 | 231 | 08470401604 | Replace Generator - Abilene District Headquarters | Safety/Security | Highway Trans. Fund 6 | 58000 | 44300 | 2016-11-30 | 100% | 100% | 0 | 44300 | 0
744 | 752 | 239 | 234 | 234 | 234 | 234 | 232 | 08470402233 | Repair Damage To Walls And Wood In Area Ofice - Big Spring MNT | Capital Repairs | Highway Trans. Fund 6 | 8000 | 6181 | 2016-09-08 | 100% | 100% | 0 | 6181 | 0
N/A | N/A | 661 | 235 | 235 | 235 | 235 | 233 | 14470403018 | San Marcos Septic replacement - San Marcos MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 32875 | 2016-11-02 | 100% | 100% | 0 | 32875 | 0
616 | 626 | 270 | 236 | 236 | 236 | 236 | 234 | 18470402105 | Paint Exterior - Ennis MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24420 | 2016-11-21 | 100% | 100% | 0 | 24420 | 0
922 | 930 | 295 | 237 | 237 | 237 | 237 | 235 | 17470402413 | Install Automatic Gate On Rear Gate - Bryan Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 15881 | 2017-03-29 | 100% | 100% | 0 | 15881 | 0
615 | 625 | 300 | 238 | 238 | 238 | 238 | 236 | 18470402104 | Floor Tile Abatement - Corridors Only (Stain Concrete) - Ennis MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 20728 | 2016-10-21 | 100% | 100% | 0 | 20728 | 0
1154 | 1162 | 1355 | 239 | 239 | 239 | 239 | 237 | 17470402645 | Improve Lighting In Yard/Shed - Hearne Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24480 | 2016-08-17 | 100% | 100% | 0 | 24480 | 0
1099 | 1107 | 233 | 240 | 240 | 240 | 240 | 238 | 20470402590 | Interior Lighting - Liberty Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24630 | 2016-10-05 | 100% | 100% | 0 | 24630 | 0
844 | 852 | 240 | 241 | 241 | 241 | 241 | 239 | 11470402334 | Underskirt Fuel Awning - Lufkin MNT | Capital Repairs | Highway Trans. Fund 6 | 6000 | 24860 | 2016-12-09 | 100% | 100% | 0 | 24860 | 0
517 | 527 | 269 | 242 | 242 | 242 | 242 | 240 | 18470402006 | Paint Exterior - Waxahachie Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24840 | 2016-11-17 | 100% | 100% | 0 | 24840 | 0
913 | 921 | 272 | 243 | 243 | 243 | 243 | 241 | 18470402404 | Paint Exterior - Hutchins Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 19460 | 2016-09-23 | 100% | 100% | 0 | 19460 | 0
848 | 856 | 299 | 244 | 244 | 244 | 244 | 242 | 20470402338 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24958 | 2016-10-07 | 100% | 100% | 0 | 24958 | 0
930 | 938 | 1206 | 245 | 245 | 245 | 245 | 243 | 17470402421 | Improve Lighting In Yard/Shed - Buffalo MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 12596 | 2016-08-22 | 100% | 100% | 0 | 12596 | 0
171 | 99 | 185 | 246 | 246 | 246 | 246 | 244 | 05470401657 | Replace Roof - Plains MNT | Roofing | Highway Trans. Fund 6 | 50000 | 187900 | 2017-01-04 | 100% | 100% | 0 | 187900 | 0
842 | 850 | 219 | 247 | 247 | 247 | 247 | 245 | 11470402332 | Replace Fuel Dispensers - Lufkin MNT | Site Work | Highway Trans. Fund 6 | 15000 | 20878 | 2017-01-26 | 100% | 100% | 0 | 20878 | 0
87 | 104 | 251 | 248 | 248 | 248 | 248 | 246 | 03470401726 | Replace Roof - Vernon Area Engineer & MNT | Roofing | Highway Trans. Fund 6 | 120000 | 257325 | 2016-11-18 | 100% | 100% | 0 | 257325 | 0
784 | 792 | 257 | 249 | 249 | 249 | 249 | 247 | 11470402273 | Replace Windows - Crockett MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24625 | 2017-01-11 | 100% | 100% | 0 | 24625 | 0
995 | 1003 | 258 | 250 | 250 | 250 | 250 | 248 | 11470402486 | Upgrade Interior Lighting - San Augustine Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 21562 | 2016-08-09 | 100% | 100% | 0 | 21562 | 0
1035 | 1043 | 266 | 251 | 251 | 251 | 251 | 249 | 20470402526 | Replace Carpet And VCT - Jasper Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24320 | 2016-10-07 | 100% | 100% | 0 | 24320 | 0
622 | 632 | 278 | 252 | 252 | 252 | 252 | 250 | 20470402111 | Interior Lighting - Newton MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24725 | 2016-09-12 | 100% | 100% | 0 | 24725 | 0
543 | 553 | 289 | 253 | 253 | 253 | 253 | 251 | 11470402032 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 22849 | 2016-08-29 | 100% | 100% | 0 | 22849 | 0
362 | 374 | 388 | 254 | 254 | 254 | 254 | 252 | 20470401851 | Reconfigure Parking Lot - Newton MNT | Site Work | Highway Trans. Fund 6 | 10000 | 24100 | 2016-08-04 | 100% | 100% | 0 | 24100 | 0
984 | 992 | 394 | 255 | 255 | 255 | 255 | 253 | 11470402475 | Install Electric Baydoor Openers - Nacogdoches Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24951 | 2016-09-30 | 100% | 100% | 0 | 24951 | 0
154 | 178 | 397 | 256 | 256 | 256 | 256 | 254 | 20470401635 | Replace Roof - Beaumont District Headquarters | Roofing | Highway Trans. Fund 6 | 95000 | 147394 | 2016-12-22 | 100% | 100% | 0 | 147394 | 0
1156 | 1164 | 1357 | 257 | 257 | 257 | 257 | 255 | 17470402647 | Improve Lighting In Yard/Shed - Huntsville Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 15663 | 2016-08-22 | 100% | 100% | 0 | 15663 | 0
550 | 560 | 284 | 258 | 258 | 258 | 258 | 256 | 04470402039 | Remove Oh Door In Breakroom And Install Walk Door - Dumas MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 5000 | 2016-09-01 | 100% | 100% | 0 | 5000 | 0
157 | 168 | 353 | 259 | 259 | 259 | 259 | 257 | 03470401639 | Upgrade Security (C-CURE) - Wichita Falls District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 341263 | 2017-04-14 | 100% | 100% | 0 | 341263 | 0
90 | 142 | 207 | 260 | 260 | 260 | 260 | 258 | 16470401730 | Replace Roof On The Maintenance Building - Nueces East | Roofing | Highway Trans. Fund 6 | 250000 | 148690 | 2018-02-27 | 100% | 100% | 0 | 148690 | 0
1081 | 1089 | 285 | 261 | 261 | 261 | 261 | 259 | 05470402572 | Replace Windows AE's Office - Littlefield Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 4684 | 2016-09-20 | 100% | 100% | 0 | 4684 | 0
979 | 987 | 241 | 262 | 262 | 262 | 262 | 260 | 11470402470 | Replace Windows - Center MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24325 | 2017-03-27 | 100% | 100% | 0 | 24325 | 0
540 | 550 | 277 | 263 | 263 | 263 | 263 | 261 | 11470402029 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24675 | 2016-08-30 | 100% | 100% | 0 | 24675 | 0
104 | 156 | 263 | 264 | 264 | 264 | 264 | 262 | 38470401570 | Modifications/Upgrade HVAC - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 114269 | 2017-05-03 | 100% | 100% | 0 | 114269 | 0
1142 | 1150 | 283 | 265 | 265 | 265 | 265 | 263 | 11470402633 | Upgrade Interior Lighting - Groveton MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23380 | 2016-08-30 | 100% | 100% | 0 | 23380 | 0
N/A | N/A | N/A | 266 | 266 | 266 | 266 | 264 | 03470403031 | Phase III Wichita falls flooring - Wichita Falls | Capital Repairs | Highway Trans. Fund 6 | 0 | 342333 | 2016-08-17 | 100% | 100% | 0 | 342333 | 0
N/A | N/A | N/A | 267 | 267 | 267 | 267 | 265 | 06470403032 | Odessa Shop HVAC - Odessa | HVAC | Highway Trans. Fund 6 | 0 | 12483 | 2016-08-09 | 100% | 100% | 0 | 12483 | 0
N/A | N/A | N/A | 268 | 268 | 268 | 268 | 266 | 05470401969 | New 2" Water Line Installation - Tulia MNT | Site Work | Highway Trans. Fund 6 | 20000 | 46500 | 2017-02-06 | 100% | 100% | 0 | 46500 | 0
16 | 65 | 226 | 269 | 269 | 269 | 269 | 267 | 38470401505 | Install Generator For Data Center (Camp Hubbard Bldg. 6) - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 517000 | 449205 | 2017-09-12 | 100% | 100% | 0 | 449205 | 0
725 | 733 | 1052 | 270 | 270 | 270 | 270 | 268 | 05470402214 | Remove In-Ground Hydraulic Floor Lift - Brownfield Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 6050 | 2016-08-17 | 100% | 100% | 0 | 6050 | 0
815 | 823 | 1124 | 271 | 271 | 271 | 271 | 269 | 05470402305 | Remove In-Ground Hydraulic Floor Lift - Levelland MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5500 | 2016-08-12 | 100% | 100% | 0 | 5500 | 0
837 | 845 | 1141 | 272 | 272 | 272 | 272 | 270 | 05470402327 | Remove In-Ground Hydraulic Floor Lift - Lamesa MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 4600 | 2016-08-15 | 100% | 100% | 0 | 4600 | 0
869 | 877 | 1162 | 273 | 273 | 273 | 273 | 271 | 05470402360 | Remove In-Ground Hydraulic Floor Lift - Tahoka MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5600 | 2016-08-19 | 100% | 100% | 0 | 5600 | 0
99 | 46 | 75 | 274 | 274 | 274 | 274 | 272 | 21470401775 | Complete Power Project (Single, Electrical Power Upgrade Project, To Encompass All Of The Electrical Issues To Include Study/Assessment) - Pharr District Headquarters | Safety/Security | Highway Trans. Fund 6 | 300000 | 520873 | 2017-09-26 | 100% | 100% | 0 | 520873 | 0
192 | 115 | 165 | 275 | 275 | 275 | 275 | 273 | 07470401685 | Replace Roofing - San Angelo District Headquarters | Roofing | Highway Trans. Fund 6 | 125000 | 387525 | 2017-05-31 | 100% | 100% | 0 | 387525 | 0 | Let w 1685,1700 - Roof Replacement - Dist. Shop
722 | 730 | 236 | 276 | 276 | 276 | 276 | 274 | 05470402211 | Repaint Exterior, Old Faded Peeling - Bovina MNT | Capital Repairs | Highway Trans. Fund 6 | 25000 | 23704 | 2016-11-04 | 100% | 100% | 0 | 23704 | 0
742 | 750 | 238 | 277 | 277 | 277 | 277 | 275 | 08470402231 | New VCT Floor - Big Spring MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 14962 | 2016-09-30 | 100% | 100% | 0 | 14962 | 0
N/A | N/A | N/A | 278 | 278 | 278 | 278 | 276 | 05470403029 | Upgrade Light - | Safety/Security | Highway Trans. Fund 6 | 0 | 12500 | 2016-09-16 | 100% | 100% | 0 | 12500 | 0
138 | 143 | 343 | 279 | 279 | 279 | 279 | 277 | 06470401615 | Replace Main HVAC Multi-Zone Units - Odessa District Headquarters | HVAC | Highway Trans. Fund 6 | 160000 | 241281 | 2016-12-27 | 100% | 100% | 0 | 241281 | 0
757 | 765 | 303 | 280 | 280 | 280 | 280 | 278 | 06470402246 | Repaint Exterior - McCamey MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15765 | 2016-10-06 | 100% | 100% | 0 | 15765 | 0
1097 | 1105 | 320 | 281 | 281 | 281 | 281 | 279 | 20470402588 | Install Roll-Up Door Opener - Anahuac MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 11407 | 2016-09-01 | 100% | 100% | 0 | 11407 | 0
841 | 849 | 360 | 282 | 282 | 282 | 282 | 280 | 11470402331 | Replace Flooring - Lufkin MNT | Capital Repairs | Highway Trans. Fund 6 | 12000 | 24875 | 2016-11-18 | 100% | 100% | 0 | 24875 | 0
978 | 986 | 389 | 283 | 283 | 283 | 283 | 281 | 11470402469 | Replace Overhead Doors - Center MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24825 | 2016-09-12 | 100% | 100% | 0 | 24825 | 0
586 | 596 | 301 | 284 | 284 | 284 | 284 | 282 | 06470402075 | Paint Building Exterior - McCamey MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 21364 | 2016-10-06 | 100% | 100% | 0 | 21364 | 0
887 | 895 | 315 | 285 | 285 | 285 | 285 | 283 | 08470402378 | Convert Old Propane Gas Heaters In Shop To Natural Gas - Snyder MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 5700 | 2016-10-05 | 100% | 100% | 0 | 5700 | 0
1080 | 1088 | 319 | 286 | 286 | 286 | 286 | 284 | 05470402571 | New VCT Floor - Littlefield Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 30000 | 24201 | 2016-12-02 | 100% | 100% | 0 | 24201 | 0
1090 | 1098 | 339 | 287 | 287 | 287 | 287 | 285 | 20470402581 | Interior Lighting - Beaumont Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 5000 | 23425 | 2016-10-12 | 100% | 100% | 0 | 23425 | 0
627 | 637 | 980 | 288 | 288 | 288 | 288 | 286 | 17470402116 | Restroom Remodels - Buffalo MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 12400 | 2016-09-29 | 100% | 100% | 0 | 12400 | 0
1106 | 1114 | 1323 | 289 | 289 | 289 | 289 | 287 | 17470402597 | Restroom Remodels, Training Building - Bryan Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 11850 | 2016-09-26 | 100% | 100% | 0 | 11850 | 0
587 | 597 | 302 | 290 | 290 | 290 | 290 | 288 | 06470402076 | Replace Linolium With Tile In Offices - McCamey MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 13964 | 2016-10-26 | 100% | 100% | 0 | 13964 | 0
N/A | N/A | N/A | 291 | 291 | 291 | 291 | 289 | 12470403033 | Replace 10 Ton HVAC - La Marque Area Engineer & Maintenance | HVAC | Highway Trans. Fund 6 | 0 | 23295 | 2016-10-18 | 100% | 100% | 0 | 23295 | 0
159 | 101 | 222 | 292 | 292 | 292 | 292 | 290 | 04470401641 | Upgrade Generator - Amarillo District Headquarters | Safety/Security | Highway Trans. Fund 6 | 400000 | 617750 | 2017-10-05 | 100% | 100% | 0 | 617750 | 0
787 | 795 | 290 | 293 | 293 | 293 | 293 | 291 | 11470402276 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 19335 | 2016-09-13 | 100% | 100% | 0 | 19335 | 0
387 | 399 | 322 | 294 | 294 | 294 | 294 | 292 | 08470401876 | Replace Water Cut Offs On The Complex For Various Buildings - District Headquarters | Site Work | Highway Trans. Fund 6 | 8500 | 5327 | 2016-10-21 | 100% | 100% | 0 | 5327 | 0
987 | 995 | 329 | 295 | 295 | 295 | 295 | 293 | 11470402478 | Replace Windows - Nacogdoches Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24968 | 2017-03-10 | 100% | 100% | 0 | 24968 | 0
1101 | 1109 | 330 | 296 | 296 | 296 | 296 | 294 | 20470402592 | Replace Carpet And VCT - Liberty Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24512 | 2016-10-03 | 100% | 100% | 0 | 24512 | 0
983 | 991 | 390 | 297 | 297 | 297 | 297 | 295 | 11470402474 | Upgrade Interior Lighting - Livingston Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 19760 | 2016-10-05 | 100% | 100% | 0 | 19760 | 0
15 | 80 | 260 | 298 | 298 | 298 | 298 | 296 | 38470401504 | Demolish Existing Building and Convert To Parking - testing done on this Proj ID funds moved to 38-3033 - Camp Hubbard State Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 119090 | 2017-01-02 | 100% | 100% | 0 | 119090 | 0
N/A | N/A | N/A | 299 | 299 | 299 | 299 | 297 | 02470403030 | EMERGENCY -Staircase Replacement (Ft. Worth DHQ Admin Bldg) - Ft. Worth | Capital Repairs | Highway Trans. Fund 6 | 0 | 40525 | 2017-01-12 | 100% | 100% | 0 | 40525 | 0
900 | 908 | 337 | 300 | 300 | 300 | 300 | 298 | 25470402391 | Paint Interior & Exterior, Resurface Parking Area - Quanah MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 47113 | 2016-11-10 | 100% | 100% | 0 | 47113 | 0
544 | 554 | 305 | 301 | 301 | 301 | 301 | 299 | 16470402033 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Refugio Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15715 | 2016-12-13 | 100% | 100% | 0 | 15715 | 0 | Combined Let 2033,2126, 2264
637 | 647 | 323 | 302 | 302 | 302 | 302 | 300 | 16470402126 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Goliad Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15715 | 2016-12-13 | 100% | 100% | 0 | 15715 | 0 | Combined Let 2033,2126, 2264
775 | 783 | 336 | 303 | 303 | 303 | 303 | 301 | 16470402264 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Karnes Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15715 | 2016-12-13 | 100% | 100% | 0 | 15715 | 0 | Combined Let 2033,2126, 2264
N/A | N/A | 309 | 304 | 304 | 304 | 304 | 302 | 01470402991 | Fuel Canopy - Sulphur Springs | Capital Repairs | Highway Trans. Fund 6 | 0 | 102045 | 2017-02-21 | 100% | 100% | 0 | 102045 | 0
N/A | N/A | 663 | 305 | 305 | 305 | 305 | 303 | 08470402681 | Add Canopy To Back Of Welding Shop 45' X 25' Area - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 82522 | 2017-01-09 | 100% | 100% | 0 | 82522 | 0
853 | 861 | 1150 | 306 | 306 | 306 | 306 | 304 | 05470402344 | Replace Steps With ADA Ramp Back Door - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 12000 | 21364 | 2017-01-20 | 100% | 100% | 0 | 21364 | 0
845 | 853 | 314 | 307 | 307 | 307 | 307 | 305 | 11470402335 | Upgrade Interior Lighting - Lufkin MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24842 | 2016-10-12 | 100% | 100% | 0 | 24842 | 0
980 | 988 | 317 | 308 | 308 | 308 | 308 | 306 | 11470402471 | Upgrade Interior Lighting - Center MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 21138 | 2016-09-12 | 100% | 100% | 0 | 21138 | 0
888 | 896 | 1176 | 309 | 309 | 309 | 309 | 307 | 08470402379 | Convert The Old Salt Bin Into A Sign And Traffic Control Room Storage - Snyder MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 16824 | 2016-11-18 | 100% | 100% | 0 | 16824 | 0
993 | 1001 | 395 | 310 | 310 | 310 | 310 | 308 | 11470402484 | Replace Windows - San Augustine Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24325 | 2017-03-17 | 100% | 100% | 0 | 24325 | 0
361 | 373 | 775 | 311 | 311 | 311 | 311 | 309 | 20470401850 | Replace Fuel Dispensers - Anahuac MNT | Site Work | Highway Trans. Fund 6 | 20000 | 17600 | 2016-10-13 | 100% | 100% | 0 | 17600 | 0
541 | 551 | 915 | 312 | 312 | 312 | 312 | 310 | 11470402030 | Renovate Baydoor Offices - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24827 | 2016-09-12 | 100% | 100% | 0 | 24827 | 0
N/A | N/A | N/A | 313 | 313 | 313 | 313 | 311 | 16470403037 | New Waterline - Emergency request - Robstown MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 61449 | 2017-01-31 | 100% | 100% | 0 | 61449 | 0
339 | 351 | 293 | 314 | 314 | 314 | 314 | 312 | 22470401828 | Parking Lot Lighting - Del Rio MNT (US 90) | Site Work | Highway Trans. Fund 6 | 35000 | 24352 | 2016-09-21 | 100% | 100% | 0 | 24352 | 0
N/A | N/A | N/A | 315 | 315 | 315 | 315 | 313 | 05470403035 | Replace Carpeting - Lubbock SE MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 18796 | 2016-12-09 | 100% | 100% | 0 | 18796 | 0
67 | 160 | 146 | 316 | 316 | 316 | 316 | 314 | 07470401699 | Modifications/Upgrade HVAC - San Angelo District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 93152 | 2017-04-03 | 100% | 100% | 0 | 93152 | 0
49 | 132 | 227 | 317 | 317 | 317 | 317 | 315 | 02470401585 | Upgrade Security (C-CURE) - Fort Worth District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 782989 | 2018-04-14 | 100% | 100% | 45750 | 737239 | 0
877 | 885 | 294 | 318 | 318 | 318 | 318 | 316 | 20470402368 | Install Overhead Doors - Kountze MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 35700 | 2017-02-13 | 100% | 100% | 0 | 35700 | 0
1126 | 1134 | 1340 | 319 | 319 | 319 | 319 | 317 | 13470402617 | Repair Sheetrock And Paint Walls - Hallettsville MNT | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23400 | 2016-10-12 | 100% | 100% | 0 | 23400 | 0
833 | 841 | 1137 | 320 | 320 | 320 | 320 | 318 | 22470402323 | Retrofit Locker Room Into Storage/Supply Room - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24880 | 2016-11-28 | 100% | 100% | 0 | 24880 | 0
312 | 324 | 223 | 321 | 321 | 321 | 321 | 319 | 19470401801 | Replace 2 HVAC Systems - District Headquarters | HVAC | Highway Trans. Fund 6 | 35000 | 53995 | 2016-10-24 | 100% | 100% | 0 | 53995 | 0
583 | 593 | 407 | 322 | 322 | 322 | 322 | 320 | 06470402072 | Repaint Exterior - Andrews MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 17140 | 2016-12-22 | 100% | 100% | 0 | 17140 | 0
N/A | 44 | 18 | 323 | 323 | 323 | 323 | 321 | 38470402974 | Paving Overlay Parking Lot - Camp Hubbard State Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 1520769 | 2017-07-24 | 100% | 100% | 0 | 1520769 | 0
752 | 760 | 298 | 325 | 325 | 325 | 324 | 322 | 20470402241 | Flag Pole Lights - Districtwide | Capital Repairs | Highway Trans. Fund 6 | 12000 | 15937 | 2016-10-17 | 100% | 100% | 0 | 15937 | 0
621 | 631 | 313 | 326 | 326 | 326 | 325 | 323 | 20470402110 | Install Storm Shutters - Anahuac MNT | Capital Repairs | Highway Trans. Fund 6 | 14000 | 23250 | 2016-11-11 | 100% | 100% | 0 | 23250 | 0
143 | 177 | 345 | 327 | 327 | 327 | 326 | 324 | 08470401623 | Replace Roof - Big Spring MNT | Roofing | Highway Trans. Fund 6 | 60000 | 297259 | 2017-04-19 | 100% | 100% | 0 | 297259 | 0
286 | 298 | 357 | 328 | 328 | 328 | 327 | 325 | 05470401774 | Replace Roof - Littlefield MNT | Roofing | Highway Trans. Fund 6 | 45000 | 272314 | 2017-06-30 | 100% | 100% | 0 | 272314 | 0
110 | 165 | 408 | 329 | 329 | 329 | 328 | 326 | 10470401576 | Upgrade Security (C-CURE) - Tyler District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 331243 | 2017-07-18 | 100% | 100% | 0 | 331243 | 0
572 | 582 | 940 | 330 | 330 | 330 | 329 | 327 | 05470402061 | Remove In-Ground Hydraulic Floor Lift - Post MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5500 | 2016-09-27 | 100% | 100% | 0 | 5500 | 0
721 | 729 | 1050 | 331 | 331 | 331 | 330 | 328 | 05470402210 | Remove In-Ground Hydraulic Floor Lift - Bovina MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5500 | 2016-09-22 | 100% | 100% | 0 | 5500 | 0
728 | 736 | 1054 | 332 | 332 | 332 | 331 | 329 | 05470402217 | Remove In-Ground Hydraulic Floor Lift - Ralls MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 6750 | 2016-09-23 | 100% | 100% | 0 | 6750 | 0
778 | 786 | 1094 | 333 | 333 | 333 | 332 | 330 | 05470402267 | Remove In-Ground Hydraulic Floor Lift - Plains MNT | Capital Repairs | Highway Trans. Fund 6 | 3000 | 6000 | 2016-09-29 | 100% | 100% | 0 | 6000 | 0
N/A | N/A | N/A | 334 | 334 | 334 | 333 | 331 | 24470403036 | El Paso DHQ C UPS System - El Paso DHQ | Safety/Security | Highway Trans. Fund 6 | 0 | 12633 | 2016-08-30 | 100% | 100% | 0 | 12633 | 0
164 | 170 | 291 | 335 | 335 | 335 | 334 | 332 | 16470401648 | Modifications/Upgrade Electrical - Corpus Christi District Headquarters | Safety/Security | Highway Trans. Fund 6 | 250000 | 369995 | 2017-08-04 | 100% | 100% | 0 | 369995 | 0
818 | 826 | 331 | 336 | 336 | 336 | 335 | 333 | 11470402308 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24960 | 2017-02-28 | 100% | 100% | 0 | 24960 | 0 | 0
132 | 172 | 350 | 337 | 337 | 337 | 336 | 334 | 08470401605 | Replace Roof - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 65000 | 242976 | 2017-07-28 | 100% | 100% | 0 | 242976 | 0 | Combined Let 1605,1606,1607.
133 | 173 | 351 | 338 | 338 | 338 | 337 | 335 | 08470401606 | Replace Roof (Warehouse) - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 130000 | 242976 | 2017-07-28 | 100% | 100% | 0 | 242976 | 0 | Combined Let 1605,1606,1607.
134 | 174 | 352 | 339 | 339 | 339 | 338 | 336 | 08470401607 | Reroof Building Or Repatch In Areas - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 10000 | 242976 | 2017-07-28 | 100% | 100% | 0 | 242976 | 0 | Combined Let 1605,1606,1607.
124 | 189 | 368 | 340 | 340 | 340 | 339 | 337 | 15470401595 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 75000 | 342156 | 2018-03-21 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
125 | 190 | 369 | 341 | 341 | 341 | 340 | 338 | 15470401596 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 100000 | 342156 | 2018-03-31 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
126 | 191 | 370 | 342 | 342 | 342 | 341 | 339 | 15470401597 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 100000 | 342156 | 2018-03-31 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
127 | 192 | 371 | 343 | 343 | 343 | 342 | 340 | 15470401598 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 125000 | 342156 | 2018-03-31 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
128 | 193 | 372 | 344 | 344 | 344 | 343 | 341 | 15470401599 | Replace Roof - Buildings 1, 3 & 4 - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 342156 | 2018-03-31 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
129 | 194 | 373 | 345 | 345 | 345 | 344 | 342 | 15470401600 | Replace Roof - Buildings 8 & 9 - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 150000 | 342156 | 2018-03-31 | 100% | 100% | 6503 | 335653 | 0 | Let 1595, 1596, 1597, 1598, 1599, & 1600
854 | 862 | 393 | 346 | 346 | 346 | 345 | 343 | 11470402345 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 18250 | 2016-10-14 | 100% | 100% | 0 | 18250 | 0
882 | 890 | 412 | 347 | 347 | 347 | 346 | 344 | 24470402373 | Paint Interior Walls - Terlingua Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 17500 | 18865 | 2016-11-18 | 100% | 100% | 0 | 18865 | 0
561 | 571 | 929 | 348 | 348 | 348 | 347 | 345 | 24470402050 | Add Rolling Doors To Existing Storage Bldg. - Fort Hancock Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 6000 | 9680 | 2016-11-04 | 100% | 100% | 0 | 9680 | 0
581 | 591 | 949 | 349 | 349 | 349 | 348 | 346 | 11470402070 | Renovate Bathroom - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24976 | 2016-11-28 | 100% | 100% | 0 | 24976 | 0
N/A | N/A | 405 | 350 | 350 | 350 | 349 | 347 | 24470402817 | Add 25' To Roof At Existing Salt / Sand Canopy - El Paso | Site Work | Highway Trans. Fund 6 | 0 | 62750 | 2017-04-27 | 100% | 100% | 0 | 62750 | 0
N/A | N/A | N/A | 351 | 351 | 351 | 350 | 348 | 18470402685 | Canopy At Mechanic Shop - Waxahachie Area Engineer & MNT | Site Work | Highway Trans. Fund 6 | 0 | 89979 | 2017-05-17 | 100% | 100% | 0 | 89979 | 0
N/A | N/A | N/A | 352 | 352 | 352 | 351 | 349 | 06470403038 | New Generator - Odessa | Safety/Security | Highway Trans. Fund 6 | 0 | 294469 | 2017-08-24 | 100% | 100% | 0 | 294469 | 0
307 | 319 | 256 | 353 | 353 | 353 | 352 | 350 | 10470401796 | Upgrade HVAC In Maint &Area Office - South Tyler Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 150000 | 61697 | 2017-02-01 | 100% | 100% | 0 | 61697 | 0
56 | 158 | 262 | 354 | 354 | 354 | 353 | 351 | 13470401661 | Convert Flat Roof To Gable Style - Port Lavaca MNT - Calhoun Cty Maint. | Roofing | Highway Trans. Fund 6 | 250000 | 392750 | 2018-05-24 | 100% | 100% | 214571 | 178179 | 0
1022 | 1030 | 318 | 399 | 355 | 355 | 354 | 352 | 18470402513 | Paint Exterior And Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 18744 | 2016-10-06 | 100% | 100% | 0 | 18744 | 0
N/A | N/A | N/A | N/A | 356 | 356 | 355 | 353 | 10470403042 | Interior remodel - Athens RDC | Capital Repairs | Highway Trans. Fund 6 | 0 | 295512 | 2017-02-23 | 100% | 100% | 0 | 295512 | 0
N/A | N/A | N/A | N/A | 357 | 357 | 356 | 354 | 23470401392 | Renovate Existing Facilities - Brownwood District Headquarters | Capital Construction | Highway Trans. Fund 6 | 6000000 | 4500000 | 2018-12-03 | 100% | 95% | 514882 | 3985118 | 0 | Changed Proj ID from 23-2339 to 23-1392; Ccure project 23470401667 cancelled and combined with this project.
117 | 180 | 367 | 447 | 358 | 358 | 357 | 355 | 02470401584 | Roof Replacement and Interior upgrade. | Roofing | Highway Trans. Fund 6 | 480000 | 1263199 | 2018-11-16 | 100% | 100% | 3176 | 1260023 | 0 | Let both 1583 and 1584. 02-1584 includes foundation repairs
1111 | 1119 | 406 | 449 | 359 | 359 | 358 | 356 | 24470402602 | Install Truck Lift - El Paso Engineer & Maint. Office | Capital Repairs | Highway Trans. Fund 6 | 12500 | 25000 | 2016-09-29 | 100% | 100% | 0 | 25000 | 0
298 | 310 | 347 | 387 | 360 | 360 | 359 | 357 | 20470401787 | Rehab Roof With Insulation - Liberty MNT | Roofing | Highway Trans. Fund 6 | 95000 | 23283 | 2016-12-01 | 100% | 100% | 0 | 23283 | 0
265 | 277 | R87 | R116 | 361 | 361 | 360 | 358 | 20470401753 | Rehab Metal Roofing - Orange MNT | Roofing | Highway Trans. Fund 6 | 95000 | 24000 | 2016-12-09 | 100% | 100% | 0 | 24000 | 0
822 | 830 | 1128 | 393 | 362 | 362 | 361 | 359 | 11470402312 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 18250 | 2016-10-14 | 100% | 100% | 0 | 18250 | 0
659 | 669 | 362 | 381 | 363 | 363 | 362 | 360 | 06470402148 | Paint Exterior Walls & Re-Insulate Weldging Shop - Kermit MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24106 | 2016-11-16 | 100% | 100% | 0 | 24106 | 0
688 | 698 | 651 | 428 | 364 | 364 | 363 | 361 | 24470402177 | Insulate Interior Of Stock Room / Storage - Ft. Davis MNT | Capital Repairs | Highway Trans. Fund 6 | 22500 | 19100 | 2017-02-15 | 100% | 100% | 0 | 19100 | 0
871 | 879 | 186 | 378 | 365 | 365 | 364 | 362 | 04470402362 | Install Overhead Doors And Openers - Canadian MNT | Capital Repairs | Highway Trans. Fund 6 | 25000 | 19800 | 2016-11-03 | 100% | 100% | 0 | 19800 | 0
649 | 659 | 335 | 380 | 366 | 366 | 365 | 363 | 25470402138 | Replace Floor Tiles - Munday MNT | Capital Repairs | Highway Trans. Fund 6 | 9500 | 13199 | 2017-01-11 | 100% | 100% | 0 | 13199 | 0
135 | 63 | 228 | 432 | 367 | 367 | 366 | 364 | 14470401610 | Replace Generator - Austin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 250000 | 369560 | 2017-08-04 | 100% | 100% | 0 | 369560 | 0
1093 | 1101 | 1318 | 383 | 368 | 368 | 367 | 365 | 18470402584 | Flooring Replaced - Remove VCT And Replace With VCT - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 2460 | 2016-10-14 | 100% | 100% | 0 | 2460 | 0
650 | 660 | 271 | 394 | 369 | 369 | 368 | 366 | 18470402139 | Paint Exterior/Scope changed to enclose breakroom - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 9726 | 2016-11-15 | 100% | 100% | 0 | 9726 | 0 | Combined 18-2511 into this project.
1094 | 1102 | 273 | 395 | 370 | 370 | 369 | 367 | 18470402585 | Paint Exterior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24872 | 2016-10-28 | 100% | 100% | 0 | 24872 | 0
1147 | 1155 | 297 | 398 | 371 | 371 | 370 | 368 | 18470402638 | Paint Exterior - Corsicana Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 22444 | 2016-10-24 | 100% | 100% | 0 | 22444 | 0
310 | 322 | 747 | 401 | 372 | 372 | 371 | 369 | 18470401799 | Install Gates - Electric/Key Pad - Cedar Hill MNT | Safety/Security | Highway Trans. Fund 6 | 20000 | 24998 | 2016-12-16 | 100% | 100% | 0 | 24998 | 0
827 | 835 | 1133 | 402 | 373 | 373 | 372 | 370 | 18470402317 | Electrical Panel Upgrades - Rockwall MNT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 21667 | 2016-10-21 | 100% | 100% | 0 | 21667 | 0
1079 | 1087 | 333 | 400 | 375 | 374 | 373 | 371 | 18470402570 | Paint Exterior - Denton Area Engineer & MNT | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24990 | 2016-12-14 | 100% | 100% | 0 | 24990 | 0
281 | 293 | 356 | 358 | 376 | 375 | 374 | 372 | 05470401769 | Replace Roof - District Headquarters | Roofing | Highway Trans. Fund 6 | 40000 | 102950 | 2017-04-25 | 100% | 100% | 0 | 102950 | 0
N/A | 85 | 657 | 376 | 377 | 376 | 375 | 373 | 08470402983 | Slab repair - Baird MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 46715 | 2017-02-23 | 100% | 100% | 0 | 46715 | 0
300 | 312 | 332 | 379 | 378 | 377 | 376 | 374 | 24470401789 | Upgrade Evaporative AC Unit In The Shop. Add Heaters And Double Door - El Paso Area Engineer & MNT | HVAC | Highway Trans. Fund 6 | 35000 | 4815 | 2016-09-26 | 100% | 100% | 0 | 4815 | 0
864 | 872 | 325 | 405 | 379 | 378 | 377 | 375 | 16470402355 | Replace Flooring At Maintenance - Kingsville MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 13333 | 2017-01-19 | 100% | 100% | 0 | 13333 | 0 | Let with 2355,2449,2458
958 | 966 | 327 | 406 | 380 | 379 | 378 | 376 | 16470402449 | Replace Flooring At Area Engineer And Maintenance - Corpus Christi AEM | Capital Repairs | Highway Trans. Fund 6 | 20000 | 13333 | 2016-12-12 | 100% | 100% | 0 | 13333 | 0 | Let with 2355,2449,2458
967 | 975 | 338 | 407 | 381 | 380 | 379 | 377 | 16470402458 | Replace Flooring At Area Engineer And Maintenance - Sinton AEM | Capital Repairs | Highway Trans. Fund 6 | 20000 | 13333 | 2016-12-19 | 100% | 100% | 0 | 13333 | 0 | Let with 2355,2449,2458
904 | 912 | 1187 | 450 | 382 | 381 | 380 | 378 | 06470402395 | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Capital Repairs | Highway Trans. Fund 6 | 20000 | 23975 | 2016-12-22 | 100% | 100% | 0 | 23975 | 0
N/A | N/A | N/A | N/A | 383 | 382 | 381 | 379 | 16470403040 | Boiler - Corpus Christi | HVAC | Highway Trans. Fund 6 | 0 | 32615 | 2017-02-09 | 100% | 100% | 0 | 32615 | 0
1089 | 1097 | 655 | 375 | 384 | 383 | 382 | 380 | 38470402580 | Repair Drainage Issues Around Hangars Water Run Off Going Inside - Austin Flight Services | Capital Repairs | Highway Trans. Fund 6 | 60000 | 260468 | 2017-03-07 | 100% | 100% | 0 | 260468 | 0
322 | 334 | 402 | 374 | 385 | 384 | 383 | 381 | 18470401811 | Roof - Coating Metal Roof Over Storage/Salt Shed - Ennis MNT | Roofing | Highway Trans. Fund 6 | 40000 | 70748 | 2017-05-05 | 100% | 100% | 0 | 70748 | 0
811 | 819 | 647 | 382 | 386 | 385 | 384 | 382 | 24470402301 | Install Bird Screens @ Truck Bays - Dell City MNT | Capital Repairs | Highway Trans. Fund 6 | 5500 | 7965 | 2017-04-04 | 100% | 100% | 0 | 7965 | 0
1085 | 1093 | 650 | 410 | 387 | 386 | 385 | 383 | 21470402576 | Flooring Replacement - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 4523 | 2016-10-10 | 100% | 100% | 0 | 4523 | 0
26 | 81 | 261 | 413 | 388 | 387 | 386 | 384 | 09470401518 | Modifications/Upgrade HVAC - Waco District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 484267 | 2017-09-27 | 100% | 100% | 0 | 484267 | 0
N/A | N/A | N/A | 367 | 389 | 388 | 387 | 385 | 12470402639 | Install Safety Flooring - District Headquarter | Capital Repairs | Highway Trans. Fund 6 | 45000 | 52000 | 2017-05-16 | 100% | 100% | 0 | 52000 | 0
N/A | N/A | 665 | 364 | 390 | 389 | 388 | 386 | 08470402690 | Build Canopy Over The Back Door Of Building - Sweetwater MNT | Site Work | Highway Trans. Fund 6 | 0 | 3414 | 2016-10-12 | 100% | 100% | 0 | 3414 | 0
1072 | 1080 | 244 | 385 | 391 | 390 | 389 | 387 | 17470402563 | Install Welding Ventilation Hood - Hearne AEM | Capital Repairs | Highway Trans. Fund 6 | 7500 | 4535 | 2016-11-22 | 100% | 100% | 0 | 4535 | 0
N/A | N/A | N/A | 408 | 392 | 391 | 390 | 388 | 05470403039 | Replace carpet - Lubbock | Capital repairs | Highway Trans. Fund 6 | 0 | 13876 | 2017-05-08 | 100% | 100% | 0 | 13876 | 0
677 | 687 | 1014 | 421 | 393 | 392 | 391 | 389 | 38470402166 | Replace Data Closet AC - Camp Hubbard State Headquarters | Capital Repairs | Highway Trans. Fund 6 | 6000 | 9794 | 2017-01-20 | 100% | 100% | 0 | 9794 | 0
287 | 299 | 346 | 434 | 394 | 393 | 392 | 390 | 21470401776 | HVAC Upgrade In HQ Bldg. - District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 506557 | 2017-11-08 | 100% | 100% | 0 | 506557 | 0
69 | 120 | 342 | 356 | 395 | 394 | 393 | 391 | 15470401701 | Replace Roof - Pearsall MNT | Roofing | Highway Trans. Fund 6 | 65000 | 70505 | 2017-05-23 | 100% | 100% | 0 | 70505 | 0
140 | 176 | 344 | 357 | 396 | 395 | 394 | 392 | 15470401617 | Replace Roof - Seguin AEM | Roofing | Highway Trans. Fund 6 | 100000 | 186159 | 2018-03-09 | 100% | 100% | 186159 | 0 | 0
256 | 268 | 399 | 360 | 397 | 396 | 395 | 393 | 13470401744 | Roof Replacement - Gonzales MNT | Roofing | Highway Trans. Fund 6 | 200000 | 259380 | 2017-04-05 | 100% | 100% | 0 | 259380 | 0
267 | 279 | 400 | 361 | 398 | 397 | 396 | 394 | 12470401755 | Replace Roof - Houston AEM | Roofing | Highway Trans. Fund 6 | 45000 | 109955 | 2017-05-02 | 100% | 100% | 26475 | 83480 | 0
N/A | N/A | N/A | 366 | 400 | 398 | 397 | 395 | 15470403028 | Replace Roof in Kerrville - San Antonio | Roofing | Highway Trans. Fund 6 | 0 | 202052 | 2018-08-31 | 100% | 100% | 0 | 202052 | 0
N/A | 100 | 93 | 384 | 402 | 400 | 399 | 396 | 19470402979 | Restroom Upgrades - Austin Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 366373 | 2017-08-17 | 100% | 100% | 0 | 366373 | 0 | Part of 19-2619
355 | 367 | 359 | 418 | 403 | 401 | 400 | 397 | 23470401844 | Demolish Old Structures On Adjacent Site - Breckenridge MNT | Site Work | Highway Trans. Fund 6 | 39500 | 131304 | 2017-03-07 | 100% | 100% | 19626 | 111678 | 0
514 | 524 | 380 | 419 | 404 | 402 | 401 | 398 | 09470402003 | Site Drainage Improvements - Waco AEM | Site Work | Highway Trans. Fund 6 | 25200 | 377091 | 2017-03-31 | 100% | 100% | 0 | 377091 | 0
359 | 371 | 649 | 409 | 406 | 403 | 402 | 399 | 21470401848 | Repave Parking Lot - Zapata MNT | Site Work | Highway Trans. Fund 6 | 19780 | 24175 | 2016-12-22 | 100% | 100% | 0 | 24175 | 0
N/A | N/A | N/A | 442 | 408 | 404 | 403 | 400 | 38470403008 | Generator & Electrical Upgrades - Cedar Park Tech Center | Safety/Security | Highway Trans. Fund 6 | 0 | 2031853 | 2018-09-04 | 100% | 100% | 0 | 2031853 | 0
N/A | 205 | 286 | 433 | 409 | 405 | 404 | 401 | 24470402992 | Generator Replacement - El Paso District Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 488872 | 2018-04-19 | 100% | 100% | 0 | 488872 | 0
315 | 327 | 749 | 365 | 410 | 406 | 405 | 402 | 18470401804 | Fire/Sprinkler Upgrade (Obsolete Panels) - Corsicana AEM | Safety/Security | Highway Trans. Fund 6 | 25000 | 20503 | 2017-04-11 | 100% | 100% | 0 | 20503 | 0 | Let with 1782, 1804, 2637
116 | 188 | 366 | 446 | 411 | 407 | 406 | 403 | 02470401583 | Replace Roof (3 Buildings) - Ft. Worth District Headquarters | Roofing | Highway Trans. Fund 6 | 492000 | 911268 | 2018-11-16 | 100% | 100% | 0 | 911268 | 0 | Let both 1583 and 1584
1070 | 1078 | 1306 | 1060 | 412 | 408 | 407 | 404 | 13470402561 | Level Building & Repair Exterior Cracks In Brick - Yoakum Area Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 47455 | 2017-02-25 | 100% | 100% | 0 | 47455 | 0
1129 | 1137 | 215 | 370 | 413 | 409 | 408 | 405 | 17470402620 | Enclose Two Bays Of Equipment Shed - Brenham AEM | Capital Repairs | Highway Trans. Fund 6 | 10000 | 38164 | 2017-03-10 | 100% | 100% | 0 | 38164 | 0
59 | 54 | 413 | 451 | 414 | 410 | 409 | 406 | 38470401689 | Modifications/Upgrade HVAC - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 287500 | 2127645 | 2017-12-18 | 100% | 100% | 0 | 2127645 | 0
704 | 714 | 224 | 443 | 415 | 411 | 410 | 407 | 08470402193 | Add Wall, Lighting, And Ventilation - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 12500 | 2017-01-16 | 100% | 100% | 0 | 12500 | 0
160 | 179 | 398 | 372 | 416 | 412 | 411 | 408 | 19470401643 | Building 300 Storage Needs Replace Roof - Atlanta District Headquarters | Roofing | Highway Trans. Fund 6 | 200000 | 177727 | 2017-07-26 | 100% | 100% | 0 | 177727 | 0
109 | 161 | 264 | 430 | 417 | 413 | 412 | 409 | 10470401575 | Replace Roof At North Tyler Fuel Station - North Tyler MNT | Roofing | Highway Trans. Fund 6 | 85000 | 70350 | 2017-07-26 | 100% | 100% | 0 | 70350 | 0
380 | 392 | 235 | 429 | 418 | 414 | 413 | 410 | 05470401869 | Nw Side Of Long Building Dirt Work To Shed Water - Post RDC | Site Work | Highway Trans. Fund 6 | 10000 | 16245 | 2017-11-21 | 100% | 100% | 0 | 16245 | 0 | Let both 1869,1870
381 | 393 | 790 | 420 | 419 | 415 | 414 | 411 | 05470401870 | Site Work And Concrete Flume - Post RDC | Site Work | Highway Trans. Fund 6 | 50000 | 16245 | 2017-11-22 | 100% | 100% | 0 | 16245 | 0 | Let both 1869,1870
103 | 153 | 287 | 414 | 421 | 416 | 415 | 412 | 05470401568 | Replace Generator - Post RDC | Safety/Security | Highway Trans. Fund 6 | 75000 | 82725 | 2018-08-10 | 100% | 100% | 0 | 82725 | 0
5 | 167 | 259 | 371 | 422 | 417 | 416 | 413 | 22470401492 | Replace Generators (x2) - Del Rio MNT | Safety/Security | Highway Trans. Fund 6 | 50000 | 40160 | 2017-03-02 | 100% | 100% | 0 | 40160 | 0
N/A | N/A | 308 | 415 | 423 | 418 | 417 | 414 | 38470403002 | Install Bird Screens at Hangars 3 and 4 - Austin Flight Services | Site Work | Highway Trans. Fund 6 | 0 | 399880 | 2017-09-08 | 100% | 100% | 0 | 399880 | 0
174 | 155 | 409 | 363 | 424 | 419 | 418 | 415 | 21470401660 | Upgrade Security (C-CURE) - Pharr District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 363115 | 2017-12-05 | 100% | 100% | 0 | 363115 | 0
N/A | N/A | N/A | 389 | 425 | 420 | 419 | 416 | 38470403025 | Relace cooling tower and add Isolations valves - State Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 682158 | 2018-07-12 | 100% | 100% | 7800 | 674358 | 0
155 | 62 | 646 | 441 | 426 | 421 | 420 | 417 | 20470401636 | Upgrade Security (C-CURE) - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 347190 | 2018-06-29 | 100% | 100% | 347190 | 0 | 0
78 | 114 | 304 | 425 | 427 | 422 | 421 | 418 | 21470401713 | Replace Roof - Mission MNT | Roofing | Highway Trans. Fund 6 | 300000 | 276946 | 2017-11-20 | 100% | 100% | 0 | 276946 | 0
289 | 301 | 358 | 427 | 428 | 423 | 422 | 419 | 21470401778 | Replace Roof - San Benito AEM | Roofing | Highway Trans. Fund 6 | 300000 | 247852 | 2018-05-02 | 100% | 100% | 17843 | 230009 | 0
8 | 150 | 410 | 439 | 429 | 424 | 423 | 420 | 11470401495 | Upgrade Security (C-CURE) - Lufkin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 487190 | 2018-01-11 | 100% | 100% | 7080 | 480110 | 0
N/A | N/A | 396 | 388 | 430 | 425 | 424 | 421 | 11470402990 | SMFO Fire Exit - Lufkin District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 296848 | 2018-08-07 | 100% | 100% | 148452 | 148396 | 0
N/A | N/A | 268 | 386 | 432 | 427 | 425 | 422 | 11470402989 | SFMO Fire Wall - Livingston AEM | Capital Repairs | Highway Trans. Fund 6 | 0 | 93848 | 2017-10-06 | 100% | 100% | 0 | 93848 | 0
N/A | 201 | 648 | 445 | 433 | 428 | 426 | 423 | 38470402977 | ADA entrances and driveway - Austin Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 56880 | 2017-05-03 | 100% | 100% | 0 | 56880 | 0
316 | 328 | 376 | 391 | 436 | 429 | 427 | 424 | 18470401805 | Generator Backup Power Completed - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 90000 | 86957 | 2017-08-09 | 100% | 100% | 0 | 86957 | 0 | Let 1805,1806
317 | 329 | 386 | 392 | 437 | 430 | 428 | 425 | 18470401806 | HVAC Upgrade - Leibert System @ Server Room - District Headquarters | HVAC | Highway Trans. Fund 6 | 45000 | 86957 | 2017-08-09 | 100% | 100% | 0 | 86957 | 0 | Let 1805,1806
191 | 164 | 265 | 424 | 438 | 431 | 429 | 426 | 21470401683 | Replace Roof - Pharr District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 146560 | 2017-06-20 | 100% | 100% | 0 | 146560 | 0
263 | 275 | 355 | 426 | 439 | 432 | 430 | 427 | 22470401751 | Roof Repairs - Cotulla MNT | Roofing | Highway Trans. Fund 6 | 50000 | 271600 | 2018-01-16 | 100% | 100% | 0 | 271600 | 0
81 | 125 | 363 | 435 | 440 | 433 | 431 | 428 | 38470401720 | Replacement of R22 to 410 HVAC System - Austin Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 583304 | 2018-04-24 | 100% | 100% | 0 | 583304 | 0 | Let with 1720, 1815, 1817, 1818
326 | 338 | 378 | 436 | 441 | 434 | 432 | 429 | 38470401815 | Replacement of R22 to 410 HVAC System - Austin Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 583304 | 2018-04-24 | 100% | 100% | 0 | 583304 | 0 | Let with 1720, 1815, 1817, 1818
329 | 341 | 379 | 437 | 442 | 435 | 433 | 430 | 38470401818 | Replacement of R22 to 410 HVAC System - Austin Headquarters | HVAC | Highway Trans. Fund 6 | 360000 | 583304 | 2018-04-20 | 100% | 100% | 0 | 583304 | 0 | Let with 1720, 1815, 1817, 1818
328 | 340 | 404 | 438 | 443 | 436 | 434 | 431 | 38470401817 | Replace Roof | Roofing | Highway Trans. Fund 6 | 450000 | 583304 | 2018-04-24 | 100% | 100% | 0 | 583304 | 0 | Let with 1720, 1815, 1817, 1818
1053 | 1061 | 1291 | 411 | 444 | 437 | 435 | 432 | 10470402544 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 55314 | 2017-04-05 | 100% | 100% | 0 | 55314 | 0
175 | 166 | 645 | 440 | 445 | 438 | 436 | 433 | 13470401662 | Upgrade Security (C-CURE) - Yoakum District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 303567 | 2017-12-06 | 100% | 100% | 30019 | 273548 | 0
N/A | 211 | 340 | 444 | 446 | 439 | 437 | 434 | 09470402991 | SMFO Fire Exit - Waco District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 277231 | 2018-06-07 | 100% | 100% | 13862 | 263369 | 0
197 | 197 | 411 | 452 | 449 | 440 | 438 | 435 | 18470402299 | Remodel - Dallas District Main Office | Capital Construction | Highway Trans. Fund 6 | 5653246 | 7862703 | 2018-11-20 | 100% | 100% | 383777 | 7478926 | 0
98 | 169 | 364 | 462 | 451 | 442 | 439 | 436 | 15470401739 | Modifications/Upgrade HVAC - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
253 | 265 | 375 | 463 | 452 | 443 | 440 | 437 | 15470401741 | Replace All VAV and Upgrade To Electrical Control - District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
324 | 336 | 377 | 464 | 453 | 444 | 441 | 438 | 15470401813 | Replace 3 Each 20 Ton Chillers For Backup - District Headquarters | HVAC | Highway Trans. Fund 6 | 125000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
119 | 181 | 381 | 465 | 454 | 445 | 442 | 439 | 15470401590 | Install All New Hot And Chill Water Valves And Connect To New Control System - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
120 | 109 | 382 | 466 | 455 | 446 | 443 | 440 | 15470401591 | New Boiler - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
122 | 183 | 383 | 467 | 456 | 447 | 444 | 441 | 15470401593 | Replace 60 Ton Chiller - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
123 | 184 | 384 | 468 | 457 | 448 | 445 | 442 | 15470401594 | Replace All VAV and Upgrade To Electrical Control - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 100000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
279 | 291 | 385 | 469 | 458 | 449 | 446 | 443 | 15470401767 | Replace 2 - 75 Ton Chillers And Add Chiller For (Backup) - - San Antonio Transguide | HVAC | Highway Trans. Fund 6 | 150000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
252 | 264 | 724 | 531 | 459 | 450 | 447 | 444 | 15470401740 | New Boiler - District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 345377 | 2018-07-10 | 100% | 100% | 0 | 345377 | 0 | Let with 1590,1591,1593, 1594,1739,1740, 1741,1767,1813
734 | 742 | 1060 | 833 | 460 | 451 | 448 | 445 | 10470402223 | Remodel Office & New Roof - North Tyler MNT | Capital Construction | Highway Trans. Fund 6 | 300000 | 718942.84 | 2019-02-26 | 100% | 60% | 299831.84 | 419111 | 0 | 11/30/18 This project went from 90% to 60% completion based on additional scope.
293 | 305 | 741 | 368 | 461 | 452 | 449 | 446 | 18470401782 | Fire/Sprinkler Upgrade (Obsolete Panels) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 25000 | 20503 | 2017-04-11 | 100% | 100% | 0 | 20503 | 0 | Let with 1782, 1804, 2637
1146 | 1154 | 296 | 397 | 462 | 453 | 450 | 447 | 18470402637 | Floor Tile Removal - Corridors Only (Stain Concrete) - Corsicana AEM | Capital Repairs | Highway Trans. Fund 6 | 10000 | 20503 | 2017-04-11 | 100% | 100% | 0 | 20503 | 0 | Let with 1782, 1804, 2637
N/A | N/A | N/A | N/A | N/A | 454 | 451 | 448 | 08470403044 | Construct Store Front Office - Abilene District Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 38600 | 2017-06-23 | 100% | 100% | 0 | 38600 | 0
N/A | N/A | N/A | N/A | N/A | 455 | 452 | 449 | 04470403045 | Repair water line - Darrouzett MNT | Site Work | Highway Trans. Fund 6 | 0 | 23150 | 2017-01-18 | 100% | 100% | 0 | 23150 | 0
N/A | N/A | N/A | N/A | N/A | 456 | 453 | 450 | 05470403051 | Bridge Crane- Lubbock | Site Work | Highway Trans. Fund 6 | 0 | 27750 | 2017-07-17 | 100% | 100% | 0 | 27750 | 0
299 | 311 | 348 | 417 | 464 | 457 | 454 | 451 | 24470401788 | Install/Repair Roof - El Paso Area AEM | Roofing | Highway Trans. Fund 6 | 100000 | 61623 | 2017-07-24 | 100% | 100% | 0 | 61623 | 0
N/A | N/A | N/A | N/A | N/A | 458 | 455 | 452 | 08470403046 | Replace Generator - Roby MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 108823 | 2018-03-22 | 100% | 100% | 0 | 108823 | 0 | Let 08-3046, 3048, & 3049
N/A | N/A | N/A | N/A | N/A | 459 | 456 | 453 | 08470403047 | Replace Generator - Haskell MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 113448 | 2018-02-02 | 100% | 100% | 0 | 113448 | 0 | Let 08-3050 and 3047
N/A | N/A | N/A | N/A | N/A | 460 | 457 | 454 | 08470403048 | Replace Generator - Colorado MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 108823 | 2018-03-22 | 100% | 100% | 0 | 108823 | 0 | Let 08-3046, 3048, & 3049
N/A | N/A | N/A | N/A | N/A | 461 | 458 | 455 | 08470403049 | Replace Generator - Big Spring MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 108823 | 2018-03-22 | 100% | 100% | 0 | 108823 | 0 | Let 08-3046, 3048, & 3049
N/A | N/A | N/A | N/A | N/A | 462 | 459 | 456 | 08470403050 | Replace Generator - Anson MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 113448 | 2018-02-02 | 100% | 100% | 0 | 113448 | 0 | Let 08-3050 and 3047
N/A | N/A | N/A | N/A | N/A | 464 | 460 | 457 | 38470403054 | New Lift Station and site plumbing improvements - Camp Hubbard Austin | Capital Repairs | Highway Trans. Fund 6 | 0 | 241510 | 2017-11-07 | 100% | 100% | 0 | 241510 | 0
912 | 920 | 1194 | 403 | 374 | 465 | 461 | 458 | 18470402403 | Electrical Panel Upgrades - Hutchins Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 84000 | 2017-04-18 | 100% | 100% | 0 | 84000 | 0
N/A | N/A | N/A | N/A | N/A | N/A | 463 | 459 | 02470403060 | Gas Line Repairs | Safety/Security | Highway Trans. Fund 6 | 0 | 250687 | 2018-01-23 | 100% | 100% | 228087 | 22600 | 0
N/A | N/A | N/A | N/A | N/A | N/A | N/A | 462 | 01470403061 | Drainage Repairs - Paris | Site Work | Highway Trans. Fund 6 | 0 | 160247 | 2018-07-13 | 100% | 100% | 0 | 160247 | 0
N/A | N/A | N/A | N/A | N/A | N/A | N/A | 463 | 23470403063 | Automatic Gate & Operator - Brownwood | Safety/Security | Highway Trans. Fund 6 | 0 | 260000 | 2018-04-11 | 100% | 100% | 0 | 260000 | 0
N/A | N/A | N/A | N/A | N/A | N/A | N/A | 464 | 03470403064 | Storm Shelters - Ft. Worth | Safety/Security | Highway Trans. Fund 6 | 0 | 54000 | 2017-10-26 | 100% | 100% | 0 | 54000 | 0
N/A | N/A | N/A | N/A | N/A | N/A | N/A | 465 | 12470403065 | Overhead Crane Shops -Houston | Site Work | Highway Trans. Fund 6 | 0 | 54000 | 2017-05-12 | 100% | 100% | 0 | 54000 | 0
1180 | 1188 | 1375 | 1120 | 1116 | 1121 | 1124 | 466 | 17470402672 | Overhead Crane Shops - Bryan | Site Work | Highway Trans. Fund 6 | 75000 | 51685 | 2017-08-18 | 100% | 100% | 0 | 51685 | 0
[7 empty] | 467 | U1 | Statewide Planned Projects change order | Safety/Security | Highway Trans. Fund 6 | 0 | 1014714.16 | 2019-08-31 | 0% | 0% | 0 | 0 | 1014714.16
PROJECTS LISTED ABOVE CURRENTLY FUNDED $67.2 (Includes $2M ABR in May 2017 and $2.5M added in August 2017) | [10 empty] | 67198859 | 40127926 | 67198859 |  |  |  | 2965592.84 | 63218552 | 1014714.16
PROJECTS LISTED BELOW WAITING FOR TXDOT FUNDING ALLOCATION
N/A | N/A | N/A | N/A | N/A | N/A | 462 | 467 | 17470403059 | HVAC Renovations | HVAC | Highway Trans. Fund 6 | 0 | 0
1161 | 1169 | 246 | 324 | 324 | 324 | 466 | 468 | 11470402652 | Renovate Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 0
709 | 719 | 192 | 412 | 431 | 426 | 467 | 469 | 02470402198 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500
N/A | N/A | 307 | 460 | 450 | 441 | 468 | 470 | 38470403000 | Retrofit Hangar 2 for Additional Maintenance Hangar/New Emergency Generator - Austin Flight Services | Safety/Security | Highway Trans. Fund 6 | 0 | 0
N/A | N/A | N/A | N/A | N/A | 463 | 469 | 471 | 14470403052 | Renovation of Fleet Facility - Fredericksburg MNT | Site Work | Highway Trans. Fund 6 | 0 | 600000
603 | 613 | 965 | 745 | 434 | 466 | 470 | 472 | 19470402092 | HVAC Upgrade In HQ Bldg. - District Headquarters | HVAC | Highway Trans. Fund 6 | 87000 | 0
776 | 784 | 1092 | 865 | 447 | 468 | 471 | 473 | 02470402265 | Renovate Maintenance Facility | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
N/A | N/A | N/A | N/A | 463 | 469 | 472 | 474 | 12470403041 | Replace Roof | Roofing | Highway Trans. Fund 6 | 0 | 140000
211 | 225 | 684 | 123 | 465 | 470 | 473 | 475 | 02470401548 | Upgrade Security (C-CURE) Phase I above the line w JOC 211A - MNTs | Safety/Security | Highway Trans. Fund 6 | 448000 | 305000
108 | 195 | 365 | 359 | 466 | 471 | 474 | 476 | 10470401574 | Replace Roof (Goat shed) - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 100000 | 100000
269 | 281 | 401 | 373 | 467 | 472 | 475 | 477 | 12470401757 | Replace Roof - Rosenberg Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 10000 | 10000
E5 | 84 | 387 | 423 | 468 | 473 | 476 | 478 | 10470402976 | Fire supression system water line - Athens Regional Distribution Center | Site Work | Highway Trans. Fund 6 | 0 | 200000
141 | 196 | 374 | 431 | 469 | 474 | 477 | 479 | 10470401621 | Replace Roof On Old Lab - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 200000 | 200000
335 | 347 | 311 | 448 | 470 | 475 | 478 | 480 | 21470401824 | Reconfigure Parking Lot - Pharr Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 41000 | 41000
29 | 59 | 180 | 454 | 471 | 476 | 479 | 481 | 08470401527 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
173 | 57 | 181 | 455 | 472 | 477 | 480 | 482 | 11470401659 | Replace HVAC Controls - Lufkin District Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 30000
772 | 780 | 182 | 456 | 473 | 478 | 481 | 483 | 16470402261 | Replace Overhead Gas Heaters In Auto Shop - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 24000 | 24000
264 | 276 | 196 | 457 | 474 | 479 | 482 | 484 | 22470401752 | Upgrade Propane Generator - Cotulla Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 25000 | 25000
183 | 152 | 208 | 458 | 475 | 480 | 483 | 485 | 04470401672 | Install Rooftop HVAC To Heat And Cool Shop - Amarillo District Headquarters | HVAC | Highway Trans. Fund 6 | 50000 | 50000
319 | 331 | 276 | 459 | 476 | 481 | 484 | 486 | 12470401808 | Upgrade Site Lighting - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 100000 | 100000
261 | 273 | 354 | 461 | 477 | 482 | 485 | 487 | 22470401749 | Replace Roof - Del Rio Maintenance Office | Roofing | Highway Trans. Fund 6 | 50000 | 50000
301 | 313 | 652 | 470 | 478 | 483 | 486 | 488 | 24470401790 | Upgrade Front/Rear Entrance Gates - El Paso (East) Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 75000 | 75000
302 | 314 | 653 | 471 | 479 | 484 | 487 | 489 | 24470401791 | Secure The Lobby Area - El Paso (West) Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 125000 | 125000
121 | 182 | 654 | 472 | 480 | 485 | 488 | 490 | 15470401592 | New HVAC In Shop Restrooms - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
47 | 134 | 656 | 473 | 481 | 486 | 489 | 491 | 21470401559 | Upgrade Lighting And Gates - Hebbronville Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 0 | 336000
N/A | N/A | 666 | 474 | 482 | 487 | 490 | 492 | 11470402692 | Fuel Canopy - Standalone per Byron Hicks 6/3/16 - Center Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21000
N/A | N/A | 667 | 475 | 483 | 488 | 491 | 493 | 24470402703 | Install Canopy At Truck Wash Pit Standalone per Byron Hicks 6/3/16 - Marfa Sub-Section | Site Work | Highway Trans. Fund 6 | 0 | 21500
N/A | N/A | 668 | 476 | 484 | 489 | 492 | 494 | 24470402704 | Install A Canopy Over Existing Truck Wash Standalone per Byron Hicks 6/3/16 - Presidio Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21500
N/A | N/A | 669 | 477 | 485 | 490 | 493 | 495 | 24470402705 | Install A Canopy Over Existing Truck Wash Standalone per Byron Hicks 6/3/16 - Terlingua Sub-Section | Site Work | Highway Trans. Fund 6 | 0 | 21500
N/A | N/A | 670 | 478 | 486 | 491 | 494 | 496 | 24470402706 | Install Canopy Over Existing Truck Wash Pit Standalone per Byron Hicks 6/3/16 - Van Horn Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 11500
N/A | N/A | 671 | 479 | 487 | 492 | 495 | 497 | 11470402711 | Fuel Canopy Standalone per Byron Hicks 6/3/16 - Shepherd Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21000
199 | 213 | 673 | 480 | 488 | 493 | 496 | 498 | 24470401509 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
200 | 214 | 674 | 481 | 489 | 494 | 497 | 499 | 07470401516 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
201 | 215 | 675 | 482 | 490 | 495 | 498 | 500 | 07470401520 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
202 | 216 | 676 | 483 | 491 | 496 | 499 | 501 | 25470401521 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
204 | 218 | 677 | 484 | 492 | 497 | 500 | 502 | 05470401523 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1680000 | 1680000
205 | 219 | 678 | 485 | 493 | 498 | 501 | 503 | 06470401524 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
206 | 220 | 679 | 486 | 494 | 499 | 502 | 504 | 08470401528 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
207 | 221 | 680 | 487 | 495 | 500 | 503 | 505 | 04470401529 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1680000 | 1680000
208 | 222 | 681 | 488 | 496 | 501 | 504 | 506 | 17470401531 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
209 | 223 | 682 | 489 | 497 | 502 | 505 | 507 | 16470401534 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 896000 | 350000
210 | 224 | 683 | 490 | 498 | 503 | 506 | 508 | 11470401537 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
212 | 226 | 685 | 492 | 499 | 504 | 507 | 509 | 15470401550 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 350000
213 | 227 | 686 | 493 | 500 | 505 | 508 | 510 | 18470401551 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
214 | 228 | 687 | 494 | 501 | 506 | 509 | 511 | 05470401552 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
215 | 229 | 688 | 495 | 502 | 507 | 510 | 512 | 01470401556 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
216 | 230 | 689 | 496 | 503 | 508 | 511 | 513 | 01470401557 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
203 | 217 | 690 | 497 | 504 | 509 | 512 | 514 | 25470401522 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
218 | 232 | 691 | 498 | 505 | 510 | 513 | 515 | 15470401560 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 536000
219 | 233 | 692 | 499 | 506 | 511 | 514 | 516 | 10470401561 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
220 | 234 | 693 | 500 | 507 | 512 | 515 | 517 | 10470401562 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
221 | 235 | 694 | 501 | 508 | 513 | 516 | 518 | 09470401563 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
222 | 236 | 695 | 502 | 509 | 514 | 517 | 519 | 03470401564 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
223 | 237 | 696 | 503 | 510 | 515 | 518 | 520 | 03470401565 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
224 | 238 | 697 | 504 | 511 | 516 | 519 | 521 | 13470401566 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
225 | 239 | 698 | 505 | 512 | 517 | 520 | 522 | 21470401569 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
226 | 240 | 699 | 506 | 513 | 518 | 521 | 523 | 22470401586 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
227 | 241 | 700 | 507 | 514 | 519 | 522 | 524 | 09470401603 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
228 | 242 | 701 | 508 | 515 | 520 | 523 | 525 | 19470401608 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
229 | 243 | 702 | 509 | 516 | 521 | 524 | 526 | 19470401609 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
217 | 231 | 703 | 510 | 517 | 522 | 525 | 527 | 21470401558 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
231 | 244 | 704 | 511 | 518 | 523 | 526 | 528 | 06470401614 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
233 | 245 | 705 | 512 | 519 | 524 | 527 | 529 | 13470401618 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
234 | 246 | 706 | 513 | 520 | 525 | 528 | 530 | 13470401622 | Repair Leaking Metal Roofs - Austin Cty Maint. | Roofing | Highway Trans. Fund 6 | 50000 | 50000
235 | 247 | 707 | 514 | 521 | 526 | 529 | 531 | 04470401624 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
236 | 248 | 708 | 515 | 522 | 527 | 530 | 532 | 23470401637 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
237 | 249 | 709 | 516 | 523 | 528 | 531 | 533 | 17470401647 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
238 | 250 | 710 | 517 | 524 | 529 | 532 | 534 | 20470401666 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
239 | 251 | 711 | 518 | 525 | 530 | 533 | 535 | 18470401668 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
240 | 252 | 712 | 519 | 526 | 531 | 534 | 536 | 02470401678 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
241 | 253 | 713 | 520 | 527 | 532 | 535 | 537 | 12470401679 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
242 | 254 | 714 | 521 | 528 | 533 | 536 | 538 | 11470401681 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
243 | 255 | 715 | 522 | 529 | 534 | 537 | 539 | 20470401706 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
244 | 256 | 716 | 523 | 530 | 535 | 538 | 540 | 23470401707 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
245 | 257 | 717 | 524 | 531 | 536 | 539 | 541 | 06470401709 | Install Motion Sensors On Install Automatic Gate - Iraan Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
246 | 258 | 718 | 525 | 532 | 537 | 540 | 542 | 12470401714 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
247 | 259 | 719 | 526 | 533 | 538 | 541 | 543 | 24470401715 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
248 | 260 | 720 | 527 | 534 | 539 | 542 | 544 | 22470401716 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
249 | 261 | 721 | 528 | 535 | 540 | 543 | 545 | 06470401717 | Install Motion Sensors On Install Automatic Gate - Balmorhea Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
250 | 262 | 722 | 529 | 536 | 541 | 544 | 546 | 14470401727 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
251 | 263 | 723 | 530 | 537 | 542 | 545 | 547 | 16470401732 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
254 | 266 | 725 | 532 | 538 | 543 | 546 | 548 | 10470401742 | Site Improvements - Jacksonville Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12000 | 12000
255 | 267 | 726 | 533 | 539 | 544 | 547 | 549 | 13470401743 | Convert Flat Roof To Gable Style - Gonzales Cty Maint. | Roofing | Highway Trans. Fund 6 | 250000 | 250000
262 | 274 | 728 | 534 | 540 | 545 | 548 | 550 | 22470401750 | Upgrade HVAC - Del Rio Maintenance Office (US 90) | HVAC | Highway Trans. Fund 6 | 10000 | 10000
268 | 280 | 729 | 535 | 541 | 546 | 549 | 551 | 12470401756 | Replace Roof - Humble Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 87000 | 87000
270 | 282 | 730 | 536 | 542 | 547 | 550 | 552 | 22470401758 | New HVAC In Shop Restrooms - District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
271 | 283 | 731 | 537 | 543 | 548 | 551 | 553 | 22470401759 | Replace Roof - District Headquarters | Roofing | Highway Trans. Fund 6 | 225000 | 225000
272 | 284 | 732 | 538 | 544 | 549 | 552 | 554 | 22470401760 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
273 | 285 | 733 | 539 | 545 | 550 | 553 | 555 | 22470401761 | Exterior Lighting - Laredo Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 40000 | 40000
275 | 287 | 734 | 540 | 546 | 551 | 554 | 556 | 22470401763 | Restrooms HVAC - Laredo Auto Shop | HVAC | Highway Trans. Fund 6 | 20000 | 20000
276 | 288 | 735 | 541 | 547 | 552 | 555 | 557 | 22470401764 | Repair MNT To Auto Shop Roof - Laredo District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 250000
280 | 292 | 737 | 542 | 548 | 553 | 556 | 558 | 24470401768 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
282 | 294 | 738 | 543 | 549 | 554 | 557 | 559 | 15470401770 | HVAC Upgrade- I had below line but SS was accepted? - Bexar Metro Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 15000
290 | 302 | 739 | 544 | 550 | 555 | 558 | 560 | 20470401779 | Install Card Reader Access - Beaumont Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 16000 | 16000
291 | 303 | 740 | 545 | 551 | 556 | 559 | 561 | 25470401780 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
294 | 306 | 742 | 546 | 552 | 557 | 560 | 562 | 13470401783 | Upgrade Apu To Supply Entire Maintenace Building - Fayette Cty Maint. | Safety/Security | Highway Trans. Fund 6 | 125000 | 125000
295 | 307 | 743 | 547 | 553 | 558 | 561 | 563 | 20470401784 | A/C Unit Replacement - Liberty Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 7500
296 | 308 | 744 | 548 | 554 | 559 | 562 | 564 | 20470401785 | A/C Unit Replacement - Liberty Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 18000 | 18000
304 | 316 | 745 | 549 | 555 | 560 | 563 | 565 | 22470401793 | HVAC Replacement - Freer | HVAC | Highway Trans. Fund 6 | 17000 | 17000
314 | 326 | 748 | 550 | 556 | 561 | 564 | 566 | 22470401803 | Install Gate Operator And Key Pad - La Pryor on HWY 57 | Safety/Security | Highway Trans. Fund 6 | 5000 | 5000
318 | 330 | 750 | 551 | 557 | 562 | 565 | 567 | 12470401807 | Install CCTV Security Camera (Parking Garage) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 20000 | 20000
320 | 332 | 751 | 552 | 558 | 563 | 566 | 568 | 12470401809 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
321 | 333 | 752 | 553 | 559 | 564 | 567 | 569 | 16470401810 | Replace Roof On The Maintenance Building - Aransas Co. | Roofing | Highway Trans. Fund 6 | 250000 | 250000
327 | 339 | 754 | 554 | 560 | 565 | 568 | 570 | 38470401816 | Install Redundant UPS for Data Center - Riverside Annex II RA150-200 | Safety/Security | Highway Trans. Fund 6 | 250000 | 250000
330 | 342 | 755 | 555 | 561 | 566 | 569 | 571 | 38470401819 | Roof and Weatherize Exterior - Riverside Annex II RA150-200 | Roofing | Highway Trans. Fund 6 | 350000 | 350000
332 | 344 | 756 | 556 | 562 | 567 | 570 | 572 | 21470401821 | Add Exit Only Gate To East Side - Edcouch Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 16000 | 16000
333 | 345 | 757 | 557 | 563 | 568 | 571 | 573 | 17470401822 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
336 | 348 | 758 | 558 | 564 | 569 | 572 | 574 | 21470401825 | Rework Concrete Drainage Structure - Pharr Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 11000 | 11000
337 | 349 | 759 | 559 | 565 | 570 | 573 | 575 | 22470401826 | Sprinkler System Repair & Upgrade - Del Rio | Site Work | Highway Trans. Fund 6 | 20000 | 20000
338 | 350 | 760 | 560 | 566 | 571 | 574 | 576 | 22470401827 | Furnish/Install Bollard - Del Rio Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
342 | 354 | 761 | 561 | 567 | 572 | 575 | 577 | 07470401831 | Install New 10,000 Gallon Brine Storge Tank - Eden Maintenance Office | Site Work | Highway Trans. Fund 6 | 6000 | 6000
343 | 355 | 762 | 562 | 568 | 573 | 576 | 578 | 07470401832 | Pavement Seal Coat And Restripe - Eden Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
346 | 358 | 765 | 563 | 569 | 574 | 577 | 579 | 24470401835 | Install Back Rockwall - Fort Hancock Sub-Section | Site Work | Highway Trans. Fund 6 | 18000 | 18000
348 | 360 | 767 | 564 | 570 | 575 | 578 | 580 | 07470401837 | Pavement Seal Coat And Restripe - Leakey Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
352 | 364 | 770 | 565 | 571 | 576 | 579 | 581 | 07470401841 | Pavement Seal Coat And Restripe - Ballinger Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
356 | 368 | 772 | 566 | 572 | 577 | 580 | 582 | 16470401845 | Add Additional Lateral Lines To Septic System At The Alice Ae Office - Jim Wells Co. | Site Work | Highway Trans. Fund 6 | 15000 | 15000
357 | 369 | 773 | 567 | 573 | 578 | 581 | 583 | 18470401846 | Asphalt Overlay Parking Lot - Ennis Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
360 | 372 | 774 | 568 | 574 | 579 | 582 | 584 | 20470401849 | Rehab Parking Lot And Drainage - Anahuac Maintenance Office | Site Work | Highway Trans. Fund 6 | 30000 | 30000
363 | 375 | 776 | 569 | 575 | 580 | 583 | 585 | 20470401852 | Remove Out Of Service Emulsion, Linseed Oil & Asts - Newton Maintenance Office | Site Work | Highway Trans. Fund 6 | 55000 | 55000
364 | 376 | 777 | 570 | 576 | 581 | 584 | 586 | 20470401853 | Electric Service To Yard - Stowel Maintenance Office | Site Work | Highway Trans. Fund 6 | 4000 | 4000
366 | 378 | 778 | 571 | 577 | 582 | 585 | 587 | 18470401855 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 207000 | 207000
367 | 379 | 779 | 572 | 578 | 583 | 586 | 588 | 18470401856 | Asphalt Overlay Parking Lot - District Headquarters | Site Work | Highway Trans. Fund 6 | 75000 | 75000
369 | 381 | 780 | 573 | 579 | 584 | 587 | 589 | 22470401858 | Fuel Pump Replacements - Brackettville | Site Work | Highway Trans. Fund 6 | 15000 | 15000
370 | 382 | 781 | 574 | 580 | 585 | 588 | 590 | 22470401859 | Landscaping & Irrigation - Brackettville | Site Work | Highway Trans. Fund 6 | 45000 | 45000
371 | 383 | 782 | 575 | 581 | 586 | 589 | 591 | 07470401860 | Overlay And Restripe Parking Lot - San Angelo Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
372 | 384 | 783 | 576 | 582 | 587 | 590 | 592 | 07470401861 | Install New Automated Vehicle Entry Gate - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
373 | 385 | 784 | 577 | 583 | 588 | 591 | 593 | 07470401862 | Pavement Seal Coat and Restripe - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
374 | 386 | 785 | 578 | 584 | 589 | 592 | 594 | 07470401863 | Replace Underground Fuel Tanks With New Above Ground Tanks - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
376 | 388 | 786 | 579 | 585 | 590 | 593 | 595 | 07470401865 | Pavement Seal Coat And Restripe - Sterling City Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
377 | 389 | 787 | 580 | 586 | 591 | 594 | 596 | 07470401866 | Replace Automated Swing Gate With Automated Sliding Gate - Sterling City Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
379 | 391 | 789 | 581 | 587 | 592 | 595 | 597 | 25470401868 | Resurface Parking Lot - Munday Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
382 | 394 | 791 | 582 | 588 | 593 | 596 | 598 | 21470401871 | New Fire Proof Overhead Doors - Raymondville Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
383 | 395 | 792 | 583 | 589 | 594 | 597 | 599 | 21470401872 | Resurface Maintenance Yard - Raymondville Maintenance Office | Site Work | Highway Trans. Fund 6 | 134800 | 134800
384 | 396 | 793 | 584 | 590 | 595 | 598 | 600 | 10470401873 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 110000 | 110000
385 | 397 | 794 | 585 | 591 | 596 | 599 | 601 | 08470401874 | Parking Lot Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
388 | 400 | 795 | 586 | 592 | 597 | 600 | 602 | 24470401877 | Demolish Old Emulsion Tank - Fort Davis Maintenance Office | Site Work | Highway Trans. Fund 6 | 8500 | 8500
389 | 401 | 796 | 587 | 593 | 598 | 601 | 603 | 24470401878 | Install Sprinkler System - Fort Davis Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
390 | 402 | 797 | 588 | 594 | 599 | 602 | 604 | 02470401879 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 303000 | 303000
391 | 403 | 798 | 589 | 595 | 600 | 603 | 605 | 06470401880 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
392 | 404 | 799 | 590 | 596 | 601 | 604 | 606 | 06470401881 | Xeroscape Grounds - District Headquarters | Site Work | Highway Trans. Fund 6 | 264000 | 264000
393 | 405 | 800 | 591 | 597 | 602 | 605 | 607 | 06470401882 | Reconfigure Parking In Front Of Office - Odessa Maintenance Office | Site Work | Highway Trans. Fund 6 | 30000 | 30000
396 | 408 | 801 | 592 | 598 | 603 | 606 | 608 | 07470401885 | Replace Underground Fuel Tanks With New Above Ground Tanks - Junction Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
398 | 410 | 802 | 593 | 599 | 604 | 607 | 609 | 07470401887 | Pavement Seal Coat And Restripe - Junction Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
400 | 412 | 804 | 594 | 600 | 605 | 608 | 610 | 15470401889 | Change Out Galvanized Water Main Piping - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
401 | 413 | 805 | 595 | 601 | 606 | 609 | 611 | 15470401890 | Change Out Galvanized Water Main Piping - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
402 | 414 | 806 | 596 | 602 | 607 | 610 | 612 | 15470401891 | Parking Lot Resurfacing & Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
405 | 417 | 808 | 598 | 603 | 608 | 611 | 613 | 15470401894 | Replace Radio Tower - Seguin Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
406 | 418 | 809 | 599 | 604 | 609 | 612 | 614 | 07470401895 | Pavement Seal Coat And Restripe - Sonora Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
407 | 419 | 810 | 600 | 605 | 610 | 613 | 615 | 13470401896 | Install Above Ground Fuel System/New Dispenser - Austin Cty Maint. | Site Work | Highway Trans. Fund 6 | 250000 | 250000
408 | 420 | 811 | 601 | 606 | 611 | 614 | 616 | 13470401897 | Install Above Ground Fuel System/New Dispenser - Colorado Cty Maint. | Site Work | Highway Trans. Fund 6 | 250000 | 250000
409 | 421 | 812 | 602 | 607 | 612 | 615 | 617 | 20470401898 | Additional Sidewalks - Beaumont Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
410 | 422 | 813 | 603 | 608 | 613 | 616 | 618 | 20470401899 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 101000 | 101000
411 | 423 | 814 | 604 | 609 | 614 | 617 | 619 | 20470401900 | Rehab Parking Lot And Stripe - District Headquarters | Site Work | Highway Trans. Fund 6 | 450000 | 450000
414 | 426 | 815 | 605 | 610 | 615 | 618 | 620 | 20470401903 | Re-Stripe Parking Lots And Hc Spaces - Districtwide | Site Work | Highway Trans. Fund 6 | 25000 | 25000
415 | 427 | 816 | 606 | 611 | 616 | 619 | 621 | 07470401904 | Pavement Seal Coat And Restripe - Rocksprings Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
417 | 429 | 818 | 607 | 612 | 617 | 620 | 622 | 03470401906 | Construct In-Ground Storm Shelter - District Headquarters | Site Work | Highway Trans. Fund 6 | 45000 | 45000
418 | 430 | 819 | 608 | 613 | 618 | 621 | 623 | 03470401907 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
419 | 431 | 820 | 609 | 614 | 619 | 622 | 624 | 03470401908 | Repave Parking Lot - Wichita Falls DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
420 | 432 | 821 | 610 | 615 | 620 | 623 | 625 | 16470401909 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 100000 | 100000
421 | 433 | 822 | 611 | 616 | 621 | 624 | 626 | 16470401910 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 125000 | 125000
422 | 434 | 823 | 612 | 617 | 622 | 625 | 627 | 16470401911 | Rehab Existing Parking Lots On Entire Campus - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
423 | 435 | 824 | 613 | 618 | 623 | 626 | 628 | 16470401912 | Repair Sidewalk Or Parking Lot - Corpus Christi DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
425 | 437 | 825 | 614 | 619 | 624 | 627 | 629 | 16470401914 | Replace Fuel Dispenser At Maintenance Special Jobs - Corpus Christi DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 20000 | 20000
427 | 439 | 826 | 615 | 620 | 625 | 628 | 630 | 06470401916 | Paint 10000 Gal Asphalt Tank & Insulate - Crane Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
428 | 440 | 827 | 616 | 621 | 626 | 629 | 631 | 21470401917 | Upgrade Landscaping to include Hike And Bike Trail - District Headquarters | Site Work | Highway Trans. Fund 6 | 100000 | 100000
429 | 441 | 828 | 617 | 622 | 627 | 630 | 632 | 21470401918 | Increase Parking Area - District Headquarters | Site Work | Highway Trans. Fund 6 | 350000 | 350000
430 | 442 | 829 | 618 | 623 | 628 | 631 | 633 | 21470401919 | Parking Lot Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 400000 | 400000
432 | 444 | 830 | 619 | 624 | 629 | 632 | 634 | 07470401921 | Pavement Seal Coat And Restripe - Ozona Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
434 | 446 | 832 | 620 | 625 | 630 | 633 | 635 | 13470401923 | Install Above Ground Fuel System/New Dispenser - District Headquarters | Site Work | Highway Trans. Fund 6 | 250000 | 250000
435 | 447 | 833 | 621 | 626 | 631 | 634 | 636 | 13470401924 | Replace Deteriorating Natural Gas Lines And Exterior Valves - District Headquarters | Site Work | Highway Trans. Fund 6 | 40000 | 40000
436 | 448 | 834 | 622 | 627 | 632 | 635 | 637 | 20470401925 | Rehab Parking Lot And Stripe - Port Arthur Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
437 | 449 | 835 | 623 | 628 | 633 | 636 | 638 | 23470401926 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 155000 | 155000
438 | 450 | 836 | 624 | 629 | 634 | 637 | 639 | 18470401927 | Asphalt Overlay Parking Lot - Waxahachie Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
440 | 452 | 837 | 625 | 630 | 635 | 638 | 640 | 18470401929 | Asphalt Emulsion Tank Installation - Rockwall Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
441 | 453 | 177 | 179 | 179 | 179 | 179 | 641 | 18470401930 | Asphalt Overlay Parking Lot - Rockwall MNT | Site Work | Highway Trans. Fund 6 | 20000 | 0
442 | 454 | 178 | 180 | 180 | 180 | 180 | 642 | 18470401931 | Parking Lot Striping- Rockwall MNT | Site Work | Highway Trans. Fund 6 | 5000 | 0
444 | 456 | 839 | 626 | 631 | 636 | 639 | 643 | 07470401933 | Pavement Seal Coat And Restripe - District Headquarters | Site Work | Highway Trans. Fund 6 | 30000 | 30000
445 | 457 | 840 | 627 | 632 | 637 | 640 | 644 | 07470401934 | Replace Underground Fuel Tanks With New Above Ground Tanks - District Headquarters | Site Work | Highway Trans. Fund 6 | 75000 | 75000
447 | 458 | 841 | 628 | 633 | 638 | 641 | 645 | 20470401936 | Rehab Parking Lot And Stripe - Kountze Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
448 | 459 | 842 | 629 | 634 | 639 | 642 | 646 | 24470401937 | Resufacing of Parking Lot - Terlingua Sub-Section | Site Work | Highway Trans. Fund 6 | 25000 | 25000
449 | 460 | 843 | 630 | 635 | 640 | 643 | 647 | 13470401938 | Build New Berm Around Asphalt Tanks - Wharton Cty Maint. | Site Work | Highway Trans. Fund 6 | 40000 | 40000
452 | 462 | 844 | 631 | 636 | 641 | 644 | 648 | 18470401941 | Asphalt Overlay Parking Lot - Hutchins Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
453 | 463 | 845 | 632 | 637 | 642 | 645 | 649 | 18470401942 | Parking Lot Striping - Hutchins Maintenance Office | Site Work | Highway Trans. Fund 6 | 10000 | 10000
454 | 464 | 846 | 633 | 638 | 643 | 646 | 650 | 18470401943 | Modular Building/Site Prep - NW Dallas Maintenance Office | Site Work | Highway Trans. Fund 6 | 110000 | 110000
455 | 465 | 847 | 634 | 639 | 644 | 647 | 651 | 24470401944 | Demolish Old Emulsion Tank - Alpine Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 8400 | 8400
457 | 467 | 848 | 635 | 640 | 645 | 648 | 652 | 21470401946 | Fuel Tank Relocation - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 125000 | 125000
458 | 468 | 849 | 636 | 641 | 646 | 649 | 653 | 21470401947 | Improve Drainage - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
459 | 469 | 850 | 637 | 642 | 647 | 650 | 654 | 21470401948 | Repair Sewer Line At Rear Of Yard, Add Approx. 8 Manholes. - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
460 | 470 | 851 | 638 | 643 | 648 | 651 | 655 | 21470401949 | Resurface Parking Lot - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 26200 | 26200
461 | 471 | 852 | 639 | 644 | 649 | 652 | 656 | 07470401950 | Pavement Seal Coat And Restripe - Robert Lee Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
464 | 474 | 854 | 640 | 645 | 650 | 653 | 657 | 21470401953 | Repair Fuel Dispensing Pumps & Tanks - Laguna Vista Maintenance Office Sub-Section | Site Work | Highway Trans. Fund 6 | 12000 | 12000
465 | 475 | 855 | 641 | 646 | 651 | 654 | 658 | 15470401954 | Connect To City Water/Sewer - Bandera Maintenance Office | Site Work | Highway Trans. Fund 6 | 350000 | 350000
466 | 476 | 856 | 642 | 647 | 652 | 655 | 659 | 24470401955 | Demolish Old Emulsion Tank - Pine Springs Sub-Section | Site Work | Highway Trans. Fund 6 | 8500 | 8500
469 | 479 | 857 | 643 | 648 | 653 | 656 | 660 | 07470401958 | Install New Above Ground Fuel Tanks - Big Lake Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
470 | 480 | 858 | 644 | 649 | 654 | 657 | 661 | 07470401959 | Pavement Seal Coat And Restripe - Big Lake Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
472 | 482 | 860 | 645 | 650 | 655 | 658 | 662 | 14470401961 | Parking Lot Overlay - Burnet Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 95000 | 95000
473 | 483 | 861 | 646 | 651 | 656 | 659 | 663 | 23470401962 | Remove Underground Fuel Tanks And Install Above Ground Tanks - Goldthwaite Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
474 | 484 | 862 | 647 | 652 | 657 | 660 | 664 | 07470401963 | Replace Underground Fuel Tanks With New Above Ground Tanks - Menard Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
475 | 485 | 863 | 648 | 653 | 658 | 661 | 665 | 16470401964 | Repair Fuel Monitoring System - Corpus Christi AEM - Corpus Christi Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
476 | 486 | 864 | 649 | 654 | 659 | 662 | 666 | 16470401965 | Replace Existing Sewage Line Running To Lift Station - San Patricio Co | Site Work | Highway Trans. Fund 6 | 30000 | 30000
477 | 487 | 865 | 650 | 655 | 660 | 663 | 667 | 16470401966 | Replace Sewer Line - Sinton Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
478 | 488 | 866 | 651 | 656 | 661 | 664 | 668 | 10470401967 | Parking Improvements - Jacksonville Maintenance Office | Site Work | Highway Trans. Fund 6 | 120000 | 120000
479 | 489 | 867 | 652 | 657 | 662 | 665 | 669 | 22470401968 | Irrigation Replacement - Del Rio Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
481 | 491 | 869 | 653 | 658 | 663 | 666 | 670 | 22470401970 | Install French Drainage - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
482 | 492 | 870 | 654 | 659 | 664 | 667 | 671 | 22470401971 | Install Irrigation And Landscaping - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 4250 | 4250
483 | 493 | 871 | 655 | 660 | 665 | 668 | 672 | 22470401972 | Repave & Stripe Empl & Visitor Parking Lot - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 105000 | 105000
484 | 494 | 872 | 656 | 661 | 666 | 669 | 673 | 20470401973 | Add Connection To Public Supply For Water And Sanitary Sewer System - Jasper Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
485 | 495 | 873 | 657 | 662 | 667 | 670 | 674 | 20470401974 | Remove Out Of Service Emulsion, Linseed Oil & Asts - Jasper Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
486 | 496 | 874 | 658 | 663 | 668 | 671 | 675 | 12470401975 | Sitework Modifications (Drivewal And Visitor Parking) - Conroe Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 70000 | 70000
487 | 497 | 875 | 659 | 664 | 669 | 672 | 676 | 22470401976 | Parking Lot Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 125000 | 125000
488 | 498 | 876 | 660 | 665 | 670 | 673 | 677 | 22470401977 | Irrigation, Landscaping, Grass Seeds, Planting/Adding Trees - Laredo Administration & Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 225000 | 225000
489 | 499 | 877 | 661 | 666 | 671 | 674 | 678 | 22470401978 | Reconfigure Landscaping For Walking Trail - Laredo District Headquarters | Site Work | Highway Trans. Fund 6 | 80000 | 80000
490 | 500 | 878 | 662 | 667 | 672 | 675 | 679 | 24470401979 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 318000 | 318000
491 | 501 | 879 | 663 | 668 | 673 | 676 | 680 | 13470401980 | Replace Natural Gas Lines - District Headquarters | Site Work | Highway Trans. Fund 6 | 40000 | 40000
492 | 502 | 880 | 664 | 669 | 674 | 677 | 681 | 25470401981 | Replace Fuel Station - Clarendon Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
493 | 503 | 881 | 665 | 670 | 675 | 678 | 682 | 18470401982 | Asphalt Overlay Parking Lot - Denton Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
496 | 506 | 882 | 666 | 671 | 676 | 679 | 683 | 20470401985 | Regrade Parking And Drainage - Liberty Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
497 | 507 | 883 | 667 | 672 | 677 | 680 | 684 | 24470401986 | Install/Repair Rock Wall Front And Rear - El Paso (East) Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
499 | 509 | 884 | 668 | 673 | 678 | 681 | 685 | 22470401988 | Irrigation And Landscaping - Freer | Site Work | Highway Trans. Fund 6 | 10000 | 10000
500 | 510 | 885 | 669 | 674 | 679 | 682 | 686 | 38470401989 | Retrofit Of Existing Exterior Light Fixture - CEDAR PARK Research and Technology Center | Site Work | Highway Trans. Fund 6 | 60000 | 60000
501 | 511 | 886 | 670 | 675 | 680 | 683 | 687 | 10470401990 | Sewer Connect To City - South Tyler Area Engineer And Maintenance Facility - South Tyler Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 300000 | 300000
502 | 512 | 887 | 671 | 676 | 681 | 684 | 688 | 16470401991 | Repair Fuel Monitoring System - Beeville MNT - Beeville Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
503 | 513 | 888 | 672 | 677 | 682 | 685 | 689 | 16470401992 | Replace\New Fuel Dispenser/Fuel Pump At Maintenance - Beeville MNT - Beeville Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
504 | 514 | 889 | 673 | 678 | 683 | 686 | 690 | 08470401993 | Reroute Wash Bay Drain To City Sewer Drain - Abilene Maintenance Office | Site Work | Highway Trans. Fund 6 | 10000 | 10000
505 | 515 | 890 | 674 | 679 | 684 | 687 | 691 | 22470401994 | Resurface 2 Acres Of Parking Area In Yard & Strip Where Needed - La Pryor Maintenance Office | Site Work | Highway Trans. Fund 6 | 152000 | 152000
508 | 518 | 891 | 675 | 680 | 685 | 688 | 692 | 13470401997 | Eliminate Wash Rack Waste Water Recycle System And Convert To City Utilities - Fayette Cty Maint. | Site Work | Highway Trans. Fund 6 | 75000 | 75000
509 | 519 | 892 | 676 | 681 | 686 | 689 | 693 | 18470401998 | Asphalt Overlay Parking Lot - Corsicana Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
511 | 521 | 893 | 677 | 682 | 687 | 690 | 694 | 21470402000 | Replace Fuel Pump Canopy - Laguna Vista Maintenance Office Sub-Section | Site Work | Highway Trans. Fund 6 | 13000 | 13000
512 | 522 | 894 | 678 | 683 | 688 | 691 | 695 | 15470402001 | Parking Lot Reconfiguration - New Braunfels Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
513 | 523 | 895 | 679 | 684 | 689 | 692 | 696 | 10470402002 | Parking Improvements - Athens Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 70000 | 70000
515 | 525 | 896 | 680 | 685 | 690 | 693 | 697 | 17470402004 | Parking Area Pavement - District Headquarters | Site Work | Highway Trans. Fund 6 | 450000 | 450000
518 | 528 | 897 | 681 | 686 | 691 | 694 | 698 | 24470402007 | Insulate Interior Roof And Walls, Spray Foam. - Marathon Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
519 | 529 | 898 | 682 | 687 | 692 | 695 | 699 | 16470402008 | Replace Floor In Lab Building District - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
520 | 530 | 899 | 683 | 688 | 693 | 696 | 700 | 16470402009 | Install Electrical - George West MNT - George West Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
521 | 531 | 900 | 684 | 689 | 694 | 697 | 701 | 16470402010 | Replace Metal Siding On Office Building With New Siding - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
522 | 532 | 901 | 685 | 690 | 695 | 698 | 702 | 16470402011 | Replace Sliding Garage Doors With Overhead Doors - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
524 | 534 | 902 | 686 | 691 | 696 | 699 | 703 | 19470402013 | Remodel Inside Of Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
525 | 535 | 903 | 687 | 692 | 697 | 700 | 704 | 19470402014 | Window Replacement - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
526 | 536 | 904 | 688 | 693 | 698 | 701 | 705 | 25470402015 | Re-Skin Exterior, Insulate Bujilding, Install Windows, Roof, & Doors, Upgrade Rest Room - Guthrie Maintenance Office SS | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
527 | 537 | 905 | 689 | 694 | 699 | 702 | 706 | 01470402016 | Abatement Of Roof And Walls (Monitoring) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
528 | 538 | 906 | 690 | 695 | 700 | 703 | 707 | 01470402017 | Abatement Of Roof And Walls (Remediation) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
529 | 539 | 907 | 691 | 696 | 701 | 704 | 708 | 01470402018 | Abatement Of Roof And Walls (Testing) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
530 | 540 | 908 | 692 | 697 | 702 | 705 | 709 | 01470402019 | Boiler And Chiller Repairs - District Headquarters | HVAC | Highway Trans. Fund 6 | 100000 | 100000
532 | 542 | 909 | 693 | 698 | 703 | 706 | 710 | 01470402021 | Renovate DHQ Campus - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 1950000 | 1950000
533 | 543 | 910 | 694 | 699 | 704 | 707 | 711 | 21470402022 | Add Office And Reconfigure Space - Pharr Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 4000 | 4000
534 | 544 | 911 | 695 | 700 | 705 | 708 | 712 | 21470402023 | Add Vestibule - Pharr Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10200 | 10200
535 | 545 | 912 | 696 | 701 | 706 | 709 | 713 | 22470402024 | Convert 2Nd Floor Into Four Offices And Restroom Renovation - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
536 | 546 | 913 | 697 | 702 | 707 | 710 | 714 | 22470402025 | Replace Flooring In Mechanical Room - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
537 | 547 | 914 | 698 | 703 | 708 | 711 | 715 | 22470402026 | Roof & Exterior Painting - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 70000 | 70000
545 | 555 | 916 | 699 | 704 | 709 | 712 | 716 | 16470402034 | Replace Flooring In Office Building And Paint Walls - Refugio Co. | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
546 | 556 | 917 | 700 | 705 | 710 | 713 | 717 | 16470402035 | Replace Metal Siding On Office Building With New Siding - Refugio Co. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
547 | 557 | 918 | 701 | 706 | 711 | 714 | 718 | 16470402036 | Repair Structure At Maintenance - Refugio Maintenance - Refugio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
549 | 559 | 920 | 703 | 707 | 712 | 715 | 719 | 06470402038 | Replace Metal Roof & Exterior Walls, Insulate - Andrews Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 22000 | 22000
551 | 561 | 921 | 704 | 708 | 713 | 716 | 720 | 03470402040 | Close In Front Of New Truck Shed And Add 4 Roll Up Doors - Bowie Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
552 | 562 | 922 | 705 | 709 | 714 | 717 | 721 | 10470402041 | Replace Windows - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
553 | 563 | 923 | 706 | 710 | 715 | 718 | 722 | 38470402042 | Complete Renovation Of 5th Floor - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
554 | 564 | 924 | 707 | 711 | 716 | 719 | 723 | 38470402043 | Retrofit Of Existing Exterior Light Fixture - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
557 | 567 | 925 | 708 | 712 | 717 | 720 | 724 | 20470402046 | Reskin, Replace Lighting And Reroof Bld - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 95000 | 95000
558 | 568 | 926 | 709 | 713 | 718 | 721 | 725 | 25470402047 | Replace Floor Tiles, Upgrade Rest Room; Redesign Office Space - Memphis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
559 | 569 | 927 | 710 | 714 | 719 | 722 | 726 | 25470402048 | Re-Skin Exterior, Install Roof, New Windows and Remove Sky Lights W/ Roof Replacement; Redesign Parking Area - Memphis Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 335000 | 335000
560 | 570 | 928 | 711 | 715 | 720 | 723 | 727 | 04470402049 | Retrofit Shop Bays For 10 Yard Trucks - Canadian Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
562 | 572 | 930 | 712 | 716 | 721 | 724 | 728 | 24470402051 | Exterior Renovations - Fort Hancock Sub-Section | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
563 | 573 | 931 | 713 | 717 | 722 | 725 | 729 | 24470402052 | Install Entrance Weather Canopy, Front Door. Add Rolling Doors To Existing Storage Bldg. - Fort Hancock Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 8100 | 8100
564 | 574 | 932 | 714 | 718 | 723 | 726 | 730 | 04470402053 | New Shop Heaters - Darouzett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
565 | 575 | 933 | 715 | 719 | 724 | 727 | 731 | 04470402054 | Abate and Remodel Office Area - Darrouzett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
566 | 576 | 934 | 716 | 720 | 725 | 728 | 732 | 04470402055 | Retrofit Shop Bays For 10 Yard Trucks - Gruver Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
567 | 577 | 935 | 717 | 721 | 726 | 729 | 733 | 04470402056 | Electrical Upgrades - Channing Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
568 | 578 | 936 | 718 | 722 | 727 | 730 | 734 | 04470402057 | New Unit Heaters - Channing Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
569 | 579 | 937 | 719 | 723 | 728 | 731 | 735 | 04470402058 | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows - Channing Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
570 | 580 | 938 | 720 | 724 | 729 | 732 | 736 | 04470402059 | Retrofit Shop Bays For 10 Yard Trucks - Channing Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
571 | 581 | 939 | 721 | 725 | 730 | 733 | 737 | 17470402060 | Install Bathroom/Showers In Shop/Welding Shop - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
573 | 583 | 941 | 722 | 726 | 731 | 734 | 738 | 05470402062 | Re-Skin Renovate Shop - Post Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
574 | 584 | 942 | 723 | 727 | 732 | 735 | 739 | 04470402063 | Enlarge Supervisor Office And Breakroom - Panhandle Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
575 | 585 | 943 | 724 | 728 | 733 | 736 | 740 | 04470402064 | Install Overhead Doors And Openers - Panhandle Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
576 | 586 | 944 | 725 | 729 | 734 | 737 | 741 | 04470402065 | Retrofit Shop Bays For 10 Yard Trucks - Panhandle Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
577 | 587 | 945 | 726 | 730 | 735 | 738 | 742 | 25470402066 | Upgrade Electrical & Lights In Maintenance Barn - Munday Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 30000 | 30000
578 | 588 | 946 | 727 | 731 | 736 | 739 | 743 | 16470402067 | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
579 | 589 | 947 | 728 | 732 | 737 | 740 | 744 | 16470402068 | Replace Exterior Door At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
580 | 590 | 948 | 729 | 733 | 738 | 741 | 745 | 16470402069 | Replace Exterior Windows At Laboratory - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
582 | 592 | 950 | 730 | 734 | 739 | 742 | 746 | 11470402071 | Renovate Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
589 | 599 | 952 | 732 | 735 | 740 | 743 | 747 | 07470402078 | Erect Buildings Over Lifts - Ballinger Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
590 | 600 | 953 | 733 | 736 | 741 | 744 | 748 | 09470402079 | Replace Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 33450 | 33450
591 | 601 | 954 | 734 | 737 | 742 | 745 | 749 | 06470402080 | Replace Windows - Sanderson Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
592 | 602 | 955 | 735 | 738 | 743 | 746 | 750 | 23470402081 | Renovate Facilities - Comanche Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 294000 | 294000
593 | 603 | 956 | 736 | 739 | 744 | 747 | 751 | 17470402082 | Add Lighting And Catwalks To V-Box Area - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
594 | 604 | 957 | 737 | 740 | 745 | 748 | 752 | 17470402083 | Install Above Ground Fuel Tank - Brenham Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
595 | 605 | 958 | 738 | 741 | 746 | 749 | 753 | 17470402084 | New Sidewalk Lab To Parking Lot - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12500 | 12500
598 | 608 | 960 | 740 | 742 | 747 | 750 | 754 | 21470402087 | Reconfigure Two Restrooms & Office - San Isidro Maintenance Office Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
599 | 609 | 961 | 741 | 743 | 748 | 751 | 755 | 15470402088 | Refurbish Shop Building Skin And Roof - Pearsall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 95000 | 95000
600 | 610 | 962 | 742 | 744 | 749 | 752 | 756 | 38470402089 | Austin HQ Campus Repairs - Austin HQ | Capital Construction | Highway Trans. Fund 6 | 5000000 | 5000000
601 | 611 | 963 | 743 | 745 | 750 | 753 | 757 | 09470402090 | New Insulation & Replace Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 52200 | 52200
602 | 612 | 964 | 744 | 746 | 751 | 754 | 758 | 03470402091 | Replace Exterior Windows At Warehouse - Bowie Maintenance - Bowie Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
604 | 614 | 966 | 746 | 747 | 752 | 755 | 759 | 23470402093 | Renovate Facilities - Brady Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 317000 | 317000
605 | 615 | 967 | 747 | 748 | 753 | 756 | 760 | 17470402094 | Reskin Shed - Bryan Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
606 | 616 | 968 | 748 | 749 | 754 | 757 | 761 | 17470402095 | Fence/Gate Work - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
607 | 617 | 969 | 749 | 750 | 755 | 758 | 762 | 17470402096 | Improve Lighting In Yard/Shed - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
608 | 618 | 970 | 750 | 751 | 756 | 759 | 763 | 17470402097 | Install Above Ground Fuel Tank - Madisonville Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
609 | 619 | 971 | 751 | 752 | 757 | 760 | 764 | 17470402098 | Replace Fuel Canopy - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
611 | 621 | 972 | 752 | 753 | 758 | 761 | 765 | 25470402100 | Rewire Office, New Lights; Heaters In Truck Barn - Crowell Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
612 | 622 | 973 | 753 | 754 | 759 | 762 | 766 | 25470402101 | Re-Skin Exterior, Insulate Building, Install Windows, Roof and Lights; Redesign Office Space - Matador Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 325000 | 325000
613 | 623 | 974 | 754 | 755 | 760 | 763 | 767 | 16470402102 | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island - Nueces East | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
614 | 624 | 975 | 755 | 756 | 761 | 764 | 768 | 18470402103 | Electrical Panel Upgrades - Ennis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
618 | 628 | 976 | 756 | 757 | 762 | 765 | 769 | 21470402107 | Renovate Building Into Offices. Renovate Restrooms. - Zapata Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
623 | 633 | 977 | 757 | 758 | 763 | 766 | 770 | 20470402112 | Abate Transit Siding - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
624 | 634 | 978 | 758 | 759 | 764 | 767 | 771 | 20470402113 | Replace Roof, Lighting & Siding - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
625 | 635 | 979 | 759 | 760 | 765 | 768 | 772 | 23470402114 | Renovate Facilities - Coleman Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
630 | 640 | 981 | 760 | 761 | 766 | 769 | 773 | 17470402119 | Replace Flooring (Carpet & Tile) - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
631 | 641 | 982 | 761 | 762 | 767 | 770 | 774 | 17470402120 | Redo Walls In Office - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
632 | 642 | 983 | 762 | 763 | 768 | 771 | 775 | 17470402121 | Reskin MNT Office Building - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
634 | 644 | 984 | 763 | 764 | 769 | 772 | 776 | 25470402123 | Replace Restrooms - Paducah Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
635 | 645 | 985 | 764 | 765 | 770 | 773 | 777 | 25470402124 | Insulate, New Windows And Roof - Silverton Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 275000 | 275000
636 | 646 | 986 | 765 | 766 | 771 | 774 | 778 | 25470402125 | Re-Skin Exterior, Insulate Building,Install Windows and Roof - Silverton Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
638 | 648 | 987 | 766 | 767 | 772 | 775 | 779 | 16470402127 | Replace Exterior Door At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 16000 | 16000
639 | 649 | 988 | 767 | 768 | 773 | 776 | 780 | 18470402128 | Upgrade Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
641 | 651 | 989 | 768 | 769 | 774 | 777 | 781 | 22470402130 | Deactivate Or Remove Mag Locks - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
642 | 652 | 990 | 769 | 770 | 775 | 778 | 782 | 22470402131 | Furnish/Install Exterior Safety Lights - Brackettville | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
643 | 653 | 991 | 770 | 771 | 776 | 779 | 783 | 22470402132 | Renovate Breakroom - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
644 | 654 | 992 | 771 | 772 | 777 | 780 | 784 | 22470402133 | Restroom Renovations (Both Men and Women) - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
645 | 655 | 993 | 772 | 773 | 778 | 781 | 785 | 22470402134 | Retrofit Bay Area Into Conference Room. (17'X28') 14' Ceiling. Tile Flooring, HVAC, Electrical, Communications, Removal Of Exiting Door. - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 55000 | 55000
646 | 656 | 994 | 773 | 774 | 779 | 782 | 786 | 07470402135 | Erect Buildings Over Lifts - Sterling City Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
647 | 657 | 995 | 774 | 775 | 780 | 783 | 787 | 17470402136 | Restroom Remodels - Navasota Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
648 | 658 | 996 | 775 | 776 | 781 | 784 | 788 | 25470402137 | New Partition Walls & Larger Break Room, Upgrade Rest Room, New Windows & Doors, Redesign Office Space - Munday Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
653 | 663 | 997 | 776 | 777 | 782 | 785 | 789 | 05470402142 | Campuswide Electrical Upgrade - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 150000 | 150000
656 | 666 | 998 | 777 | 778 | 783 | 786 | 790 | 05470402145 | New VCT Floor - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 78000 | 78000
660 | 670 | 999 | 778 | 779 | 784 | 787 | 791 | 21470402149 | Add Large Conference Room - Hebbronville Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 252000 | 252000
661 | 671 | 1000 | 779 | 780 | 785 | 788 | 792 | 21470402150 | Restroom Renovation - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
662 | 672 | 1001 | 780 | 781 | 786 | 789 | 793 | 21470402151 | Locker Room With Showers - Hebbronville Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 0 | 0
663 | 673 | 1002 | 781 | 782 | 787 | 790 | 794 | 21470402152 | Phone/Computer Access - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
664 | 674 | 1003 | 782 | 783 | 788 | 791 | 795 | 21470402153 | Ventilation Upgrade - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
665 | 675 | 1004 | 783 | 784 | 789 | 792 | 796 | 09470402154 | Remodel Office - Marlin Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 488000 | 488000
666 | 676 | 1005 | 784 | 785 | 790 | 793 | 797 | 03470402155 | Building Renovation - Electra Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
667 | 677 | 1006 | 785 | 786 | 791 | 794 | 798 | 03470402156 | Reskin And Replace Windows - Electra Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
668 | 678 | 1007 | 786 | 787 | 792 | 795 | 799 | 13470402157 | Paint Metal On Shed - Edna Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
669 | 679 | 1008 | 787 | 788 | 793 | 796 | 800 | 13470402158 | Paint Interior/Exterior Of Mechanic/Warehouse - Jackson Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
672 | 682 | 1009 | 788 | 789 | 794 | 797 | 801 | 17470402161 | Install Above Ground Fuel Tank - Navasota Maintenance Office | Site Work | Highway Trans. Fund 6 | 350000 | 350000
673 | 683 | 1010 | 789 | 790 | 795 | 798 | 802 | 16470402162 | Interior Renovations - Karnes City Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 350000 | 350000
674 | 684 | 1011 | 790 | 791 | 796 | 799 | 803 | 16470402163 | Repair Plumbing System - Karnes City AEM - Karnes City Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
675 | 685 | 1012 | 791 | 792 | 797 | 800 | 804 | 05470402164 | Security System Upgrade - C-Cure - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 40000 | 40000
676 | 686 | 1013 | 792 | 793 | 798 | 801 | 805 | 05470402165 | Add New Wall To Dock With Overhead Door Wk Door - Post RDC | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
678 | 688 | 1015 | 793 | 794 | 799 | 802 | 806 | 10470402167 | Demolish Abandoned Structure - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
679 | 689 | 1016 | 794 | 795 | 800 | 803 | 807 | 10470402168 | Exterior Renovations - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
680 | 690 | 1017 | 795 | 796 | 801 | 804 | 808 | 10470402169 | Replace Carpet In Administration Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
681 | 691 | 1018 | 796 | 797 | 802 | 805 | 809 | 09470402170 | Renovate Maintenance Facility - Mexia Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
682 | 692 | 1019 | 797 | 798 | 803 | 806 | 810 | 08470402171 | Construct Concrete Apron Around The District Headquarters - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
683 | 693 | 1020 | 798 | 799 | 804 | 807 | 811 | 08470402172 | Repair And Replace All Plumbing Fixtures - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 100000 | 100000
685 | 695 | 1022 | 799 | 800 | 805 | 808 | 812 | 17470402174 | New Fuel Canopy - Caldwell Maintenance Office | Site Work | Highway Trans. Fund 6 | 35000 | 35000
686 | 696 | 1023 | 800 | 801 | 806 | 809 | 813 | 17470402175 | Repaving Of Parking Areas - Caldwell Maintenance Office | Site Work | Highway Trans. Fund 6 | 400000 | 400000
689 | 699 | 1024 | 801 | 802 | 807 | 810 | 814 | 02470402178 | Convert Conference Room To EOC - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 153000 | 153000
690 | 700 | 1025 | 802 | 803 | 808 | 811 | 815 | 02470402179 | Electrical Upgrade For The Whole District Headquarters - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
691 | 701 | 1026 | 803 | 804 | 809 | 812 | 816 | 02470402180 | Install Interior Walls At Warehouse - Fort Worth DHQ Ware House Office - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
692 | 702 | 1027 | 804 | 805 | 810 | 813 | 817 | 02470402181 | Install Interiors At Shop - Fort Worth DHQ Locker Rooms - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
693 | 703 | 1028 | 805 | 806 | 811 | 814 | 818 | 02470402182 | Modifications/Upgrade HVAC - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 125000 | 125000
695 | 705 | 1029 | 806 | 807 | 812 | 815 | 819 | 12470402184 | Paint Exterior (5 Buildings) - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 97000 | 97000
696 | 706 | 1030 | 807 | 808 | 813 | 816 | 820 | 12470402185 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 150000 | 150000
697 | 707 | 1031 | 808 | 809 | 814 | 817 | 821 | 12470402186 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 240000 | 240000
698 | 708 | 1032 | 809 | 810 | 815 | 818 | 822 | 05470402187 | Electrical Up-Grade Panel To Switches,Light Plug - Post Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
699 | 709 | 1033 | 810 | 811 | 816 | 819 | 823 | 06470402188 | Repair/Replace Carpet In Tp&D Area - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
700 | 710 | 1034 | 811 | 812 | 817 | 820 | 824 | 06470402189 | Upgrade The District Complex Plumbing System - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 280000 | 280000
701 | 711 | 1035 | 812 | 813 | 818 | 821 | 825 | 15470402190 | Repair Foundation - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
702 | 712 | 1036 | 813 | 814 | 819 | 822 | 826 | 15470402191 | Repair Sidewalks - District Headquarters | Site Work | Highway Trans. Fund 6 | 8000 | 8000
703 | 713 | 1037 | 814 | 815 | 820 | 823 | 827 | 15470402192 | Restroom Renovation/Addition - Seguin RDC | Capital Construction | Highway Trans. Fund 6 | 80000 | 80000
705 | 715 | 1038 | 815 | 816 | 821 | 824 | 828 | 08470402194 | New Carpet - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
707 | 717 | 1039 | 816 | 817 | 822 | 825 | 829 | 25470402196 | Re-Skin Exterior, Insulate Building, Install Windows and Roof, Redesign Office Space - Wellington Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 325000 | 325000
708 | 718 | 1040 | 817 | 818 | 823 | 826 | 830 | 02470402197 | Lab Upgrades - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 558500 | 558500
710 | 720 | 1041 | 818 | 819 | 824 | 827 | 831 | 12470402199 | Renovate 3 Buildings Into One - Houston South Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 1200000 | 1200000
711 | 721 | 1042 | 819 | 820 | 825 | 828 | 832 | 12470402200 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 29000 | 29000
712 | 722 | 1043 | 820 | 821 | 826 | 829 | 833 | 12470402201 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 485000 | 485000
713 | 723 | 1044 | 821 | 822 | 827 | 830 | 834 | 12470402202 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
715 | 724 | 1045 | 822 | 823 | 828 | 831 | 835 | 06470402204 | Replace/Repair Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
718 | 726 | 1047 | 823 | 824 | 829 | 832 | 836 | 15470402207 | Restroom Renovation/Addition - Seguin Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
719 | 727 | 1048 | 824 | 825 | 830 | 833 | 837 | 04470402208 | Abate Inside,Replace Windows And Replace Roof - Canyon Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
720 | 728 | 1049 | 825 | 826 | 831 | 834 | 838 | 05470402209 | Electrical Up-Grade Panel To Switches,Light Plug - Bovina Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
723 | 731 | 1051 | 826 | 827 | 832 | 835 | 839 | 05470402212 | Electrical Up-Grade Panel To Switches,Light Plug - Brownfield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
726 | 734 | 1053 | 827 | 828 | 833 | 836 | 840 | 05470402215 | Electrical Up-Grade Panel To Switches,Light Plug - Ralls Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
729 | 737 | 1055 | 828 | 829 | 834 | 837 | 841 | 15470402218 | Carpet & Paint - Tilden Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
730 | 738 | 1056 | 829 | 830 | 835 | 838 | 842 | 15470402219 | Relocate Radio Tower - Tilden Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 0
731 | 739 | 1057 | 830 | 831 | 836 | 839 | 843 | 15470402220 | Upgrade Restrooms - Tilden Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
732 | 740 | 1058 | 831 | 832 | 837 | 840 | 844 | 38470402221 | Renovate Interior Office Space, Include Abatement, New Lighting, New Windows, New Duct Work - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 1000000 | 1000000
733 | 741 | 1059 | 832 | 833 | 838 | 841 | 845 | 10470402222 | Elevated Water Storage - North Tyler Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
735 | 743 | 1061 | 834 | 834 | 839 | 842 | 846 | 13470402224 | Paint Interior Structure Of Equip Shed - Austin Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
736 | 744 | 1062 | 835 | 835 | 840 | 843 | 847 | 13470402225 | Rehab. Of Mechanic Area (Front Wall W/ Door) - Austin Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
737 | 745 | 1063 | 836 | 836 | 841 | 844 | 848 | 13470402226 | Level And Paint Interior Of Office Building - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
739 | 747 | 1064 | 837 | 837 | 842 | 845 | 849 | 13470402228 | Level Building (Maintenance Bldg) - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
740 | 748 | 1065 | 838 | 838 | 843 | 846 | 850 | 13470402229 | Paint Office & Warehouse Exterior - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
741 | 749 | 1066 | 839 | 839 | 844 | 847 | 851 | 13470402230 | Paint Exterior Structure Of Fuel Canopy - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
743 | 751 | 1067 | 840 | 840 | 845 | 848 | 852 | 08470402232 | Paint Exterior - Big Spring Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
745 | 753 | 1068 | 841 | 841 | 846 | 849 | 853 | 20470402234 | Install Rotary Lift & 2 Ton Overhead Crane And Trolley - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 13000 | 13000
748 | 756 | 1069 | 842 | 842 | 847 | 850 | 854 | 20470402237 | Interior Remodel - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 6700 | 6700
749 | 757 | 1070 | 843 | 843 | 848 | 851 | 855 | 20470402238 | Interior Remodel - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 39000 | 39000
750 | 758 | 1071 | 844 | 844 | 849 | 852 | 856 | 20470402239 | Repair ADA Ramps - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
751 | 759 | 1072 | 845 | 845 | 850 | 853 | 857 | 20470402240 | Replace 25 Infra-Red Heaters - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
753 | 761 | 1073 | 846 | 846 | 851 | 854 | 858 | 20470402242 | Replace Fuel Dispensers Districtwide - Districtwide | Site Work | Highway Trans. Fund 6 | 150000 | 150000
754 | 762 | 1074 | 847 | 847 | 852 | 855 | 859 | 25470402243 | Replace Windows & Locks - Dickens Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
755 | 763 | 1075 | 848 | 848 | 853 | 856 | 860 | 12470402244 | Renovate Interior - La Marque Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 300000 | 300000
756 | 764 | 1076 | 849 | 849 | 854 | 857 | 861 | 12470402245 | Replace Siding (8 Buildings) - La Marque Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 640000 | 640000
758 | 766 | 1077 | 850 | 850 | 855 | 858 | 862 | 03470402247 | Building Renovations - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 112000 | 112000
759 | 767 | 1078 | 851 | 851 | 856 | 859 | 863 | 03470402248 | Foundation And Cosmetic Repairs - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 160000 | 160000
760 | 768 | 1079 | 852 | 852 | 857 | 860 | 864 | 13470402249 | Close Open Bay And Add To Sign Room - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
N/A | N/A | 1080 | 853 | 853 | 858 | 861 | 865 | 08470402250 | Replace 5 Overhead Roll Up Doors And Paint 3 - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
762 | 770 | 1081 | 854 | 854 | 859 | 862 | 866 | 13470402251 | Replace Oh Doors On Shed - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
763 | 771 | 1082 | 855 | 855 | 860 | 863 | 867 | 13470402252 | Bird Proof Underside Of Roof-Purlins - Matagorda Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 6000 | 6000
764 | 772 | 1083 | 856 | 856 | 861 | 864 | 868 | 13470402253 | Construct Elevated Platform For Wash Rack - Matagorda Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
765 | 773 | 1084 | 857 | 857 | 862 | 865 | 869 | 19470402254 | Renovation Of Warehouse - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 515000 | 515000
766 | 774 | 1085 | 858 | 858 | 863 | 866 | 870 | 19470402255 | Remodel Inside Of Building - Texarkana Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
767 | 775 | 1086 | 859 | 859 | 864 | 867 | 871 | 19470402256 | Replace Overhead Doors - Texarkana Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 111000 | 111000
769 | 777 | 1087 | 860 | 860 | 865 | 868 | 872 | 17470402258 | Remove Fuel Awning/Install New Awning For Parking - Brenham Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 250000 | 250000
770 | 778 | 1088 | 861 | 861 | 866 | 869 | 873 | 16470402259 | Repair Structure At Administration - Corpus Christi DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
771 | 779 | 1089 | 862 | 862 | 867 | 870 | 874 | 16470402260 | Replace Flooring At Administration - Corpus Christi DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
773 | 781 | 1090 | 863 | 863 | 868 | 871 | 875 | 16470402262 | Replace\New Exterior Walls At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
774 | 782 | 1091 | 864 | 864 | 869 | 872 | 876 | 16470402263 | Remodel Inside Office (Lights, Ceiling, Floor, Paint) - Karnes Co. | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
777 | 785 | 1093 | 866 | 865 | 870 | 873 | 877 | 05470402266 | Electrical Up-Grade Panel To Switches,Light Plug - Plains Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
779 | 787 | 1095 | 867 | 866 | 871 | 874 | 878 | 05470402268 | Electrical Up-Grade Panel To Switches,Light Plug - Seminole Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
780 | 788 | 1096 | 868 | 867 | 872 | 875 | 879 | 05470402269 | New VCT Floor - Seminole Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
782 | 790 | 1098 | 869 | 868 | 873 | 876 | 880 | 11470402271 | Paint Entire Facility Interior And Exterior - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
783 | 791 | 1099 | 870 | 869 | 874 | 877 | 881 | 11470402272 | Replace Fuel Dispensers - Crockett Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
785 | 793 | 1100 | 871 | 870 | 875 | 878 | 882 | 11470402274 | Upgrade Exterior Lighting - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
786 | 794 | 1101 | 872 | 871 | 876 | 879 | 883 | 11470402275 | Upgrade Interior Lighting - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
788 | 796 | 1102 | 873 | 872 | 877 | 880 | 884 | 06470402277 | Paint Exterior And Interior - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
789 | 797 | 1103 | 874 | 873 | 878 | 881 | 885 | 06470402278 | Reconfigure Bay For Break Room Locker Room. New Kitchenette Lockers Flooring Walls Plumbing Electrical - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
790 | 798 | 1104 | 875 | 874 | 879 | 882 | 886 | 06470402279 | Remove & Replace Windows In Main Office - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
791 | 799 | 1105 | 876 | 875 | 880 | 883 | 887 | 06470402280 | Upgrade Electrical Wiring, Lights And Breakers - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 4000 | 4000
793 | 801 | 1106 | 877 | 876 | 881 | 884 | 888 | 21470402282 | Upgrade Conference Rooms - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 51000 | 51000
794 | 802 | 1107 | 878 | 877 | 882 | 885 | 889 | 21470402283 | Repair Plumbing Problems - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 20000 | 20000
795 | 803 | 1108 | 879 | 878 | 883 | 886 | 890 | 21470402284 | Building Renovation - Falfurrias Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 163300 | 163300
796 | 804 | 1109 | 880 | 879 | 884 | 887 | 891 | 21470402285 | Upgrade Mechanic Shop - Falfurrias Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 190000 | 190000
797 | 805 | 1110 | 881 | 880 | 885 | 888 | 892 | 09470402286 | Retrofit Truck Bays To Conference Rooms and Meeting Space - Meridian Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
799 | 807 | 1112 | 882 | 881 | 886 | 889 | 893 | 03470402288 | Retrofit Warehouse Space To Large Meeting Room - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 28500 | 28500
800 | 808 | 1113 | 883 | 882 | 887 | 890 | 894 | 03470402289 | Building Remodel - Nocona Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
801 | 809 | 1114 | 884 | 883 | 888 | 891 | 895 | 13470402290 | Interior Renovation (Floors & Walls) - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
802 | 810 | 1115 | 885 | 884 | 889 | 892 | 896 | 13470402291 | Paint Exterior Structure Of Canopy, Mechanci Shop, & Stock Room - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
803 | 811 | 1116 | 886 | 885 | 890 | 893 | 897 | 13470402292 | Paint Interior Structure Of Equip Shed - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
804 | 812 | 1117 | 887 | 886 | 891 | 894 | 898 | 13470402293 | Replace Shifting Concrete Pad Under Pad Mount Electrical Transformer - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
809 | 817 | 1119 | 888 | 887 | 892 | 895 | 899 | 23470402298 | Renovate Lab - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 712000 | 712000
810 | 818 | 1120 | 889 | 888 | 893 | 896 | 900 | 18470402300 | Electrical - Additional Service - Waxahachie Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
812 | 820 | 1121 | 890 | 889 | 894 | 897 | 901 | 12470402302 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 120000 | 120000
813 | 821 | 1122 | 891 | 890 | 895 | 898 | 902 | 22470402303 | Exterior Warehouse Painting - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
814 | 822 | 1123 | 892 | 891 | 896 | 899 | 903 | 05470402304 | Electrical Up-Grade Panel To Switches,Light Plug - Levelland Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
816 | 824 | 1125 | 893 | 892 | 897 | 900 | 904 | 05470402306 | Electrical Up-Grade Panel To Switches,Light Plug - SE Maint. Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
817 | 825 | 63 | 369 | 401 | 399 | 398 | 905 | 11470402307 | Foundation Repairs - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 0
819 | 827 | 1126 | 894 | 893 | 898 | 901 | 906 | 11470402309 | Repair Dist Shop Parking Lot And Stripe Existing Lots At Dist HQ - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
820 | 828 | 1127 | 895 | 894 | 899 | 902 | 907 | 11470402310 | Replace Fuel Awning - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21000 | 21000
823 | 831 | 1129 | 896 | 895 | 900 | 903 | 908 | 04470402313 | Abate Windows And Paint Exterior Of Shop - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
824 | 832 | 1130 | 897 | 896 | 901 | 904 | 909 | 19470402314 | Major Renovation - Mt Pleasant Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 767000 | 767000
825 | 833 | 1131 | 898 | 897 | 902 | 905 | 910 | 19470402315 | Remodel Inside Of Building - Mt Pleasant Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
826 | 834 | 1132 | 899 | 898 | 903 | 906 | 911 | 19470402316 | Replace Overhead Doors - Mt Pleasant Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 128300 | 128300
829 | 837 | 1134 | 900 | 899 | 904 | 907 | 912 | 18470402319 | Renovate Interior - Rockwall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
831 | 839 | 1135 | 901 | 900 | 905 | 908 | 913 | 22470402321 | Replace Two Overhead Doors - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
832 | 840 | 1136 | 902 | 901 | 906 | 909 | 914 | 22470402322 | Restroom Renovation - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
834 | 842 | 1138 | 903 | 902 | 907 | 910 | 915 | 05470402324 | Electrical Up-Grade Panel To Switches,Light Plug - FloydADA Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
835 | 843 | 1139 | 904 | 903 | 908 | 911 | 916 | 05470402325 | Electrical Up-Grade Panel To Switches,Light Plug - Lamesa Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
836 | 844 | 1140 | 905 | 904 | 909 | 912 | 917 | 05470402326 | New VCT Floor - Lamesa Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
838 | 846 | 1142 | 906 | 905 | 910 | 913 | 918 | 11470402328 | Paint Entire Facility Interior And Exterior - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
840 | 848 | 1143 | 907 | 906 | 911 | 914 | 919 | 11470402330 | Renovate Interior - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
846 | 854 | 1144 | 908 | 907 | 912 | 915 | 920 | 07470402336 | Modifications/Upgrade Electrical - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
847 | 855 | 1145 | 909 | 908 | 913 | 916 | 921 | 07470402337 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500
849 | 857 | 1146 | 910 | 909 | 914 | 917 | 922 | 12470402340 | Renovate Interior/Exterior (20K Sf Concrete Tilt Wall Aquired Building) - Houston Northwest | Capital Construction | Highway Trans. Fund 6 | 2000000 | 2000000
850 | 858 | 1147 | 911 | 910 | 915 | 918 | 923 | 12470402341 | Renovation And Upgrade To AEM - West Harris Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 2000000 | 2000000
851 | 859 | 1148 | 912 | 911 | 916 | 919 | 924 | 05470402342 | New VCT Floor - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
855 | 863 | 1151 | 913 | 912 | 917 | 920 | 925 | 04470402346 | Retrofit Shop Bays For 10 Yard Trucks - Vega Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
856 | 864 | 1152 | 914 | 913 | 918 | 921 | 926 | 04470402347 | Upgrade Current Welding Shop - Vega Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
857 | 865 | 1153 | 915 | 914 | 919 | 922 | 927 | 19470402348 | Remodel Inside Of Building Paint Floor And Ceiling - New Boston Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
858 | 866 | 1154 | 916 | 915 | 920 | 923 | 928 | 19470402349 | Replace Overhead Doors - New Boston Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 99400 | 99400
859 | 867 | 1155 | 917 | 916 | 921 | 924 | 929 | 15470402350 | Paint, Carpet Replacement - Devine Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
860 | 868 | 1156 | 918 | 917 | 922 | 925 | 930 | 15470402351 | Restroom Upgrades - Devine Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
861 | 869 | 1157 | 919 | 918 | 923 | 926 | 931 | 13470402352 | Replace All Exterior Roof Facial & Renovate All Exterior Entrances - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
862 | 870 | 1158 | 920 | 919 | 924 | 927 | 932 | 16470402353 | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
863 | 871 | 1159 | 921 | 920 | 925 | 928 | 933 | 16470402354 | Paint Interior Walls At Maintenance - Kingsville Maintenance - Kingsville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
866 | 874 | 1160 | 922 | 921 | 926 | 929 | 934 | 05470402357 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
867 | 875 | 1161 | 923 | 922 | 927 | 930 | 935 | 05470402358 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
870 | 878 | 1163 | 924 | 923 | 928 | 931 | 936 | 04470402361 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 0 | 0
872 | 880 | 1164 | 925 | 924 | 929 | 932 | 937 | 04470402363 | Renovation Of Building Exterior | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
873 | 881 | 1165 | 926 | 925 | 930 | 933 | 938 | 04470402364 | Restroom Abatement And Remodel | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
874 | 882 | 1166 | 927 | 926 | 931 | 934 | 939 | 04470402365 | Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
875 | 883 | 1167 | 928 | 927 | 932 | 935 | 940 | 04470402366 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
876 | 884 | 1168 | 929 | 928 | 933 | 936 | 941 | 14470402367 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
878 | 886 | 1169 | 930 | 929 | 934 | 937 | 942 | 20470402369 | Paint Office Exterior | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
879 | 887 | 1170 | 931 | 930 | 935 | 938 | 943 | 20470402370 | Replace Electrical Panels And Upgrade Electrical Wiring. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
880 | 888 | 1171 | 932 | 931 | 936 | 939 | 944 | 24470402371 | Additional Outside LED Lighting For Houses. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
881 | 889 | 1172 | 933 | 932 | 937 | 940 | 945 | 24470402372 | Interior Renovation; Electrical, HVAC, Walls Finish, Framing, Floors And Kitchen | Capital Repairs | Highway Trans. Fund 6 | 36000 | 36000
884 | 892 | 1173 | 934 | 933 | 938 | 941 | 946 | 05470402375 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
885 | 893 | 1174 | 935 | 934 | 939 | 942 | 947 | 05470402376 | New VCT Floor | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
886 | 894 | 1175 | 936 | 935 | 940 | 943 | 948 | 07470402377 | Paint Interior Of Facility | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
890 | 898 | 1177 | 937 | 936 | 941 | 944 | 949 | 04470402381 | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
891 | 899 | 1178 | 938 | 937 | 942 | 945 | 950 | 04470402382 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
892 | 900 | 1179 | 939 | 938 | 943 | 946 | 951 | 08470402383 | Convert Old Shop Into Breakroom | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
893 | 901 | 1180 | 940 | 939 | 944 | 947 | 952 | 23470402384 | Renovate Office | Capital Construction | Highway Trans. Fund 6 | 311000 | 311000
894 | 902 | 1181 | 941 | 940 | 945 | 948 | 953 | 17470402385 | Install Above Ground Fuel Tank | Site Work | Highway Trans. Fund 6 | 350000 | 350000
896 | 904 | 1182 | 942 | 941 | 946 | 949 | 954 | 17470402387 | Repair Foundation/Porch/Walls | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
898 | 906 | 1183 | 943 | 942 | 947 | 950 | 955 | 17470402389 | Replace Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
899 | 907 | 1184 | 944 | 943 | 948 | 951 | 956 | 17470402390 | Replace Wiring In Building | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
901 | 909 | 1185 | 945 | 944 | 949 | 952 | 957 | 25470402392 | Replace Floor Tiles; Upgrade Rest Rooms, Redesign Office Space | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
902 | 910 | 1186 | 946 | 945 | 950 | 953 | 958 | 16470402393 | Replace Electrical Panels At Right Of Way - Corpus Christi District Headquarters And Area Engineer And Maintenance Special Jobs | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
906 | 914 | 1188 | 947 | 946 | 951 | 954 | 959 | 06470402397 | Replace Windows | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
907 | 915 | 1189 | 948 | 947 | 952 | 955 | 960 | 21470402398 | New 4K Gallon Fuel Tanks/Replace Fuel Pumps | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
908 | 916 | 1190 | 949 | 948 | 953 | 956 | 961 | 21470402399 | New Heavy Equipment Overhead Doors | Capital Construction | Highway Trans. Fund 6 | 57000 | 57000
909 | 917 | 1191 | 950 | 949 | 954 | 957 | 962 | 21470402400 | New Heavy Equipment Pull Through Stalls | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500
910 | 918 | 1192 | 951 | 950 | 955 | 958 | 963 | 21470402401 | Renovate Building | Capital Construction | Highway Trans. Fund 6 | 112000 | 112000
911 | 919 | 1193 | 952 | 951 | 956 | 959 | 964 | 13470402402 | Interior Renovation (Floors & Walls) | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
914 | 922 | 1195 | 953 | 952 | 957 | 960 | 965 | 24470402405 | Remodel Bay For Maintenance Training And Breakroom, Add One Additional Office In Bay. | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
915 | 923 | 1196 | 954 | 953 | 958 | 961 | 966 | 12470402406 | Renovate Restrooms (Locker Rooms) | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
916 | 924 | 1197 | 955 | 954 | 959 | 962 | 967 | 12470402407 | Replace Windows | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
917 | 925 | 1198 | 956 | 955 | 960 | 963 | 968 | 21470402408 | Upgrade Mechanic Shop | Capital Construction | Highway Trans. Fund 6 | 0 | 0
921 | 929 | 1200 | 957 | 956 | 961 | 964 | 969 | 17470402412 | Install Above Ground Fuel Tank | Capital Repairs | Highway Trans. Fund 6 | 350000 | 350000
925 | 933 | 1201 | 958 | 957 | 962 | 965 | 970 | 21470402416 | Upgrade Ballasts | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
926 | 934 | 1202 | 959 | 958 | 963 | 966 | 971 | 24470402417 | Convert Bay Into A Break Room | Capital Repairs | Highway Trans. Fund 6 | 19500 | 19500
927 | 935 | 1203 | 960 | 959 | 964 | 967 | 972 | 24470402418 | Extend Office Space Along Same Roof Line To The South 16 Feet | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
928 | 936 | 1204 | 961 | 960 | 965 | 968 | 973 | 19470402419 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 32200 | 32200
929 | 937 | 1205 | 962 | 961 | 966 | 969 | 974 | 19470402420 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
931 | 939 | 1207 | 963 | 962 | 967 | 970 | 975 | 17470402422 | Remove Undergrnd/Install Above Grnd Fuel Tanks | Site Work | Highway Trans. Fund 6 | 350000 | 350000
932 | 940 | 1208 | 964 | 963 | 968 | 971 | 976 | 21470402423 | Building Renovation | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
933 | 941 | 1209 | 965 | 964 | 969 | 972 | 977 | 21470402424 | Replace Overhead Doors | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
934 | 942 | 1210 | 966 | 965 | 970 | 973 | 978 | 04470402425 | Electrical Upgrades | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
936 | 944 | 1211 | 967 | 966 | 971 | 974 | 979 | 04470402427 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
937 | 945 | 1212 | 968 | 967 | 972 | 975 | 980 | 15470402428 | Paint, Carpet Replacement | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
938 | 946 | 1213 | 969 | 968 | 973 | 976 | 981 | 15470402429 | Restroom Upgrades | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
939 | 947 | 1214 | 970 | 969 | 974 | 977 | 982 | 15470402430 | Window Replacement | Capital Construction | Highway Trans. Fund 6 | 180000 | 180000
940 | 948 | 1215 | 971 | 970 | 975 | 978 | 983 | 15470402431 | Asbestos Abatement, Carpet & Paint | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
941 | 949 | 1216 | 972 | 971 | 976 | 979 | 984 | 15470402432 | Restroom Upgrade | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
942 | 950 | 1217 | 973 | 972 | 977 | 980 | 985 | 12470402433 | Locker Room Upgrades/Addition Of Showers | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
944 | 952 | 1218 | 974 | 973 | 978 | 981 | 986 | 15470402435 | Replace Irrigation System | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
948 | 956 | 1219 | 975 | 974 | 979 | 982 | 987 | 08470402439 | Repair Structural Damage to Columns | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
950 | 958 | 1220 | 976 | 975 | 980 | 983 | 988 | 08470402441 | Upgrade Wash Bay | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
951 | 959 | 1221 | 977 | 976 | 981 | 984 | 989 | 24470402442 | Additional Outside LED Lighting For Houses. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
953 | 961 | 1222 | 978 | 977 | 982 | 985 | 990 | 24470402444 | Renovate Stock Area; Insulate Metal Walls, Ceiling | Capital Repairs | Highway Trans. Fund 6 | 11500 | 11500
954 | 962 | 1223 | 979 | 978 | 983 | 986 | 991 | 07470402445 | Construct Buildings Over Lifts | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
956 | 964 | 1224 | 980 | 979 | 984 | 987 | 992 | 14470402447 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 167200 | 167200
957 | 965 | 1225 | 981 | 980 | 985 | 988 | 993 | 17470402448 | Replace Fuel Canopy - Navasota MNT | Site Work | Highway Trans. Fund 6 | 35000 | 35000
959 | 967 | 1226 | 982 | 981 | 986 | 989 | 994 | 16470402450 | Replace Flooring In Office Building And Paint Walls | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
960 | 968 | 1227 | 983 | 982 | 987 | 990 | 995 | 19470402451 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 82600 | 82600
961 | 969 | 1228 | 984 | 983 | 988 | 991 | 996 | 19470402452 | Remodel Inside Of Building Including Bathrooms | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
964 | 972 | 1229 | 985 | 984 | 989 | 992 | 997 | 16470402455 | Replace Flooring In Office Building And Paint Walls | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
965 | 973 | 1230 | 986 | 985 | 990 | 993 | 998 | 16470402456 | Paint Interior Walls At Area Engineer And Maintenance - Sinton AEM | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
968 | 976 | 1231 | 987 | 986 | 991 | 994 | 999 | 16470402459 | Replace Existing Floor Tile And Paint Office | Capital Repairs | Highway Trans. Fund 6 | 17500 | 17500
969 | 977 | 1232 | 988 | 987 | 992 | 995 | 1000 | 16470402460 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
970 | 978 | 1233 | 989 | 988 | 993 | 996 | 1001 | 16470402461 | Install Exteriors At Maintenance - Rockport MNT | Capital Repairs | Highway Trans. Fund 6 | 28000 | 28000
971 | 979 | 1234 | 990 | 989 | 994 | 997 | 1002 | 16470402462 | Repair Exterior Windows At Maintenance - Rockport MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
973 | 981 | 1235 | 991 | 990 | 995 | 998 | 1003 | 12470402464 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
974 | 982 | 1236 | 992 | 991 | 996 | 999 | 1004 | 12470402465 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 320000 | 320000
975 | 983 | 1237 | 993 | 992 | 997 | 1000 | 1005 | 22470402466 | Storage Shed Asbestos Testing & Abatement | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
976 | 984 | 1238 | 994 | 993 | 998 | 1001 | 1006 | 22470402467 | Storage Shed Repairs | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
977 | 985 | 1239 | 995 | 994 | 999 | 1002 | 1007 | 11470402468 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
985 | 993 | 1240 | 996 | 995 | 1000 | 1003 | 1008 | 11470402476 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
986 | 994 | 1241 | 997 | 996 | 1001 | 1004 | 1009 | 11470402477 | Replace Fuel Dispensers | Site Work | Highway Trans. Fund 6 | 30000 | 30000
988 | 996 | 1242 | 998 | 997 | 1002 | 1005 | 1010 | 11470402479 | Upgrade Exterior Lighting | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
991 | 999 | 1243 | 999 | 998 | 1003 | 1006 | 1011 | 11470402482 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
992 | 1000 | 1244 | 1000 | 999 | 1004 | 1007 | 1012 | 11470402483 | Replace Fuel Dispensers | Site Work | Highway Trans. Fund 6 | 30000 | 30000
999 | 1007 | 1247 | 1003 | 1000 | 1005 | 1008 | 1013 | 21470402490 | Exterior Facade Repairs To Warehouse, Shop & Teleconference Training Center | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1000 | 1008 | 1248 | 1004 | 1001 | 1006 | 1009 | 1014 | 21470402491 | Renovate Shop | Capital Construction | Highway Trans. Fund 6 | 117000 | 117000
1001 | 1009 | 1249 | 1005 | 1002 | 1007 | 1010 | 1015 | 21470402492 | Install Vehicle Exhaust System. Replace Existing Ceiling Fans. | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1002 | 1010 | 1250 | 1006 | 1003 | 1008 | 1011 | 1016 | 21470402493 | Replace All Windows/Frames. | Capital Repairs | Highway Trans. Fund 6 | 85000 | 85000
1004 | 1012 | 1251 | 1007 | 1004 | 1009 | 1012 | 1017 | 15470402495 | Restroom Upgrade | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1005 | 1013 | 1252 | 1008 | 1005 | 1010 | 1013 | 1018 | 04470402496 | Electrical Upgrades | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
1006 | 1014 | 1253 | 1009 | 1006 | 1011 | 1014 | 1019 | 04470402497 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
1007 | 1015 | 1254 | 1010 | 1007 | 1012 | 1015 | 1020 | 04470402498 | Shop Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1008 | 1016 | 1255 | 1011 | 1008 | 1013 | 1016 | 1021 | 19470402499 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
1009 | 1017 | 1256 | 1012 | 1009 | 1014 | 1017 | 1022 | 19470402500 | Replace Overhead Doors | Capital Construction | Highway Trans. Fund 6 | 113000 | 113000
1012 | 1020 | 1257 | 1013 | 1010 | 1015 | 1018 | 1023 | 02470402503 | Remodel Old Sign Shop Into A Fitness Center | Capital Construction | Highway Trans. Fund 6 | 831000 | 831000
1013 | 1021 | 1258 | 1014 | 1011 | 1016 | 1019 | 1024 | 06470402504 | Paint Exterior Walls | Capital Repairs | Highway Trans. Fund 6 | 21000 | 21000
1014 | 1022 | 1259 | 1015 | 1012 | 1017 | 1020 | 1025 | 13470402505 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1015 | 1023 | 1260 | 1016 | 1013 | 1018 | 1021 | 1026 | 04470402506 | Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1016 | 1024 | 1261 | 1017 | 1014 | 1019 | 1022 | 1027 | 04470402507 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
1017 | 1025 | 1262 | 1018 | 1015 | 1020 | 1023 | 1028 | 19470402508 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 83000 | 83000
1018 | 1026 | 1263 | 1019 | 1016 | 1021 | 1024 | 1029 | 19470402509 | Replace VCT Flooring And Paint Interior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1019 | 1027 | 1264 | 1020 | 1017 | 1022 | 1025 | 1030 | 18470402510 | Modular Furniture Installation | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1023 | 1031 | 1266 | 1021 | 1018 | 1023 | 1026 | 1031 | 22470402514 | Relocate Generator From Freer | Safety/Security | Highway Trans. Fund 6 | 25000 | 25000
1024 | 1032 | 1267 | 1022 | 1019 | 1024 | 1027 | 1032 | 22470402515 | Men's Restroom Renovation | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1025 | 1033 | 1268 | 1023 | 1020 | 1025 | 1028 | 1033 | 05470402516 | Repaint Exterior, Old Faded Peeling | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1026 | 1034 | 1269 | 1024 | 1021 | 1026 | 1029 | 1034 | 05470402517 | Repaint Exterior, Old Faded Peeling | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1027 | 1035 | 1270 | 1025 | 1022 | 1027 | 1030 | 1035 | 13470402518 | Paint Interior Structure Of Equip Shed | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1028 | 1036 | 1271 | 1026 | 1023 | 1028 | 1031 | 1036 | 22470402519 | Men's Restroom Renovation | Capital Repairs | Highway Trans. Fund 6 | 24000 | 24000
1029 | 1037 | 1272 | 1027 | 1024 | 1029 | 1032 | 1037 | 22470402520 | Replace Breakroom Flooring | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1030 | 1038 | 1273 | 1028 | 1025 | 1030 | 1033 | 1038 | 20470402521 | Replace AV Electrical Circuit | Capital Repairs | Highway Trans. Fund 6 | 1500 | 0
1034 | 1042 | 1274 | 1029 | 1026 | 1031 | 1034 | 1039 | 20470402525 | Remodel Rest Rooms & Wall Repair | Capital Repairs | Highway Trans. Fund 6 | 54000 | 54000
1036 | 1044 | 1275 | 1030 | 1027 | 1032 | 1035 | 1040 | 20470402527 | Replace Siding And Roofing | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
1037 | 1045 | 1276 | 1031 | 1028 | 1033 | 1036 | 1041 | 20470402528 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1038 | 1046 | 1277 | 1032 | 1029 | 1034 | 1037 | 1042 | 12470402529 | New Carpet/VCT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1039 | 1047 | 1278 | 1033 | 1030 | 1035 | 1038 | 1043 | 12470402530 | Paint Exterior | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1040 | 1048 | 1279 | 1034 | 1031 | 1036 | 1039 | 1044 | 12470402531 | Reconfigure Cubicles (Space Management) | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1042 | 1050 | 1280 | 1035 | 1032 | 1037 | 1040 | 1045 | 22470402533 | Administration: Nail Down Spanish Tiles; Remove/Replace Broken Spanish Tiles | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1043 | 1051 | 1281 | 1036 | 1033 | 1038 | 1041 | 1046 | 22470402534 | Remove Worn Out Existing VCT Flooring & Replace Ceramic Tile | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1044 | 1052 | 1282 | 1037 | 1034 | 1039 | 1042 | 1047 | 22470402535 | Retrofit To Video Teleconference Room | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1045 | 1053 | 1283 | 1038 | 1035 | 1040 | 1043 | 1048 | 22470402536 | Bat Issues (Clean Up And Resolution) | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
1046 | 1054 | 1284 | 1039 | 1036 | 1041 | 1044 | 1049 | 22470402537 | Minor Restrooms Renovation | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1047 | 1055 | 1285 | 1040 | 1037 | 1042 | 1045 | 1050 | 22470402538 | Exterior Painting | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1048 | 1056 | 1286 | 1041 | 1038 | 1043 | 1046 | 1051 | 22470402539 | Carpet Replacement | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1049 | 1057 | 1287 | 1042 | 1039 | 1044 | 1047 | 1052 | 22470402540 | Modular Unit (12) | Capital Repairs | Highway Trans. Fund 6 | 96000 | 96000
1050 | 1058 | 1288 | 1043 | 1040 | 1045 | 1048 | 1053 | 15470402541 | Proportionate Share Of 1St Floor Renovation | Capital Construction | Highway Trans. Fund 6 | 1000000 | 1000000
1051 | 1059 | 1289 | 1044 | 1041 | 1046 | 1049 | 1054 | 10470402542 | Demo Warehouse Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1052 | 1060 | 1290 | 1045 | 1042 | 1047 | 1050 | 1055 | 10470402543 | Install New Elevator | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
1054 | 1062 | 1292 | 1046 | 1043 | 1048 | 1051 | 1056 | 13470402545 | Paint Interior Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1055 | 1063 | 1293 | 1047 | 1044 | 1049 | 1052 | 1057 | 13470402546 | Sealing Exterior Block Walls | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1056 | 1064 | 1294 | 1048 | 1045 | 1050 | 1053 | 1058 | 13470402547 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1057 | 1065 | 1295 | 1049 | 1046 | 1051 | 1054 | 1059 | 13470402548 | Replace Wash Rack Canopy | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1058 | 1066 | 1296 | 1050 | 1047 | 1052 | 1055 | 1060 | 16470402549 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1059 | 1067 | 1297 | 1051 | 1048 | 1053 | 1056 | 1061 | 16470402550 | Paint Exterior Walls At Shop - Corpus Christi DHQ | Capital Repairs | Highway Trans. Fund 6 | 27500 | 27500
1060 | 1068 | 1298 | 1052 | 1049 | 1054 | 1057 | 1062 | 24470402551 | Install LED Lighting In Wall Packs | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1061 | 1069 | 1299 | 1053 | 1050 | 1055 | 1058 | 1063 | 24470402552 | Install Vestabule / Canopy Near Breakroom | Capital Repairs | Highway Trans. Fund 6 | 36000 | 36000
1062 | 1070 | 1300 | 1054 | 1051 | 1056 | 1059 | 1064 | 24470402553 | Install Vestibule Front And Rear, Lobby Entries | Capital Repairs | Highway Trans. Fund 6 | 48000 | 48000
1065 | 1073 | 1301 | 1055 | 1052 | 1057 | 1060 | 1065 | 05470402556 | New VCT Floor | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1066 | 1074 | 1302 | 1056 | 1053 | 1058 | 1061 | 1066 | 15470402557 | Interior LED Lighting Upgrade | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
1067 | 1075 | 1303 | 1057 | 1054 | 1059 | 1062 | 1067 | 15470402558 | Raise Truck Wash Canopy | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1068 | 1076 | 1304 | 1058 | 1055 | 1060 | 1063 | 1068 | 15470402559 | Retrofit Equipment Bay For Enclosed Climate Control LED Storage | Capital Repairs | Highway Trans. Fund 6 | 2000 | 2000
1069 | 1077 | 1305 | 1059 | 1056 | 1061 | 1064 | 1069 | 09470402560 | Upgrade Shop And Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1071 | 1079 | 1307 | 1061 | 1057 | 1062 | 1065 | 1070 | 13470402562 | Level Building (Area Engineers Bldg) | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1073 | 1081 | 1308 | 1062 | 1058 | 1063 | 1066 | 1071 | 17470402564 | Redo HVAC/Vent/Pipes | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1076 | 1084 | 1309 | 1063 | 1059 | 1064 | 1067 | 1072 | 05470402567 | Repaint Exterior | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1077 | 1085 | 1310 | 1064 | 1060 | 1065 | 1068 | 1073 | 03470402568 | Renovate Building For Storage | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1078 | 1086 | 1311 | 1065 | 1061 | 1066 | 1069 | 1074 | 25470402569 | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1082 | 1090 | 1312 | 1066 | 1062 | 1067 | 1070 | 1075 | 05470402573 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
1086 | 1094 | 1314 | 1067 | 1063 | 1068 | 1071 | 1076 | 15470402577 | Interior Paint | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1087 | 1095 | 1315 | 1068 | 1064 | 1069 | 1072 | 1077 | 38470402578 | Building Renovations | Capital Construction | Highway Trans. Fund 6 | 430000 | 430000
1088 | 1096 | 1316 | 1069 | 1065 | 1070 | 1073 | 1078 | 38470402579 | New Epoxy Flooring In Hangars 2,3 And 4 | Capital Construction | Highway Trans. Fund 6 | 210000 | 210000
1092 | 1100 | 1317 | 1070 | 1066 | 1071 | 1074 | 1079 | 16470402583 | Paint Interior Walls At Vehicle Titles And Registration - Corpus Christi DHQ | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1096 | 1104 | 1319 | 1071 | 1067 | 1072 | 1075 | 1080 | 13470402587 | Interior Renovation (Floors, Ceiling, & Ac Ducts) | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1103 | 1111 | 1320 | 1072 | 1068 | 1073 | 1076 | 1081 | 20470402594 | Rest Room/Shower/Ac/Water Heater | Capital Repairs | Highway Trans. Fund 6 | 9500 | 9500
1104 | 1112 | 1321 | 1073 | 1069 | 1074 | 1077 | 1082 | 17470402595 | Renovate Maintenance Building | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1105 | 1113 | 1322 | 1074 | 1070 | 1075 | 1078 | 1083 | 17470402596 | Replace Fuel Canopy - Bryan AEM | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1107 | 1115 | 1324 | 1075 | 1071 | 1076 | 1079 | 1084 | 25470402598 | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1108 | 1116 | 1325 | 1076 | 1072 | 1077 | 1080 | 1085 | 24470402599 | Install New Front Doors (Building ) And Secure The Lobby Area | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1109 | 1117 | 1326 | 1077 | 1073 | 1078 | 1081 | 1086 | 24470402600 | Modify Interior Doorway, At Stockroom Forklift Access. | Capital Repairs | Highway Trans. Fund 6 | 5900 | 5900
1110 | 1118 | 1327 | 1078 | 1074 | 1079 | 1082 | 1087 | 24470402601 | Building Renovations | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1112 | 1120 | 1328 | 1079 | 1075 | 1080 | 1083 | 1088 | 24470402603 | Larger Restroom In Our Maintenance Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1113 | 1121 | 1329 | 1080 | 1076 | 1081 | 1084 | 1089 | 02470402604 | Emergency Generator At Intelligent Transportation Management Center - Fort Worth DHQ | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000
1114 | 1122 | 1330 | 1081 | 1077 | 1082 | 1085 | 1090 | 22470402605 | Interior & Exterior Painting & Sheet Metal Painting | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1115 | 1123 | 1331 | 1082 | 1078 | 1083 | 1086 | 1091 | 22470402606 | Overhead Projector & Electrical | Capital Repairs | Highway Trans. Fund 6 | 2500 | 2500
1116 | 1124 | 1332 | 1083 | 1079 | 1084 | 1087 | 1092 | 38470402607 | Interior Renovations | Capital Construction | Highway Trans. Fund 6 | 180000 | 180000
1118 | 1126 | 1333 | 1084 | 1080 | 1085 | 1088 | 1093 | 09470402609 | Upgrade Lab | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1119 | 1127 | 1334 | 1085 | 1081 | 1086 | 1089 | 1094 | 09470402610 | Replace Plumbing | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
1120 | 1128 | 1335 | 1086 | 1082 | 1087 | 1090 | 1095 | 13470402611 | Painting Interior Structure Of Equip Shed | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1121 | 1129 | 1336 | 1087 | 1083 | 1088 | 1091 | 1096 | 16470402612 | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1122 | 1130 | 1337 | 1088 | 1084 | 1089 | 1092 | 1097 | 18470402613 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1124 | 1132 | 1338 | 1089 | 1085 | 1090 | 1093 | 1098 | 13470402615 | Replace Tin & Paint Exterior Struct Of Wash Rack | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1125 | 1133 | 1339 | 1090 | 1086 | 1091 | 1094 | 1099 | 13470402616 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1127 | 1135 | 1341 | 1091 | 1087 | 1092 | 1095 | 1100 | 19470402618 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1128 | 1136 | 1342 | 1092 | 1088 | 1093 | 1096 | 1101 | 19470402619 | Restroom Upgrades | Capital Construction | Highway Trans. Fund 6 | 181000 | 151000
1134 | 1142 | 1343 | 1093 | 1089 | 1094 | 1097 | 1102 | 17470402625 | Close In Part Of Shed For Work Area | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1135 | 1143 | 1344 | 1094 | 1090 | 1095 | 1098 | 1103 | 22470402626 | Install Interior Lighting | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1136 | 1144 | 1345 | 1095 | 1091 | 1096 | 1099 | 1104 | 22470402627 | Renovation Conference Room | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
1137 | 1145 | 1346 | 1096 | 1092 | 1097 | 1100 | 1105 | 22470402628 | Renovate Maintenance Facility | Capital Construction | Highway Trans. Fund 6 | 125000 | 125000
1138 | 1146 | 1347 | 1097 | 1093 | 1098 | 1101 | 1106 | 22470402629 | Retrofit Existing Office Space | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1143 | 1151 | 1348 | 1098 | 1094 | 1099 | 1102 | 1107 | 16470402634 | Repair Plumbing System At Truck Wash Bay - Kingsville MNT | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1144 | 1152 | 1349 | 1099 | 1095 | 1100 | 1103 | 1108 | 16470402635 | Repair Plumbing System At Truck Wash Bay - Robstown Maintenance | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1145 | 1153 | 1350 | 1100 | 1096 | 1101 | 1104 | 1109 | 22470402636 | Bay Wash Repairs | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1149 | 1157 | 1352 | 1101 | 1097 | 1102 | 1105 | 1110 | 12470402640 | Renovate Restrooms (Locker Rooms) | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
1150 | 1158 | 1353 | 1102 | 1098 | 1103 | 1106 | 1111 | 12470402641 | Replace Emergency Exit Signage | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
1151 | 1159 | 1354 | 1103 | 1099 | 1104 | 1107 | 1112 | 12470402642 | Upgrade Lighting (LED) | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
1155 | 1163 | 1356 | 1104 | 1100 | 1105 | 1108 | 1113 | 17470402646 | New Fuel Canopy - Hearne AEM | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1157 | 1165 | 1358 | 1105 | 1101 | 1106 | 1109 | 1114 | 16470402648 | Install Electrical Wiring - Alice AEM | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1159 | 1167 | 1360 | 1106 | 1102 | 1107 | 1110 | 1115 | 12470402650 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
1160 | 1168 | 1361 | 1107 | 1103 | 1108 | 1111 | 1116 | 22470402651 | Demo (D) And Install (I) Of 2 Lamp T8 Light Fixture (D-2 & I-6 @ Fueling Station; D-57 & I-45 @ Warehouse; And D-39 & I-31 @ MNT Vehicle | Capital Repairs | Highway Trans. Fund 6 | 18000 | 18000
1163 | 1171 | 1362 | 1108 | 1104 | 1109 | 1112 | 1117 | 15470402654 | Interior Paint | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1164 | 1172 | 1363 | 1109 | 1105 | 1110 | 1113 | 1118 | 15470402655 | Retrofit Shop Bay To Meeting Room | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1165 | 1173 | 1364 | 1110 | 1106 | 1111 | 1114 | 1119 | 38470402656 | Retrofit Of Existing Exterior Light Fixture | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1166 | 1174 | 1365 | 1111 | 1107 | 1112 | 1115 | 1120 | 38470402657 | EOC Technology Renovation (Electronics) | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
1167 | 1175 | 1366 | 1112 | 1108 | 1113 | 1116 | 1121 | 38470402658 | Retrofit Of Existing Exterior Light Fixture | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1168 | 1176 | 1367 | 1113 | 1109 | 1114 | 1117 | 1122 | 03470402659 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
1169 | 1177 | 1368 | 1114 | 1110 | 1115 | 1118 | 1123 | 16470402660 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1170 | 1178 | 1369 | 1115 | 1111 | 1116 | 1119 | 1124 | 11470402661 | Upgrade Interior Lighting | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1174 | 1182 | 1370 | 1116 | 1112 | 1117 | 1120 | 1125 | 17470402665 | Add Awning To Shop Building | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1175 | 1183 | 1371 | 1117 | 1113 | 1118 | 1121 | 1126 | 17470402666 | Administration Bldg Foundation Repair | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1176 | 1184 | 1372 | 1118 | 1114 | 1119 | 1122 | 1127 | 17470402667 | Awnings Between Buildings W/ Lights | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1179 | 1187 | 1374 | 1119 | 1115 | 1120 | 1123 | 1128 | 17470402671 | New Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
1181 | 1189 | 1376 | 1121 | 1117 | 1122 | 1125 | 1129 | 17470402673 | Paint Signal Warehouse Walls | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1182 | 1190 | 1377 | 1122 | 1118 | 1123 | 1126 | 1130 | 17470402674 | Repair Admin Building Water Intrusion | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1184 | 1192 | 1378 | 1123 | 1119 | 1124 | 1127 | 1131 | 21470402676 | Building Finish Out | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
N/A | N/A | N/A | N/A | 1120 | 1125 | 1128 | 1132 | 15470403043 | New Generator | Safety/Security | Highway Trans. Fund 6 | 0 | 0
1185 | 1193 | 1379 | 1124 | 1121 | 1126 | 1129 | 1133 | 38470402678 | Emergency Repairs - Statewide | Safety/Security | Highway Trans. Fund 6 | 50866849 | 49992465.505
SUBTOTAL PROJECTS NOT CURRENTLY FUNDED | [11 empty] | 146858049 | 145815165.505
805 | 813 | 1118 | 1125 | 1122 | 1127 | 1127 |  | 13470402294 | Replace Flooring |  | Other Funds Identified | 10000 | -10000
716 | 725 | 1046 | 1126 | 1123 | 1128 | 1128 |  | 15470402205 | Exterior Paint - Project done with Other Funds |  | Other Funds Identified | 15000 | -15000
SUBTOTAL PROJECTS CHANGED TO OTHER FUNDING SOURCE | [11 empty] | 25000 | -25000 |  |  |  | 0 | 0 | 0
PROJECTS BELOW WERE REMOVED OR CANCELLED FROM LIST
Removed | R1 | R1 | R1 | R1 | R1 | R1 | R1 | 38470402968 | Condition Assessment |  |  | 5000000 | -5000000
Removed | R2 | R2 | R2 | R2 | R2 | R2 | R2 | 38470402969 | Condition Assessment Software |  |  | 1000000 | -1000000
531 | 541 | R5 | R3 | R3 | R3 | R3 | R3 | 01470402020 | Demolish Existing Building |  |  | 29500 | -29500
156 | R17 | R6 | R4 | R4 | R4 | R4 | R4 | 03470401638 | In-Ground Shelter |  |  | 144125 | -144125
N/A | 206 | R108 | R5 | R5 | R5 | R5 | R5 | 03470402987 | Lift Station Grinder Pump Replacements |  |  | 0 | 0
53 | R19 | R7 | R6 | R6 | R6 | R6 | R6 | 04470401642 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
340 | 352 | R8 | R7 | R7 | R7 | R7 | R7 | 04470401829 | Sprinkler System Repairs |  |  | 8000 | -8000
189 | 70 | R9 | R8 | R8 | R8 | R8 | R8 | 05470401680 | Retrofit Existing Gate Opener W/C-Cure |  |  | 18000 | -18000
96 | 103 | R10 | R9 | R9 | R9 | R9 | R9 | 05470401737 | Install New Gate Opener To Existing Gate |  |  | 6500 | -6500
305 | 317 | 746 | R10 | R10 | R10 | R10 | R10 | 05470401794 | Replace Roof |  |  | 40000 | -40000
654 | 664 | R11 | R11 | R11 | R11 | R11 | R11 | 05470402143 | Install Exit Loops |  |  | 2500 | -2500
781 | 789 | 1097 | R12 | R12 | R12 | R12 | R12 | 05470402270 | Remove in ground hydraulic lift - Completed w/District funds Remove |  |  | 3000 | -3000
1084 | 1092 | 1313 | R13 | R13 | R13 | R13 | R13 | 05470402575 | Remove In-Ground Hydraulic Floor Lift |  |  | 3000 | -3000
Removed | R4 | R12 | R14 | R14 | R14 | R14 | R14 | 06470401497 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R6 | R13 | R15 | R15 | R15 | R15 | R15 | 06470401515 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R8 | R14 | R16 | R16 | R16 | R16 | R16 | 06470401525 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R12 | R15 | R17 | R17 | R17 | R17 | R17 | 06470401555 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
232 | R16 | R16 | R18 | R18 | R18 | R18 | R18 | 06470401616 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
323 | 335 | 753 | R19 | R19 | R19 | R19 | R19 | 06470401812 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
350 | 362 | R17 | R20 | R20 | R20 | R20 | R20 | 06470401839 | Paint Asphalt Tank Bases And Hardware. Deteriorating Paint And Rusting Steel |  |  | 10000 | -10000
354 | 366 | R18 | R21 | R21 | R21 | R21 | R21 | 06470401843 | Repair Irrigation Systems |  |  | 5000 | -5000
395 | 407 | R19 | R22 | R22 | R22 | R22 | R22 | 06470401884 | Replace Irrigation System For New Yard Design |  |  | 10000 | -10000
404 | 416 | R20 | R23 | R23 | R23 | R23 | R23 | 06470401893 | Repair Irrigation Systems |  |  | 5000 | -5000
451 | 461 | R21 | R24 | R24 | R24 | R24 | R24 | 06470401940 | Repair Irrigation Systems |  |  | 5000 | -5000
456 | 466 | R22 | R25 | R25 | R25 | R25 | R25 | 06470401945 | Repair Irrigation Systems |  |  | 5000 | -5000
467 | 477 | R23 | R26 | R26 | R26 | R26 | R26 | 06470401956 | Repair Irrigation Systems |  |  | 5000 | -5000
584 | 594 | R24 | R27 | R27 | R27 | R27 | R27 | 06470402073 | Repair/Replace Atg System On Above Ground Fuel Tanks |  |  | 12000 | -12000
585 | 595 | R25 | R28 | R28 | R28 | R28 | R28 | 06470402074 | Seal Roof Penetrations |  |  | 3000 | -3000
714 | R29 | R26 | R29 | R29 | R29 | R29 | R29 | 06470402203 | Repair/Replace Atg System On Above Ground Fuel Tanks |  |  | 12000 | -12000
792 | 800 | R27 | R30 | R30 | R30 | R30 | R30 | 06470402281 | Upgrade Rain Gutters |  |  | 7000 | -7000
1162 | 1170 | R28 | R31 | R31 | R31 | R31 | R31 | 06470402653 | Paint Cat-Walk |  |  | 10000 | -10000
341 | 353 | R29 | R32 | R32 | R32 | R32 | R32 | 07470401830 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
344 | 356 | 763 | R33 | R33 | R33 | R33 | R33 | 07470401833 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
347 | 359 | 766 | R34 | R34 | R34 | R34 | R34 | 07470401836 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
349 | 361 | 768 | R35 | R35 | R35 | R35 | R35 | 07470401838 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
351 | 363 | 769 | R36 | R36 | R36 | R36 | R36 | 07470401840 | Demolish Old Asphalt Storage Tank |  |  | 30000 | -30000
353 | 365 | 771 | R37 | R37 | R37 | R37 | R37 | 07470401842 | Replace Old Asphalt Storage Tank |  |  | 122000 | -122000
375 | 387 | R30 | R38 | R38 | R38 | R38 | R38 | 07470401864 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
378 | 390 | 788 | R39 | R39 | R39 | R39 | R39 | 07470401867 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
397 | 409 | R31 | R40 | R40 | R40 | R40 | R40 | 07470401886 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
399 | 411 | 803 | R41 | R41 | R41 | R41 | R41 | 07470401888 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
416 | 428 | 817 | R42 | R42 | R42 | R42 | R42 | 07470401905 | Replace Old Asphalt Storage Tank |  |  | 122000 | -122000
431 | 443 | R32 | R43 | R43 | R43 | R43 | R43 | 07470401920 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
433 | 445 | 831 | R44 | R44 | R44 | R44 | R44 | 07470401922 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
462 | 472 | 853 | R45 | R45 | R45 | R45 | R45 | 07470401951 | Demolish Old Asphalt Storage Tank |  |  | 30000 | -30000
468 | 478 | R33 | R46 | R46 | R46 | R46 | R46 | 07470401957 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
471 | 481 | 859 | R47 | R47 | R47 | R47 | R47 | 07470401960 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
112 | R13 | R34 | R48 | R48 | R48 | R48 | R48 | 08470401578 | Replace Roof |  |  | 40000 | -40000
113 | R14 | R35 | R49 | R49 | R49 | R49 | R49 | 08470401579 | Modifications/Upgrade HVAC |  |  | 120000 | -120000
48 | R15 | R36 | R50 | R50 | R50 | R50 | R50 | 08470401580 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
945 | 953 | R37 | R51 | R51 | R51 | R51 | R51 | 08470402436 | Install Floor Tile |  |  | 18000 | -18000
946 | 954 | R38 | R52 | R52 | R52 | R52 | R52 | 08470402437 | Level Wash Bay |  |  | 1500 | -1500
949 | 957 | R39 | R53 | R53 | R53 | R53 | R53 | 08470402440 | Upgrade Power Washer Building |  |  | 2500 | -2500
1133 | 1141 | R40 | R54 | R54 | R54 | R54 | R54 | 08470402624 | Install Double Pane Glass Windows In Store Front Entry Area |  |  | 4500 | -4500
N/A | 146 | 267 | R55 | R55 | R55 | R55 | R55 | 08470402982 | Spalling Concrete hazard - Add approved 1/5/16 Soloman create schedule..DUPLICATE WITH PROJECT ID 08-2983 |  |  | 0 | 0
27 | R7 | R41 | R56 | R56 | R56 | R56 | R56 | 09470401519 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
284 | 296 | R42 | R57 | R57 | R57 | R57 | R57 | 09470401772 | Replace Roof |  |  | 350000 | -350000
182 | 163 | 183 | R58 | R58 | R58 | R58 | R58 | 11470401671 | Replace Boiler At Warehouse-Count as one project (combined with /11-1494 ) |  |  | 45000 | -45000
190 | R21 | R43 | R59 | R59 | R59 | R59 | R59 | 11470401682 | Replace Emergency Generator |  |  | 38000 | -38000
1141 | 1149 | R44 | R60 | R60 | R60 | R60 | R60 | 11470402632 | Replace Fuel Dispensers |  |  | 20000 | -20000
N/A | 144 | 195 | R61 | R61 | R61 | R61 | R61 | 11470402981 | Foundation repair - Project is same as PROJ ID 11470402307 |  |  | 0 | 0
1041 | 1049 | R45 | R62 | R62 | R62 | R62 | R62 | 12470402532 | Renovate Breakroom |  |  | 5000 | -5000
158 | R18 | R46 | R63 | R63 | R63 | R63 | R63 | 13470401640 | Replace APU (Generator) |  |  | 10000 | -10000
495 | 505 | R47 | R64 | R64 | R64 | R64 | R64 | 13470401984 | Replace Asphalt Tank Berm |  |  | 10000 | -10000
738 | 746 | R48 | R65 | R65 | R65 | R65 | R65 | 13470402227 | Paint Exterior Structure Of Fuel Canopy |  |  | 5000 | -5000
1123 | 1131 | R49 | R66 | R66 | R66 | R66 | R66 | 13470402614 | Replace Tin At Mechanic Shop |  |  | 7000 | -7000
60 | 87 | R50 | R67 | R67 | R67 | R67 | R67 | 15470401690 | Replace Roof |  |  | 100000 | -100000
325 | 337 | 349 | R68 | R68 | R68 | R68 | R68 | 15470401814 | Replace Roof |  |  | 100000 | -100000
1003 | 1011 | R51 | R69 | R69 | R69 | R69 | R69 | 15470402494 | Paint, Carpet Replacement |  |  | 20000 | -20000
165 | 128 | R52 | R70 | R70 | R70 | R70 | R70 | 16470401649 | Replace Existing Security And Access Control System To C-Cure |  |  | 300000 | -300000
169 | 171 | R53 | R71 | R71 | R71 | R71 | R71 | 16470401654 | Upgrade HQ Campus Emergency Generator |  |  | 200000 | -200000
74 | R24 | R54 | R72 | R72 | R72 | R72 | R72 | 16470401708 | Replace Roof |  |  | 300000 | -300000
88 | R27 | R55 | R73 | R73 | R73 | R73 | R73 | 16470401728 | Replace Roof At Area Engineer And Maintenance - Corpus Christi AEM |  |  | 24000 | -24000
89 | R28 | R56 | R74 | R74 | R74 | R74 | R74 | 16470401729 | Replace\New Security Fence - Corpus Christi AEM |  |  | 17000 | -17000
523 | 533 | 190 | R75 | R75 | R75 | R75 | R75 | 16470402012 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Merged into 16-1913 |  |  | 12000 | -12000
865 | 873 | 326 | R76 | R76 | R76 | R76 | R76 | 16470402356 | Replace Flooring In Office Building And Paint Walls |  |  | 25000 | -25000
903 | 911 | R57 | R77 | R77 | R77 | R77 | R77 | 16470402394 | Replace\New Electrical Panel At Right Of Way - Corpus Christi DHQ |  |  | 15000 | -15000
962 | 970 | R58 | R78 | R78 | R78 | R78 | R78 | 16470402453 | Replace Ceiling Tiles In Office Building |  |  | 7500 | -7500
963 | 971 | 191 | R79 | R79 | R79 | R79 | R79 | 16470402454 | Replace 2 Existing Dual Product Fuel Dispensers At The Fuel Station - Merged into 16-1913 |  |  | 15000 | -15000
966 | 974 | R59 | R80 | R80 | R80 | R80 | R80 | 16470402457 | Replace Ceilings At Area Engineer And Maintenance - Sinton AEM |  |  | 7500 | -7500
972 | 980 | 328 | R81 | R81 | R81 | R81 | R81 | 16470402463 | Replace Flooring At Maintenance - Rockport MNT |  |  | 15000 | -15000
1158 | 1166 | 1359 | R82 | R82 | R82 | R82 | R82 | 16470402649 | Repair Sewer System - Alice AEM |  |  | 10000 | -10000
628 | 638 | 204 | R83 | R83 | R83 | R83 | R83 | 17470402117 | Upgrade HVAC System |  |  | 20000 | -20000
629 | 639 | R60 | R84 | R84 | R84 | R84 | R84 | 17470402118 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
633 | 643 | R82 | R85 | R85 | R85 | R85 | R85 | 17470402122 | Cameron MNT |  |  | 25000 | -25000
670 | 680 | R61 | R86 | R86 | R86 | R86 | R86 | 17470402159 | Demolish Old Ae Building |  |  | 12500 | -12500
671 | 681 | R62 | R87 | R87 | R87 | R87 | R87 | 17470402160 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
687 | 697 | R63 | R88 | R88 | R88 | R88 | R88 | 17470402176 | Replace Gutters |  |  | 5000 | -5000
918 | 926 | 1199 | R89 | R89 | R89 | R89 | R89 | 17470402409 | Upgrade Lighting In Washbay-CANCELLED COMPLETED BY DISTRICT |  |  | 5000 | -5000
920 | 928 | R64 | R90 | R90 | R90 | R90 | R90 | 17470402411 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
1074 | 1082 | R65 | R91 | R91 | R91 | R91 | R91 | 17470402565 | Redo Lighting In Washbay |  |  | 5000 | -5000
1075 | 1083 | R66 | R92 | R92 | R92 | R92 | R92 | 17470402566 | Replace Ceiling Tiles |  |  | 10000 | -10000
1130 | 1138 | R67 | R93 | R93 | R93 | R93 | R93 | 17470402621 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
1131 | 1139 | R68 | R94 | R94 | R94 | R94 | R94 | 17470402622 | Install Electric Door Openers For Roll-Up Doors |  |  | 7500 | -7500
1132 | 1140 | R69 | R95 | R95 | R95 | R95 | R95 | 17470402623 | Replace Windows On Storage Shed |  |  | 5000 | -5000
1152 | 1160 | 245 | R96 | R96 | R96 | R96 | R96 | 17470402643 | Add Network Connections To Lab Area |  |  | 7500 | -7500
1177 | 1185 | 1373 | R97 | R97 | R97 | R97 | R97 | 17470402669 | Install A/C System To HQ Warehouse - CANCELLED AC included in a portion of bldg. |  |  | 25000 | -25000
1183 | 1191 | R70 | R98 | R98 | R98 | R98 | R98 | 17470402675 | Upgrade Used Oil & Antifreeze Containers |  |  | 5000 | -5000
42 | R10 | R71 | R99 | R99 | R99 | R99 | R99 | 18470401545 | Relocate And Add HVAC To Break Room |  |  | 15000 | -15000
44 | R11 | R72 | R100 | R100 | R100 | R100 | R100 | 18470401547 | Fence - Repair Chain Link/Top Rail At Easement |  |  | 10000 | -10000
187 | R20 | R73 | R101 | R101 | R101 | R101 | R101 | 18470401676 | New Generator - Diesel |  |  | 25000 | -25000
311 | 323 | R74 | R102 | R102 | R102 | R102 | R102 | 18470401800 | New Generator - Diesel |  |  | 15000 | -15000
358 | 370 | R75 | R103 | R103 | R103 | R103 | R103 | 18470401847 | Parking Lot Striping |  |  | 5000 | -5000
368 | 380 | R76 | R104 | R104 | R104 | R104 | R104 | 18470401857 | Parking Lot Striping |  |  | 20000 | -20000
439 | 451 | R77 | R105 | R105 | R105 | R105 | R105 | 18470401928 | Parking Lot Striping |  |  | 10000 | -10000
494 | 504 | R78 | R106 | R106 | R106 | R106 | R106 | 18470401983 | Parking Lot Striping |  |  | 10000 | -10000
510 | 520 | R79 | R107 | R107 | R107 | R107 | R107 | 18470401999 | Parking Lot Striping |  |  | 10000 | -10000
617 | 627 | R81 | R108 | R108 | R108 | R108 | R108 | 18470402106 | Restroom Partitions Replaced |  |  | 3000 | -3000
651 | 661 | R83 | R109 | R109 | R109 | R109 | R109 | 18470402140 | Restroom Partitions Replacement - Men's Restroom |  |  | 1500 | -1500
1010 | 1018 | R84 | R110 | R110 | R110 | R110 | R110 | 18470402501 | Analysis By Engineering Consultant |  |  | 45000 | -45000
1021 | 1029 | R85 | R111 | R111 | R111 | R111 | R111 | 18470402512 | Countertops - Restrooms On 4Th Floor |  |  | 5000 | -5000
1 | 140 | R4 | R112 | R112 | R112 | R112 | R112 | 19470401488 | Install LED Parking Lot Lighting |  |  | 85000 | -85000
2 | R3 | R3 | R113 | R113 | R113 | R113 | R113 | 19470401489 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
39 | R9 | R86 | R114 | R114 | R114 | R114 | R114 | 20470401542 | Install Card Reader Access |  |  | 12000 | -12000
151 | 69 | 274 | R115 | R115 | R115 | R115 | R115 | 20470401632 | Fence Repairs |  |  | 9000 | -9000
365 | 377 | R88 | R117 | R117 | R117 | R117 | R117 | 20470401854 | Remove Out Of Service Emulsion, Linseed Oil & Asts |  |  | 20000 | -20000
412 | 424 | R89 | R118 | R118 | R118 | R118 | R118 | 20470401901 | Remove Out Of Service Emulsion, Linseed Oil & Asts |  |  | 20000 | -20000
746 | 754 | R90 | R119 | R119 | R119 | R119 | R119 | 20470402235 | Paint Flag Pole |  |  | 3000 | -3000
747 | 755 | R91 | R120 | R120 | R120 | R120 | R120 | 20470402236 | Rebuild Overhead Door (10) |  |  | 4000 | -4000
806 | 814 | 324 | R121 | R121 | R121 | R121 | R121 | 20470402295 | Asbestos Abatement 8-17-16 cancelled during scrub |  |  | 5000 | -5000
1031 | 1039 | R92 | R122 | R122 | R122 | R122 | R122 | 20470402522 | Clean Fuel Tanks |  |  | 4000 | -4000
1091 | 1099 | R93 | R123 | R123 | R123 | R123 | R123 | 20470402582 | Repair Heating System |  |  | 7500 | -7500
1098 | 1106 | 391 | R124 | R124 | R124 | R124 | R124 | 20470402589 | Abate Floor Tile 8-17-16 cancelled during scrub |  |  | 10000 | -10000
75 | 122 | 321 | R125 | R125 | R125 | R125 | R125 | 21470401710 | Replace Generator- Merged into 21-1538 |  |  | 40000 | -40000
77 | 124 | 334 | R126 | R126 | R126 | R126 | R126 | 21470401712 | Replace Generator- Merged into 21-1538 |  |  | 40000 | -40000
82 | R26 | R94 | R127 | R127 | R127 | R127 | R127 | 21470401721 | Replace Generator |  |  | 15000 | -15000
1171 | 1179 | R95 | R128 | R128 | R128 | R128 | R128 | 21470402662 | Bird Net For Truck Wash And Equip. Shed |  |  | 1000 | -1000
1172 | 1180 | R96 | R129 | R129 | R129 | R129 | R129 | 21470402663 | Repaint Generator |  |  | 500 | -500
1173 | 1181 | R97 | R130 | R130 | R130 | R130 | R130 | 21470402664 | Repair Wall Packs |  |  | 2500 | -2500
274 | 286 | 361 | R131 | R131 | R131 | R131 | R131 | 22470401762 | Furnish/Install HVAC -- 6/6/16 Per Byron this project is cancelled. |  |  | 100000 | -100000
443 | 455 | 838 | R132 | R132 | R132 | R132 | R132 | 22470401932 | Upgrade Sprinkler System |  |  | 5000 | -5000
498 | 508 | R98 | R133 | R133 | R133 | R133 | R133 | 22470401987 | Flag Pole Lighting |  |  | 3000 | -3000
516 | 526 | R99 | R134 | R134 | R134 | R134 | R134 | 22470402005 | Parking Lot Striping |  |  | 30000 | -30000
179 | 94 | R100 | R135 | R135 | R135 | R135 | R135 | 23470401667 | Upgrade Security (C-CURE) |  |  | 350000 | -350000 | [6 empty] | Cancelled and combined with 23-1392
65 | R23 | R101 | R136 | R136 | R136 | R136 | R136 | 24470401697 | Modifications/Upgrade Electrical |  |  | 150000 | -150000
79 | R25 | R102 | R137 | R137 | R137 | R137 | R137 | 24470401718 | Replace Roof |  |  | 285000 | -285000
345 | 357 | 764 | R138 | R138 | R138 | R138 | R138 | 24470401834 | Demolish Old Asphalt Storage Tank. |  |  | 8400 | -8400
463 | 473 | R103 | R139 | R139 | R139 | R139 | R139 | 24470401952 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
506 | 516 | R104 | R140 | R140 | R140 | R140 | R140 | 24470401995 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
507 | 517 | R105 | R141 | R141 | R141 | R141 | R141 | 24470401996 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
952 | 960 | R106 | R142 | R142 | R142 | R142 | R142 | 24470402443 | Install Garage Door Openers |  |  | 7000 | -7000
610 | 620 | R80 | R143 | R143 | R143 | R143 | R143 | 25470402099 | Crowell Maintenance |  |  | 25000 | -25000
58 | R22 | R107 | R144 | R144 | R144 | R144 | R144 | 38470401688 | Modifications/Upgrade Electrical |  |  | 517000 | -517000
331 | 343 | 188 | R145 | R145 | R145 | R145 | R145 | 38470401820 | Upgrade Obsolete Johnson Control Panels |  |  | 30000 | -30000
403 | 415 | 807 | 597 | R146 | R146 | R146 | R146 | 06470401892 | Connect to City Sewer Utililty Line |  |  | 20000 | -20000
548 | 558 | 919 | 702 | R147 | R147 | R147 | R147 | 06470402037 | Replace Garage Door W/Panel & Electric Open. |  |  | 8000 | -8000
588 | 598 | 951 | 731 | R148 | R148 | R148 | R148 | 06470402077 | Upgrade Electrical Wiring & Lights In Shop Area |  |  | 7000 | -7000
596 | 606 | 959 | 739 | R149 | R149 | R149 | R149 | 06470402085 | Install Shed Kit |  |  | 100000 | -100000
997 | 1005 | 1245 | 1001 | R150 | R150 | R150 | R150 | 06470402488 | Install Ladder Or Staircase |  |  | 5000 | -5000
998 | 1006 | 1246 | 1002 | R151 | R151 | R151 | R151 | 06470402489 | Reinstall Evaporative Coolers In Wall |  |  | 8000 | -8000
285 | 297 | 275 | 396 | R152 | R152 | R152 | R152 | 18470401773 | Install Gate - Electric W/Remote On Ih35 Service Road |  |  | 20000 | -20000
139 | 175 | 403 | 362 | 399 | R153 | R153 | R153 | 12470401620 | Replace Roof - Humble Area Engineer & Maintenance Office |  |  | 87000 | -87000
N/A | N/A | N/A | 390 | 405 | R154 | R154 | R154 | 38470403026 | Relace existing batteries on UPS and install battery monitoring - State Headquarters |  |  | 0 | 0 | [6 empty] | 2/3/17 Project scope moved to project 38-1505. Cancelled 11/16/16 to be relet in April 2017
334 | 346 | 310 | 416 | 407 | R155 | R155 | R155 | 01470401823 | Resurface Parking Lot - District Headquarters |  |  | 164000 | -164000
3 | 198 | 341 | 355 | 420 | R156 | R156 | R156 | 01470401490 | Replace Roof And Walls - Paris District Headquarters |  |  | 50000 | -50000
1020 | 1028 | 1265 | 404 | 448 | R157 | R157 | R157 | 18470402511 | Reconfigure To Allow For Drivethrough - District Headquarters |  |  | 21500 | -21500
[7 empty] | R157 | 16470403034 | Water Well - Alice Maintenance |  |  | 0 | 0 | [6 empty] | November - both phases moved to AY20-21. June 2018 Project split phases. Second half being done in 2018/19
SUBTOTAL PROJECTS REMOVED OR CANCELLED | [11 empty] | 12989025 | -12989025
[12 empty] | 200000000 | 199999999.505
Note on C7: Diana Miller: Now Ordering based on Start Sheet Dates