## FY18-19
FY 18-19 Report
| Original Estimated Project Budget | Current Estimated Project Budget | FY 2018-19 Encumbered | Percent Encumbered | FY 2018-19 Expended | Percent Expended | Remaining Project Balance | Percent Remaining
December 2018 Quarterly Report
DPS | 12000000 | 12000000 | 1467018 | 12.23% | 4934545 | 41.12% | 5598437 | 46.65%
TMD | 11000000 | 10992230 | 4779449 | 43.48% | 1583248 | 14.4% | 4629533 | 42.12%
TPWD | 66185665 | 66185665 | 6297691 | 9.515% | 7994435 | 12.08% | 51893539 | 78.41%
TDCJ | 41635989 | 50700727 | 27844311 | 54.92% | 9743076 | 19.22% | 13113340 | 25.86%
TFC | 90000000 | 90000000 | 53687004 | 59.65% | 6065954 | 6.74% | 30247042 | 33.61%
TXDOT | 62500000 | 62500000 | 13907049 | 22.25% | 2618996 | 4.19% | 45973955 | 73.56%
THC | 6350000 | 6350000 | 1870887 | 29.46% | 2594566 | 40.86% | 1884547 | 29.68%
SPB | 4700000 | 4700000 | 161655 | 3.439% | 367449 | 7.818% | 4170896 | 88.74%
DSHS | 1800000 | 1800000 | 25156 | 1.398% | 208304 | 11.57% | 1566540 | 87.03%
HHSC- State Hospitals | 80000000 | 80000000 | 4113410 | 5.142% | 4285995 | 5.357% | 71600595 | 89.5%
HHSC- State Supported Living Centers | 78600000 | 78600000 | 2865456 | 3.646% | 2145552 | 2.73% | 73588992 | 93.62%
JJD | 12100000 | 12100000 | 541402 | 4.474% | 328607 | 2.716% | 11229991 | 92.81%
Totals | 466871654 | 475928622 | 117560488 | 24.7% | 42870727 | 9.008% | 315497407 | 66.29%
September 2018 Quarterly Report
DPS | 12000000 | 12000000 | 4803191 | 40.03% | 641061 | 5.342% | 6555748 | 54.63%
TMD | 11000000 | 10558578 | 4787398 | 45.34% | 909682 | 8.616% | 4861498 | 46.04%
TPWD | 66185665 | 66185665 | 6150187 | 9.292% | 6090016 | 9.201% | 53945462 | 81.51%
TDCJ | 41635989 | 43195270 | 9170956 | 21.23% | 7056107 | 16.34% | 26968207 | 62.43%
TFC | 90000000 | 90000000 | 11871398 | 13.19% | 4058054 | 4.509% | 74070548 | 82.3%
TXDOT | 62500000 | 62500000 | 10671431 | 17.07% | 1185572 | 1.897% | 50642997 | 81.03%
THC | 6350000 | 6350000 | 2069372 | 32.59% | 2327473 | 36.65% | 1953155 | 30.76%
SPB | 4700000 | 4700000 | 193190 | 4.11% | 315782 | 6.719% | 4191028 | 89.17%
DSHS | 1800000 | 1800000 | 503982 | 28% | 14741 | 0.8189% | 1281277 | 71.18%
HHSC- State Hospitals | 80000000 | 74231531 | 4364654 | 5.88% | 2589326 | 3.488% | 67277551 | 90.63%
HHSC- State Supported Living Centers | 78600000 | 70418980 | 3480845 | 4.943% | 996642 | 1.415% | 65941493 | 93.64%
JJD | 12100000 | 12100000 | 541402 | 4.474% | 326696 | 2.7% | 11231902 | 92.83%
Totals | 466871654 | 454040024 | 58608006 | 12.91% | 26511152 | 5.839% | 368920866 | 81.25%
June 2018 Quarterly Report
DPS | 12000000 | 12000000 | 668416 | 5.57% | 384047 | 3.2% | 10947537 | 91.23%
TMD | 11000000 | 10303638 | 1459178 | 14.16% | 540680 | 5.247% | 8303780 | 80.59%
TPWD | 66185665 | 66185665 | 3546695 | 5.359% | 3614331 | 5.461% | 59024639 | 89.18%
TDCJ | 41635989 | 41996216 | 8095662 | 19.28% | 3274498 | 7.797% | 30626056 | 72.93%
TFC | 90000000 | 90000000 | 11037884 | 12.26% | 401839 | 0.4465% | 78560277 | 87.29%
TXDOT | 49640000 | 50000000 | 4756121 | 9.512% | 2898353 | 5.797% | 42345526 | 84.69%
THC | 6350000 | 6350000 | 2322701 | 36.58% | 2052656 | 32.33% | 1974643 | 31.1%
SPB | 4700000 | 4700000 | 212920 | 4.53% | 42881 | 0.9124% | 4444199 | 94.56%
DSHS | 1800000 | 1800000 | 36852 | 2.047% | 0 | 0% | 1763148 | 97.95%
HHSC- State Hospitals | 80000000 | 79059077 | 5255557 | 6.648% | 1540033 | 1.948% | 72263487 | 91.4%
HHSC- State Supported Living Centers | 78600000 | 74567911 | 3538609 | 4.745% | 285675 | 0.3831% | 70743627 | 94.87%
JJD | 12100000 | 12100000 | 539294 | 4.457% | 54963 | 0.4542% | 11505743 | 95.09%
Totals | 454011654 | 449062507 | 41469889 | 9.235% | 15089956 | 3.36% | 392502662 | 87.4%
March 2018 Quarterly Report
DPS | 12000000 | 12000000 | 180475 | 1.504% | 132787 | 1.107% | 11686738 | 97.39%
TMD | 11000000 | 10444416 | 1539264 | 14.74% | 164837 | 1.578% | 8740315 | 83.68%
TPWD | 66185665 | 66185665 | 1430502 | 2.161% | 1692464 | 2.557% | 63062699 | 95.28%
TDCJ | 41635989 | 41990138 | 7530478 | 17.93% | 1675558 | 3.99% | 32784102 | 78.08%
TFC | 90000000 | 90000000 | 3213288 | 3.57% | 33816 | 0.03757% | 86752896 | 96.39%
TXDOT | 49640000 | 50000000 | 3096945 | 6.194% | 0 | 0% | 46903055 | 93.81%
THC | 6350000 | 6350000 | 3594767 | 56.61% | 327224 | 5.153% | 2428009 | 38.24%
SPB | 4700000 | 4700000 | 237717 | 5.058% | 9854 | 0.2097% | 4452429 | 94.73%
DSHS | 1800000 | 1800000 | 0 | 0% | 0 | 0% | 1800000 | 100%
HHSC- State Hospitals | 80000000 | 80000000 | 3904822 | 4.881% | 255063 | 0.3188% | 75840115 | 94.8%
HHSC- State Supported Living Centers | 78600000 | 78600000 | 1086369 | 1.382% | 51289 | 0.06525% | 77462342 | 98.55%
JJD | 12100000 | 12100000 | 354871 | 2.933% | 9067 | 0.01154% | 11736062 | 96.99%
Totals | 454011654 | 454170219 | 26169498 | 5.762% | 4351959 | 0.9582% | 423648762 | 93.28%
December 2017 Quarterly Report
DPS | 12000000 | 12000000 | 143908 | 1.199% | 27191 | 0.2266% | 11828901 | 98.57%
TMD | 11000000 | 9777775 | 1491460 | 15.25% | 0 | 0% | 8286315 | 84.75%
TPWD | 66185665 | 66185665 | 964733 | 1.458% | 820525 | 1.24% | 64400407 | 97.3%
TDCJ | 41635989 | 41999389 | 2778596 | 6.616% | 845573 | 2.013% | 38375220 | 91.37%
TFC | 90000000 | 90000000 | 0 | 0% | 0 | 0% | 90000000 | 100%
TXDOT | 50000000 | 50000000 | 605000 | 1.21% | 0 | 0% | 49395000 | 98.79%
THC | 6350000 | 6350000 | 721825 | 11.37% | 63355 | 0.9977% | 5564820 | 87.63%
SPB | 4700000 | 4700000 | 9854 | 0.2097% | 0 | 0% | 4690146 | 99.79%
DSHS | 1800000 | 1800000 | 0 | 0% | 0 | 0% | 1800000 | 100%
HHSC- State Hospitals | 80000000 | 79632659 | 970829 | 1.219% | 0 | 0% | 78661830 | 98.78%
HHSC- State Supported Living Centers | 78600000 | 78515321 | 0 | 0% | 0 | 0% | 78515321 | 100%
JJD | 12100000 | 12100000 | 341665 | 2.824% | 0 | 0% | 11758335 | 97.18%
Totals | 454371654 | 453060809 | 8027870 | 1.772% | 1756644 | 0.3877% | 443276295 | 97.84%
October Hearing
DPS | 12000000 | 12000000 | 0 | 0% | 0 | 0% | 12000000 | 100%
TMD | 11000000 | 11000000 | 0 | 0% | 0 | 0% | 11000000 | 100%
TPWD | 66185665 | 66185665 | 0 | 0% | 0 | 0% | 66185665 | 100%
TDCJ | 41635989 | 41635989 | 609388 | 1.464% | 300361 | 0.7214% | 40726240 | 97.81%
TFC | 90000000 | 90000000 | 0 | 0% | 0 | 0% | 90000000 | 100%
TXDOT | 50000000 | 50000000 | 0 | 0% | 0 | 0% | 50000000 | 100%
THC | 6350000 | 6350000 | 1000000 | 15.75% | 0 | 0% | 5350000 | 84.25%
SPB | 4700000 | 4700000 | 9854 | 0.2097% | 0 | 0% | 4690146 | 99.79%
DSHS | 1800000 | 1800000 | 0 | 0% | 0 | 0% | 1800000 | 100%
HHSC- State Hospitals | 79923257 | 79923257 | 0 | 0% | 0 | 0% | 79923257 | 100%
HHSC- State Supported Living Centers | 79862729 | 79862729 | 0 | 0% | 0 | 0% | 79862729 | 100%
JJD | 12100000 | 12100000 | 0 | 0% | 0 | 0% | 12100000 | 100%
Totals | 455557640 | 455557640 | 1619242 | 0.3554% | 300361 | 0.06593% | 453638037 | 99.58%

## DPS
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2018-12-15
| Prepared by: | 85th Legislature - $12M DM Projects
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (FY19 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-18-62601 | Statewide DM Staff | Professional staff employed by DPS and/or contractors to administer DM projects | Economic Stabilization Fund (ESF) | 750000 | 750000 | NA | NA | NA |  |  | 750000 | No
2 | ST-IWMS-18-62930 | Statewide Integrated Workplace Management System | A computerized Integrated Workplace Management system (IWMS) that is web based and can be implemented statewide is needed to track and plan for maintenance of DPS facilities. As funding permits, this will include the implementation of space management, inventory management, lease management, and environmental sustainability integration. | ESF | 1700000 | 1700000 | 2019-08-31 | 0% | 0% |  |  | 1700000 | No
3 | ST-FCA-18-62931 | Statewide Facility Condition Assessment | Statewide Assessment: An updated professional statewide Facility Condition Assessment study is needed to identify current deferred maintenance and capital renewal projects and associated costs. - NOT APPROVED BY LBB - Project Substitution - Midland District Office Multi DM project. | ESF | 1300000 | 0 | CANCELED. Will be removed from JOC Report 3/2019 | 0% | 0% |  |  | 0 | Yes
3 | 4-MID-18-62931 | Midland District Office (Reg 4) Multi-Trade DM Project 2405 S. Loop 250 West Midland, Texas 79703 | Multi-trade deferred maintenance project | ESF |  | 1300000 | 2019-08-31 | 100% | 0% |  |  | 1300000 | Yes
4 | ST-SEC-18-62933 | Statewide Security Upgrade/Replacements | Replace and upgrade access controls, video surveillance systems, door hardware, exterior doors, replace broken/old cameras, add cameras, and add access control where needed. | ESF | 1000000 | 387000 | 2019-08-31 | 0% | 0% | 6635.25 | 63944.79 | 316419.96 | No
5 | ST-UST-18-62934 | Statewide Fuel System Removal/Replace | Remove underground storage tanks (UST) and replace with above ground storage tanks (Midland UST bulk fuel Removal/install AST for generator; Remove Plainview UST bulk fuel, Remove Sulphur Springs UST bulk fuel; Remove San Antonio diesel UST, inventory automation of various fuel systems) | ESF | 450000 | 34981 | 2019-08-31 | FUEL SYSTEM CONTROL BUDGET LINE | N/A |  |  | 34981 | No
5 | ST-UST-18-62934 | Midland District Office (Reg 4) Fuel System Removal 2405 S. Loop 250 West Midland, Texas 79703 | Midland UST Tank removal and AST installation | ESF |  | 75982 | 2018-05-04 | 100% | 100% |  | 75982 | 0 | No
5 | ST-UST-18-62934 | Plainview Area Office (Reg 5) Fuel System Removal 1108 South Columbia/Business I-27 Plainview, Texas 79072 | Plainview UST 4,000G Tank removal | ESF |  | 24500 | 2018-07-13 | 100% | 100% |  | 24500 | 0 | No
5 | ST-UST-18-62934 | Sulphur Springs Area Office (Reg 1) Fuel System Removal 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Sulphur Springs UST 4,000G Tank and pit water removal; Remediation of Sulphur Springs UST 4,000G Tank and pit water removal | ESF |  | 50503 | 2019-08-31 | 100% | 50% | 14995 | 30476 | 5032 | No
5 | ST-UST-18-62934 | San Antonio Regional Office (Reg 6) Fuel System Removal 6502 S. New Braunfels Ave. San Antonio, Texas 78223 | Remove and Dispose of 2,500 Gallon UST Underground Storage Tank | ESF |  | 19500 | 2018-12-31 | 100% | 90% |  | 19500 | 0 | No
5 | ST-UST-18-62934 | Angleton Area Office (Reg 2) Fuel System Removal 501 South Velasco Angleton, Texas 77515 | Angleton UST 4,000G Tank removal | ESF |  | 24499 | 2018-08-31 | 100% | 100% |  | 24499 | 0 | No
5 | ST-UST-18-62934 | Wichita Falls District Office (Reg 5) Fuel System Removal 5505 Central EXPWY Wichita Falls, Texas 76307 | Remove and Dispose of 4,000 Gallon UST | ESF |  | 47257 | 2018-12-31 | 100% | 90% | 47256.89 |  | 0.11 | No
5 | ST-UST-18-62934 | Hurst District Office (Reg 1) Fuel System Removal 624 NE Loop 820 Hurst, Texas 76053 | Remove and Dispose of 2,500 Gallon UST Underground Storage Tank | ESF |  | 22778 | 2019-03-31 | 50% | 0% | 22778 |  | 0 | No
5 | ST-UST-18-62934 | San Antonio Office (Reg 6) Fuel System Removal 6502 S New Braunfels Ave San Antonio, Texas 78223 | Remove and Dispose of 8,000 Gallon UST Underground Storage Tank | ESF |  | 50000 | 2019-08-31 |  |  |  |  | 50000 | No
5 | ST-UST-18-62934 | Longview Area Office (Reg 1) Fuel System Removal 416 Lake Lamond Longview, Texas 75604 | Remove and Dispose of 4,000 Gallon UST Underground Storage Tank | ESF |  | 50000 | 2019-08-31 |  |  |  |  | 50000 | No
5 | ST-UST-18-62934 | Denton Area Office (Reg 1) Fuel System Removal 820 N. Loop 288 Denton, Texas 76209 | Remove and Dispose of 6,000 Gallon UST Underground Storage Tank | ESF |  | 50000 | 2019-08-31 |  |  |  |  | 50000 | No
6 | ST-TEST-18-62935 | Statewide Support Project Consultants | Funding for design team, testing, consulting, commissioning, CMT, inspections type of expenditures associated with projects. | ESF | 300000 | 300000 | 2019-08-31 | 100% | 0% | 16000 |  | 284000 | No
7 | HQ-C-18-62936 | Austin HQ (Building C) HVAC System Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC System including piping, chiller, add DDC, etc. | ESF | 2950000 | 2950000 | TBD by TFC | 0% | 0% |  | 2950000 | 0 | No
8 | HQ-E-18-62937 | Austin HQ (Building E) Chiller Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chiller | ESF | 275000 | 275000 | TBD by TFC | 0% | 0% |  | 275000 | 0 | No
9 | 2-HHQ-18-62938 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Replace second chiller | ESF | 275000 | 340000 | 2019-02-01 | 100% | 50% | 236940 |  | 103060 | No
10 | 2-HQ-18-62939 | Houston Regional Headquarters (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Replace both chillers | ESF | 375000 | 680000 | 2019-06-30 | 100% | 0% | 401863 |  | 278137 | No
11 | 5-PLA-18-62940 | Plainview Area Office (Reg 5) Roof Replacement 1108 South Columbia/Business I-27 Plainview, Texas 79072 | Roof replacement (approx. 2,800 sf - addition) | ESF | 150000 | 150000 | 2018-05-31 | 100% | 100% |  | 62900 | 87100 | No
12 | 6-VIC-18-62941 | Victoria Sub District Office (Reg 6) CID Roof Replacement 8802 North Navarro Victoria, Texas 77904 | Roof replacement of CID building | ESF | 100000 | 65000 | 2018-07-06 | 100% | 100% |  | 33188 | 31812 | No
13 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Repave deteriorated asphalt with concrete on main drive lanes from Guadalupe to loading dock of Building A. Repair and expand paving at the Director's parking lot (Building A) | ESF | 583000 | 583000 | 2019-08-31 | 50% | 0% |  | 583000 | 0 | No
14 | HQ-CAM1-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Building E & G; Requires specialized EIFS clean, repair, paint, caulk, paint exterior doors | ESF | 200000 | 200000 | 2018-12-31 | 100% | 65% | 97950 | 97950 | 4100 | No
15 | HQ-CAM2-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Building A, B & C Annex; requires specialized repointing of joints, caulking and cleaning of historic limestone surfaces. Paint exterior doors and handrails. | ESF | 317000 | 317000 | 2019-08-31 | 100% | 30% | 268515 | 47385 | 1100 | No
16 | HQ-CAM3-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Buildings D, F4, F5, GA, H, K, L, O, & Q; Requires general caulking, repointing, cleaning and painting of block/metal/wood surfaces. Paint exterior doors and handrails. | ESF | 125000 | 125000 | 2018-12-31 | 100% | 97% | 8335 | 158365 | -41700 | No
17 | HQ-CAM4-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Repair and expand existing irrigation systems | ESF | 150000 | 150000 | 2019-08-31 | 100% | 0% |  |  | 150000 | No
18 | ST-CON-18-62932 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | ESF | 1000000 | 323094.92 | 2019-08-31 | CONTINGENCY CONTROL BUDGET LINE | NA |  |  | 323094.92 | No
19 | ST-CON-18-62932 | Austin District Office (Reg 6) - Roof Replacement Change Order 9000 IH-35 North Austin, Texas 78753 | Add to address hidden conditions revealed during the roof replacement | ESF |  | 19230 | 2019-01-31 | 100% | 95% | 19230 |  | 0 | No
20 | ST-CON-18-62932 | Austin HQ (Building A) Chiller Air Bleeder Repair 5805 North Lamar Blvd Austin, Texas 78752 | Chiller penthouse air bleeder repair | ESF |  | 3300 | 2019-08-31 | 100% | 0% | 3300 | 0 | 0 | No
21 | ST-CON-18-62932 | Austin HQ (Building C) Chilled Water Piping Repair 5805 North Lamar Blvd Austin, Texas 78752 | Chilled water piping repair | ESF |  | 2153 | 2019-08-31 | 100% | 0% | 2153 |  | 0 | No
22 | ST-CON-18-62932 | Statewide Alerton System | Statewide Repairs to Alerton System | ESF |  | 25000 | 2018-08-31 | 100% | 75% | 7150 | 17850 | 0 | No
23 | ST-CON-18-62932 | Wallisville Area Office (Reg 2) HVAC Replacement 20906 I-10 East Wallisville, Texas 77597 | HVAC System replacement of 7 1/2 Ton unit | ESF | 0 | 18950 | 2018-12-31 | 100% | 95% | 18950 |  | 0 | No
24 | ST-CON-18-62932 | Austin HQ (Bldg U) Urgent Chiller Repair 5805 North Lamar Blvd Austin, Texas 78752 | Chiller repair Building U | ESF |  | 3481.05 | 2018-08-23 | 100% | 100% |  | 3481 | 0.05 | No
25 | ST-CON-18-62932 | Corpus Christi District Office (Reg 3) Flooring Replacement 1922 South Padre Island Dr Corpus Christi, 78416 | Flooring replacement for CID area | ESF |  | 64220.17 | 2019-03-31 | 100% | 0% | 0 |  | 64220.17 | No
26 | ST-CON-18-62932 | Tactical Training Center (HQ) Asphalt Remediation 810 County Road 240 Florence, Texas 76527 | Asphalt remediation at the Tactical Training Center located in Florence. | ESF |  | 0 | CANCELED. Will be removed from JOC Report 3/2019 | 100% | 0% |  |  | 0 | Yes
27 | ST-CON-18-62932 | Tactical Training Center (HQ) Concrete Remediation 810 County Road 240 Florence, Texas 76527 | Concrete remediation | ESF |  | 11500 | 2018-12-22 | 100% | 0% | 11500 |  | 0 | No
28 | ST-CON-18-62932 | Austin HQ (Building G Annex) Replacement of Window 5805 North Lamar Blvd Austin, Texas 78752 | Replacement of window gasket | ESF |  | 94250 | 2018-11-21 | 100% | 100% | 94250 |  | 0 | No
29 | ST-CON-18-62932 | Corpus Christi District (Reg 3) Door Replacement 1922 South Padre Island Corpus Christi, Texas 78416 | Front and rear door replacement | ESF |  | 25500 | 2019-01-30 | 100% | 0% |  |  | 25500 | No
30 | ST-CON-18-62932 | Lubbock Crime Lab (Reg 5) AC Module Replacement 1404 Lubbock Business Park Blvd #200 Lubbock, Texas 79403 | A/C module replacement | ESF |  | 7500 | 2018-10-12 | 100% | 100% | 7500 | 0 | 0 | No
31 | ST-CON-18-62932 | Weslaco Regional Office (Reg 3) HVAC Coil Replacement 2525 N International Hwys Weslaco, Texas 78596 | HVAC coil replacement | ESF |  | 6733 | 2018-12-31 | 100% | 50% | 6733 |  | 0 | No
32 | ST-CON-18-62932 | Austin HQ (Building C) Temporary Chiller Rental 5805 North Lamar Blvd Austin, Texas 78752 | Rental of temporary 200 ton chiller Training Academy | ESF |  | 28484 | 2018-11-08 | 100% | 100% | 28484 |  | 0 | No
33 | ST-CON-18-62932 | Corpus Christi Crime Lab (Reg 3) HVAC Fan Motor Replacement 1922 S Padre Island Corpus Christi, TX 78416 | HVAC fan motor replacement | ESF |  | 5635 | TBD | 100% | 0% |  |  | 5635 | No
34 | ST-CON-18-62932 | Houston Regional Office (Reg 2) HVAC Controller Replacement 12230 West Road Jersey City, TX 77065 | Replacement of controllers and repair | ESF |  | 4380.75 | 2019-02-28 | 100% | 50% | 4380.75 |  | 0 | No
35 | ST-CON-18-62932 | Houston Crime Lab (Reg 2) HVAC Repair 12230 West Road Houston, TX 77065 | Remove and replace EXVA for repair of HVAC | ESF |  | 5137 | 2019-01-31 | 100% | 0% |  |  | 5137 | No
36 | ST-CON-18-62932 | Austin HQ (Building A) Corridor Refresh 5805 North Lamar Austin, TX 78752 | Refresh ceiling, walls, flooring | ESF |  | 20809 | TBD | 100% | 0% |  |  | 20809 | No
37 | ST-CON-18-62932 | Laredo Crime Laboratory (Reg 3) Fire Alarm Repair 1901 Bob Bullock Loop Laredo, Texas 78043 | Repairs required after an electrical storm for the Laredo Fire Alarm Panel | ESF |  | 8285 | 2017-12-07 | 100% | 100% |  | 8285.4 | -0.4 | No
38 | ST-CON-18-62932 | Houston Regional Headquarters Crime Lab (Reg 2) Chiller Repair 12230 West Road Jersey Village, Texas 77065 | Repairs to crime lab chiller #2 | ESF |  | 4100 | 2017-12-08 | 100% | 100% |  | 4100 | 0 | No
39 | ST-CON-18-62932 | Houston Regional Headquarters Crime Lab (Reg 2) Boiler Repair 12230 West Road Jersey Village, Texas 77065 | Repairs to the Houston crime lab boiler | ESF |  | 4732 | 2017-12-18 | 100% | 100% |  | 4732 | 0 | No
40 | ST-CON-18-62932 | Houston Regional Headquarters (Reg 2) Boiler Replacement 12230 West Road Jersey Village, Texas 77065 | Replace boiler | ESF |  | 29985 | 2018-01-05 | 100% | 100% |  | 29985 | 0 | No
41 | ST-CON-18-62932 | Decatur Area Office (Reg 1) RTU Replacement 2000 S. Trinity St Decatur, Texas 76234 | Replace roof top unit | ESF |  | 10079 | 2017-10-05 | 100% | 100% |  | 10079 | 0 | No
42 | ST-CON-18-62932 | Corpus Christi Crime Lab (Reg 3) RTU Coil Replacement 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Repairs to RTU #1 and #2 | ESF |  | 18653 | 2018-02-09 | 100% | 100% |  | 18653 | 0 | No
43 | ST-CON-18-62932 | San Antonio Regional HQ (Reg 6) ATG Repair 6502 South New Braunfels Ave San Antonio, Texas 78223 | ATG repairs and upgrades to the leak detection system | ESF |  | 14585.37 | 2018-03-19 | 100% | 100% |  | 14585.37 | 0 | No
44 | ST-CON-18-62932 | Odessa Area Office (Reg 4) Natural Gas Line Repair 1910 IH-20 West Odessa, Texas 79762 | Main natural gas line from meter to building repair | ESF |  | 4982.4 | 2018-01-02 | 100% | 100% |  | 4982.4 | 0 | No
45 | ST-CON-18-62932 | Babcock Area Office (Reg 6) Roof Repair 1258 Babcock Rd San Antonio, Texas 78201 | Roof repair | ESF |  | 2500 | 2017-10-06 | 100% | 100% |  | 2500 | 0 | No
46 | ST-CON-18-62932 | Childress District Office (Reg 5) Roof Repair 1700 Ave. F Northwest Ste A Childress, Texas 79201 | Repair leak in main office roof | ESF |  | 4000 | 2017-10-20 | 100% | 100% |  | 4000 | 0 | No
47 | ST-CON-18-62932 | Weslaco Regional Office (Reg 3) RTU Coil Replacement 2525 N. International Blvd Weslaco, Texas 78596 | Coil replacement for RTUs 5,8 & 9 | ESF |  | 39951.44 | 2018-08-20 | 100% | 100% | 39951.44 |  | 0 | No
48 | ST-CON-18-62932 | San Antonio Regional HQ (Reg 6) Roof Repair 6502 South New Braunfels Ave San Antonio, Texas 78223 | Roof repair on portable building | ESF |  | 3400 | 2017-11-03 | 100% | 100% |  | 3400 | 0 | No
49 | ST-CON-18-62932 | Austin HQ (Building B) HVAC Repair 5805 North Lamar Blvd Austin, Texas 78752 | Replaced compressor for HVAC controls serving building B. | ESF |  | 3112.1 | 2017-10-02 | 100% | 100% |  | 3112.1 | 0 | No
50 | ST-CON-18-62932 | Houston Regional Headquarters Crime Lab (Reg 2) Generator Repair 12230 West Road Jersey Village, Texas 77065 | Houston crime lab generator repairs | ESF |  | 4905.4 | 2018-01-23 | 100% | 100% |  | 4905.4 | 0 | No
51 | ST-CON-18-62932 | Houston Regional Headquarters Crime Lab (Reg 2) Boiler Repair 12230 West Road Jersey Village, Texas 77065 | Houston Crime Lab boiler #1 (heat exchanger and burner assembly) repairs | ESF |  | 11822.5 | 2018-03-15 | 100% | 100% |  | 11822.5 | 0 | No
52 | ST-CON-18-62932 | Longview Area Office (Reg 1) Heat Exchange Repair 416 Lake Lamond Road Longview, Texas 75064 | Heat exchange is no longer functioning in the HP area | ESF |  | 8750 | 2018-01-05 | 100% | 100% |  | 8750 | 0 | No
53 | ST-CON-18-62932 | Austin HQ (Building U) Boiler Repair 5805 North Lamar Blvd Austin, Texas 78752 | Rental of boiler to support crime laboratory building while repairs are completed | ESF |  | 9400 | 2018-03-13 | 100% | 100% | 733.34 | 8666.66 | 0 | No
54 | ST-CON-18-62932 | Austin HQ (Building U) Boiler Repair 5805 North Lamar Blvd Austin, Texas 78752 | Repair of boiler at the crime laboratory building | ESF |  | 18084.87 | 2018-08-02 | 100% | 100% | 4000 | 14084.87 | 0 | No
55 | ST-CON-18-62932 | Lufkin Sub district Office (Reg 2) RTU Replacement 2809 South John Redditt Drive Lufkin, Texas 75904 | RTU 3 replacement | ESF |  | 6345 | 2018-03-26 | 100% | 100% |  | 6345 | 0 | No
56 | ST-CON-18-62932 | Del Rio Sub District Office (Reg 3) HVAC Repair 2012 Veteran Boulevard Del Rio, Texas 78840 | HP compressor and fan motor repair | ESF |  | 3236.56 | 2017-11-15 | 100% | 100% |  | 3236.56 | 0 | No
57 | ST-CON-18-62932 | Webster Area Office (Reg 2) Heater Replacement 111 Tristar Webster, Texas 77598-1513 | Heater replacement | ESF |  | 2910.5 | 2018-03-12 | 100% | 100% |  | 2910.5 | 0 | No
58 | ST-CON-18-62932 | Beaumont District Office (Reg 2) HVAC Repair 7200 Eastex Freeway Beaumont, Texas 77708 | HVAC condensing unit replacement | ESF |  | 3100 | 2018-01-12 | 100% | 100% |  | 3100 | 0 | No
59 | ST-CON-18-62932 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Air handler replacement - electrical panel breaker | ESF |  | 3403.84 | 2018-01-08 | 100% | 100% |  | 3403.84 | 0 | No
60 | ST-CON-18-62932 | Gilmer Area Office (Reg 1) RTU Repair 713 State Highway 155 North Gilmer, Texas 75644-5725 | Replace heat exchanger in the RTU | ESF |  | 2700 | 2018-03-19 | 100% | 100% |  | 2700 | 0 | No
61 | ST-CON-18-62932 | Houston - Gessner DL (Reg 2) Boiler Replacement 12220 South Gessner Houston, Texas 77071-2831 | Boiler replacement | ESF |  | 19840 | 2018-02-28 | 100% | 100% |  | 19840 | 0 | No
62 | ST-CON-18-62932 | Austin HQ (Building A) HVAC Thermostat Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Add zone control | ESF |  | 5500 | 2018-05-18 | 100% | 100% |  | 5500 | 0 | No
63 | ST-CON-18-62932 | Canton Area Office (Reg 1) Heating Repair 1601 North Trade Days Blvd. Canton, Texas 75103 | Additional panel required to support additional heat strips for the unit. | ESF |  | 0 | Paid from other funds. Will be removed from JOC Report 3/2019. YES | 100% | 100% |  |  | 0 | Yes
64 | ST-CON-18-62932 | Garland Regional Headquarters (Reg 1) Water Heater Replacement 350 West IH-30 Garland, Texas 75043 | Water heater replacement | ESF |  | 1942.26 | 2018-03-12 | 100% | 100% |  | 1942.26 | 0 | No
65 | ST-CON-18-62932 | Garland Crime Laboratory (Reg 1) HVAC Repair 402 West IH-30 Garland, Texas 75043 | Repair chiller for the crime laboratory | ESF |  | 25000 | 319/2018 | 100% | 100% | 14445.48 | 10554.52 | 0 | No
66 | ST-CON-18-62932 | Austin HQ (Building Q) Duct Cleaning 5805 North Lamar Blvd Austin, Texas 78752 | Duct cleaning at crime laboratory | ESF |  | 5875 | 2018-05-30 | 100% | 100% |  | 5875 | 0 | No
67 | ST-CON-18-62932 | Brenham Area Office (Reg 2) HVAC Repair 975 Hwy 290 West. Brenham, Texas 77834 | Install new electrical circuit for HVAC system | ESF |  | 2700 | 2018-01-03 | 100% | 100% |  | 2700 | 0 | No
68 | ST-CON-18-62932 | Waco District Office (Reg 6) Roof Repair 1617 E. Crest Dr. Waco, Texas 76705 | Roof leak repairs at nine locations | ESF |  | 4500 | 2018-01-09 | 100% | 100% |  | 4500 | 0 | No
69 | ST-CON-18-62932 | Seguin Area Office (Reg 6) Roof Repair 1440 East Kingsbury Seguin, Texas 78155 | Roof leak repairs | ESF |  | 4200 | 2018-01-12 | 100% | 100% |  | 4200 | 0 | No
70 | ST-CON-18-62932 | Austin HQ (Building C) HVAC Repair 5805 North Lamar Blvd Austin, Texas 78752 | HVAC repair | ESF |  | 4161.92 | 2018-01-26 | 100% | 100% |  | 4161.92 | 0 | No
71 | ST-CON-18-62932 | Houston Regional Headquarters (West Road) (Reg 2) HVAC Repair 12230 West Road Jersey Village, Texas 77065 | Repairs to the Houston chillers to keep operational until they are replaced. (replacement project is in process.) | ESF |  | 55011.93 | 2018-04-06 | 100% | 100% |  | 55011.93 | 0 | No
72 | ST-CON-18-62932 | Austin HQ (Building C) Electrical Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Upgrade electrical capacity to provide clean power for the chiller units. | ESF |  | 10908.52 | 2018-06-26 | 100% | 100% | 346.87 | 10561.75 | -0.1 | No
73 | ST-CON-18-62932 | Sweetwater Area Office (Reg 5) Security Gate Replacement 600 Northwest Georgia Sweetwater, Texas 79556 | Security gate replacement | ESF |  | 4088 | 2018-04-24 | 100% | 100% |  | 4088 | 0 | No
74 | ST-CON-18-62932 | Rio Grande Area Office (Reg 3) RTU Repair 700 E. Hidalgo St. Rio Grande City, Texas 78582 | Repair roof top unit #1 | ESF |  | 3555.83 | 2018-01-15 | 100% | 100% |  | 3555.83 | 0 | No
75 | ST-CON-18-62932 | Weslaco Regional Office (Reg 3) RTU Repair 2525 N. International Blvd Weslaco, Texas 78599 | Repair Crime Lab roof top unit #1 | ESF |  | 3445 | 2018-02-15 | 100% | 100% |  | 3445 | 0 | No
76 | ST-CON-18-62932 | Garland Crime Laboratory (Reg 1) Chiller Repair 350 West IH-30 Garland, Texas 75043 | Repair chiller for the Crime Laboratory | ESF |  | 4133.61 | 2018-03-13 | 100% | 100% |  | 4133.61 | 0 | No
77 | ST-CON-18-62932 | Lubbock Regional Office (Reg 5) Roof Exhaust Fan Repair 1404 Lubbock Business Park Blvd., Ste 100 Lubbock, Texas 79403 | Repair exhaust fan on roof (replace motor) | ESF |  | 5500.24 | 2018-07-03 | 100% | 100% | 5500.24 |  | 0 | No
78 | ST-CON-18-62932 | Austin HQ (Building A) Elevator Repair 5805 North Lamar Blvd Austin, Texas 78752 | Repair freight elevator serving TDEM | ESF |  | 31747 | 2018-07-31 | 100% | 100% | 0 | 31747 | 0 | No
79 | ST-CON-18-62932 | Austin HQ (Building Q) Generator Repair 5805 North Lamar Blvd Austin, Texas 78752 | Repair generator serving CODIS | ESF |  | 2900.27 | 2018-03-15 | 100% | 100% |  | 2900.27 | 0 | No
80 | ST-CON-18-62932 | Marshall DPS Office(Reg 1) HVAC Repair 5215 West Loop 390 North Marshall, Texas 75670-2610 | Repair 4 ton heat pump in Marshall DPS office | ESF |  | 5250 | 2018-04-18 | 100% | 100% |  | 5250 | 0 | No
81 | ST-CON-18-62932 | Webster DPS Office (Reg 2) Heat Pump Replacement 111 Tristar Webster, Texas 77598-1513 | Heat pump system replacement | ESF |  | 13786 | 2018-10-04 | 100% | 100% | 13786 |  | 0 | No
82 | ST-CON-18-62932 | Eagle Pass DL Office (Reg 4) HVAC Repair 32 Foster Maldonado Eagle Pass, Texas 78852 | Compressor repair | ESF |  | 2830.21 | 2017-11-03 | 100% | 100% |  | 2830.21 | 0 | No
83 | ST-CON-18-62932 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | A/C replacement and repairs | ESF |  | 4972.5 | 2018-04-12 | 100% | 100% |  | 4972.5 | 0 | No
84 | ST-CON-18-62932 | Victoria Sub District Office (Reg 6) Plumbing Repair 8802 North Navarro Victoria, Texas 77904 | Repair plumbing leaks | ESF |  | 6000 | 2018-07-25 | 100% | 100% | 0 | 6000 | 0 | No
85 | ST-CON-18-62932 | Austin HQ (Building C) Automation System Repair 5805 North Lamar Blvd Austin, Texas 78752 | Repair automation system | ESF |  | 4905 | 2018-04-13 | 100% | 100% |  | 4905 | 0 | No
86 | ST-CON-18-62932 | Austin HQ (Building E) A/C Repair 5805 North Lamar Blvd Austin, Texas 78752 | Damper repair | ESF |  | 2084 | 2018-07-27 | 100% | 100% | 0 | 2084 | 0 | No
87 | ST-CON-18-62932 | Austin HQ (Building C) A/C Repair 5805 North Lamar Blvd Austin, Texas 78752 | Air handler repair | ESF |  | 16590.94 | 2018-07-27 | 100% | 100% | 2140.83 | 14450.11 | 0 | No
88 | ST-CON-18-62932 | Garland Regional Headquarters (Reg 1) Fuel System Repair 350 West IH 30 Garland, Texas 75043-5953 | Repairs to ATG - leak in detection system | ESF |  | 16496.16 | 2018-08-06 | 100% | 100% | 2702.19 | 13793.97 | 0 | No
89 | ST-CON-18-62932 | Galveston Driver License Office (Reg 2) Light Pole Repair 6812 Broadway Galveston, Texas 77554-8096 | Repair electrical light pole - Lighting Conduit Wire | ESF |  | 3800 | 2018-05-02 | 100% | 100% |  | 3800 | 0 | No
90 | ST-CON-18-62932 | Rosenberg Area Office (Reg 2) HVAC Replacement 5505 Avenue N. Rosenberg, Texas 77471 | HVAC System replacement of 8 1/2 Ton unit | ESF |  | 22968 | 2018-08-17 | 100% | 100% | 22968 |  | 0 | No
91 | ST-CON-18-62932 | Conroe District Office (Reg 2) Hose Bib Repair 804 S IH-45 Conroe, Texas 77304 | Exterior hose bibs replacements that were leaking causing deterioration of the mortar joints | ESF |  | 4012 | 2018-04-23 | 100% | 100% |  | 4012 | 0 | No
92 | ST-CON-18-62932 | Bryan District Office (Reg 2) Lighting Panel Repair 2571 N Earl Rudder Frwy Bryan, Texas77805 | Repair lighting circuit | ESF |  | 3266.88 | 2018-04-10 | 100% | 100% |  | 3266.8 | 0.08 | No
93 | ST-CON-18-62932 | Baytown Area Office (Reg 2) RTU Repair 5420 Decker Drive Baytown, Texas 77520 | Repair 3 RTUs #1, #2 and #3 | ESF |  | 3500 | 2018-04-27 | 100% | 100% |  | 3500 | 0 | No
94 | ST-CON-18-62932 | Austin HQ (Building D) A/C Repair 5805 North Lamar Blvd Austin, Texas 78752 | Evaporator coil repair HVAC | ESF |  | 21391.37 | 2018-08-21 | 100% | 100% |  | 21391.37 | 0 | No
95 | ST-CON-18-62932 | Austin HQ (Building A) Interior Refresh 5805 North Lamar Blvd Austin, Texas 78752 | Vinyl tile replacement | ESF |  | 3300 | 2018-07-01 | 100% | 100% |  | 3300 | 0 | No
96 | ST-CON-18-62932 | San Angelo Sub District (Reg 4) Fire Alarm Repair 1600 West Loop 306 San Angelo, Texas 76904 | Repair the fire alarm panel | ESF |  | 3295 | 2018-04-05 | 100% | 100% |  | 3295 | 0 | No
97 | ST-CON-18-62932 | Lubbock Crime Lab (Reg 5) Coil Condenser Replacement 1404 Lubbock Business Park Blvd Ste 200 Lubbock, Texas 79403 | Coil condenser replacement | ESF |  | 7210 | 2018-08-30 | 100% | 100% | 7210 |  | 0 | No
98 | ST-CON-18-62932 | San Antonio Regional HQ (Reg 6) HVAC Repair 6502 S New Braunfels Ave New Braunfels, Texas 78223 | A/C compressor | ESF |  | 3117 | 2018-06-20 | 100% | 100% |  | 3116.97 | 0.03 | No
99 | ST-CON-18-62932 | Eagle Pass Area Office HVAC Repair 32 Foster Maldonado Blvd Eagle Pass, Texas 78852 | HVAC repair | ESF |  | 13500 | 2018-10-04 | 100% | 100% | 0 | 13500 | 0 | No
100 | ST-CON-18-62932 | Tactical Training Center (HQ) HVAC Repair 810 County Road 240 Florence, Texas 76527 | Install compression | ESF |  | 3049.78 | 2018-10-02 | 100% | 100% | 3049.78 |  | 0 | No
101 | ST-CON-18-62932 | Houston Crime Laboratory (Reg 2) Boiler Replacement 12230 West Road Houston, TX 77065 | Repair boiler #1 and #2 | ESF |  | 2167 | 2018-10-01 | 100% | 100% | 2167 |  | 0 | No
102 | ST-CON-18-62932 | Corpus Christi Crime Laboratory (Reg 3) HVAC Repair 1922 South Padre Island Drive Corpus Christi, TX 78416 | Repair HVAC Crime Lab | ESF |  | 2373.6 | 2018-10-15 | 100% | 100% | 2374 |  | -0.4 | No
103 | ST-CON-18-62932 | Austin HQ (Warehouse) HVAC Repair 108 Denson Drive Austin, TX 78758 | Repair of AC unit | ESF |  | 2421.52 | 2018-10-19 | 100% | 100% | 2422 |  | -0.48 | No
104 | ST-CON-18-62932 | Austin HQ (Warehouse) HVAC Repair 108 Denson Drive Austin, TX 78758 | Repair of A/C | ESF |  | 2850 | 2018-11-12 | 100% | 100% | 2850 |  | 0 | No
105 | ST-CON-18-62932 | Austin HQ (Building C) HVAC Repair 5805 North Lamar Austin, TX 78758 | Service to Bldg C Chiller | ESF |  | 4521.2 | 2018-11-12 | 100% | 100% | 4521.2 |  | 0 | No
106 | ST-CON-18-62932 | Austin HQ (Building C)) HVAC Repair 5805 North Lamar Austin, TX 78758 | Repair of compressor kit | ESF |  | 3739.95 | 2018-11-12 | 100% | 100% | 3740 |  | -0.05 | No
107 | ST-CON-18-62932 | Eagle Pass Area Office (Reg 3) HVAC Repair 32 Foster Maldonado Blvd. Eagle Pass, TX 78552 | Repair of compressor kit | ESF |  | 2319.44 | 2018-11-09 | 100% | 100% | 2319 |  | 0.44 | No
108 | ST-CON-18-62932 | Conroe District Office (Reg 2) Generator Repair 2 Hilbig Road Conroe, Texas 77301 | Repair of generator control board | ESF |  | 2445.5 | 2018-12-31 | 100% |  | 2446 |  | -0.5 | No
109 | ST-CON-18-62932 | Texarkana Area Office (Reg 1) HVAC Repair 1516 Hampton Texarkana, Texas 75503 | Repair of Gas Rooftop Units for the HVAC system URGENT | ESF |  | 2445.5 | 2018-12-31 | 100% |  | 2446 |  | -0.5 | No
|  |  |  | Totals: | 12000000 | 12000000 |  |  |  | 1467018.26 | 4934545.41 | 5598436.33

## DPS Sup.
DM85 SUPPLEMENTAL NOTES
3 | LBB did not approve the Facility Condition Assessment. Cancelled project. Will remove FCA project for March 2019 report. Substituted the Midland District Office multi- DM project originally funded in 83rd session and required additional funding to award to general contractor.
26 | Project exceeded $45,000 estimate. Cancelled project under DM85 and moved to DM84 bond. Will remove this contingency project line for March 2019 report.
63 | Repair paid from alternate funds. Will remove contingency project for March 2019 report.

## TMD
| Agency: | Texas Military Department - Agency 401
| Date: | 2018-11-30 | [9 empty] | 2018-11-30
Prepared by:
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 48120206 | Camp Mabry Admin Offices 2200 W 35th St Bldg 1 Austin, 78730 | The project will repair 22,702 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 4300838.9 | 2020-01-26 | 100% | 0% | 3886210.63 | 414628.27 | 5.2387e-10 | yes
2 | 48190030 | Weslaco Readiness Center 1100 Vo-Tech Drive Weslaco 78596 | The project will repair an existing 76,069 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 795518.34 | 2020-01-20 | 100% | 0% | 221950.37 | 573567.97 | 0 | yes
3 | 48140040 | Terrell Readiness Center Lions Club Parkway Hwy 80 West Terrell 75160 | The project will repair an existing 22,138 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 1500000 | 1650025.16 | Q3 FY20 | 10% | 0% | 149117.93 | 141819.23 | 1359088 | yes
4 | 48180020 | Fort Worth Shoreview Readiness Center 8111 Shoreview Dr Fort Worth 76108 | The project will repair 59,027 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2000000 | 1593179.34 | Q4 FY20 | 10% | 0% | 62643 | 221267 | 1309269.34 | yes
5 | 48190020 | Fort Worth Cobb Park Readiness Center 2101 Cobb Park Dr Fort Worth 76105 | The project will repair an existing 34,549 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 2652668 | Q4 FY20 | 10% | 0% | 459527 | 231965.45 | 1961175.55 | yes
|  |  |  | Totals: | 11000000 | 10992229.74 |  |  |  | 4779448.93 | 1583247.92 | 4629532.89
-7770.26
7770.26

## TMD Sup.
| Agency: | Texas Military Department - Agency 401
| Date: | 2018-11-30
Prepared by:
Project Priority | Supplemental Information
| Project Name & Location | Total Estimated Project Budget | Federal Share | Federal Share Encumbered | Federal Share Expended | Remaining Federal Share | Comments
1 | Camp Mabry Admin Offices 2200 W 35th St Bldg 1 Austin, 78730 | 5000000 | 4457156.4 | 4309642.9 | 147513.5 | 0 | Project in Construction
2 | Weslaco Readiness Center 1100 Vo-Tech Drive Weslaco 78596 | 5000000 | 2991325.24 | 2937593.24 | 53732 | 0 | Project in Construction
3 | Terrell Readiness Center Lions Club Parkway Hwy 80 West Terrell 75160 | 3000000 | 1650025.84 | 23789.84 | 0 | 1626236 | Project in Design
4 | Fort Worth Shoreview Readiness Center 8111 Shoreview Dr Fort Worth 76108 | 4000000 | 2137196.66 | 248876 | 0 | 1888320.66 | Project in Design
5 | Fort Worth Cobb Park Readiness Center 2101 Cobb Park Dr Fort Worth 76105 | 5000000 | 2623738 | 342025 | 0 | 2281713 | Project in Design
| Totals: | 22000000 | 13859442.14
8129557.86

## TPWD
| Agency: | Texas Parks and Wildlife Department
| Date: | 2018-12-15 | [9 empty] | 2018-12-15
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1th Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, TX,77571 (Harris County) | Construction administration and Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | General Revenue - (SGST) | 1200000 | 974726.14 | 2019-02-25 | 100% | 82% | 98341.76 | 738729.01 | 137655.37
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Construction costs Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 35000 | 1107297.34 | 2020-09-03 17:00 | 95% | 0% | 58430 | 5239.07 | 1043628.27
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Construction costs Planning and design costs to upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | General Revenue - (SGST) | 71904.6225 | 1722970.86 | 2020-02-18 17:00 | 95% | 52% | 272131.2 | 30834.24 | 1420005.42
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Construction costs Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | General Revenue - (SGST) | 50000 | 353667.49 | 2020-04-08 | 60% | 0% | 72074.5 | 8254.41 | 273338.58 | *
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 57245.7375 | 20110.39 | 2018-03-23 17:00 | 100% | 100% | -1.4211e-14 | 9871.24 | 10239.15
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | General Revenue - (SGST) | 809623.8885 | 517434.73 | 2019-02-12 | 100% | 65% | 10682.72 | 208785.56 | 297966.45
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 180000 | 159042.94 | 2018-10-05 17:00 | 100% | 95% | 5755 | 66547.57 | 86740.37
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Planning and design costs to renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | General Revenue - (SGST) | 23410.128 | 27040.47 | 2022-04-20 12:00 | 60% | 0% | 0 | 12217.28 | 14823.19
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | General Revenue - (SGST) | 25803.384 | 343773.84 | 2023-02-08 | 60% | 0% | 0 | 15771.88 | 328001.96
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Construction costs Planning and design costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | General Revenue - (SGST) | 500000 | 3262036.16 | 2020-07-24 17:00 | 95% | 0% | 301548.56 | 464313.36 | 2496174.24
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 75782.466 | 83087 | 2018-09-26 17:00 | 100% | 99% | 0 | 47759.08 | 35327.92
12 | 117505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 500891.085 | 334626.07 | 2019-03-05 17:00 | 100% | 64% | 71227.69 | 115063.58 | 148334.8
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | General Revenue - (SGST) | 126919.248 | 65470.76 | 2018-10-17 17:00 | 100% | 99% | 5489.21 | 45670.41 | 14311.14
14 | 124729 | San Jacinto Battleground SHS - Replace Residence 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Planning and design costs to replace two residences and remove from a sensitive archaeological site. (Project on Hold) | General Revenue - (SGST) | 0 | 206.29 | N/A | 100% | 0% | 0 | 206.29 | 0
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | General Revenue - (SGST) | 65290.767 | 38792.45 | 2018-10-04 17:00 | 100% | 99% | 1549.57 | 26425.7 | 10817.18
16 | 127358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | General Revenue - (SGST) | 224828.6985 | 100043.12 | 2018-09-11 | 100% | 95% | 48793.49 | 39007.07 | 12242.56
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | General Revenue - (SGST) | 93705.801 | 46269.29 | 2018-07-02 17:00 | 100% | 100% | 1202.76 | 29129.34 | 15937.19
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace multiple obsolete septic systems to meet TCEQ requirements. | General Revenue - (SGST) | 50000 | 30597.99 | 2018-02-26 | 100% | 100% | -1.4211e-14 | 30597.99 | 0
19 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Planning and design costs to renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. Project also includes the cost to construct the roof. | General Revenue - (SGST) | 60000 | 537801.79 | 2019-10-08 17:00 | 60% | 0% | 72328.7 | 66520.98 | 398952.11
20 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Construction costs Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | General Revenue - (SGST) | 25000 | 581686.44 | 2020-01-17 17:00 | 100% | 0% | 0 | 7633.08 | 574053.36
21 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Planning and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | General Revenue - (SGST) | 153638.9715 | 169571.94 | 2021-12-30 17:00 | 60% | 0% | 4336 | 63487.66 | 101748.28
22 | 117260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | General Revenue - (SGST) | 73704.4065 | 43162.99 | 2018-03-09 17:00 | 100% | 100% | 0.01 | 39460.25 | 3702.73
23 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | General Revenue - (SGST) | 25000 | 26367.35 | 2020-08-17 17:00 | 95% | 0% | 8311 | 11289.08 | 6767.27
24 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Planning and design costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | General Revenue - (SGST) | 68405.427 | 71608.18 | 2023-02-03 | 60% | 0% | 0 | 10846.66 | 60761.52
25 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | General Revenue - (SGST) | 50000 | 27475.91 | 2019-04-03 | 100% | 0% | 8998.79 | 15696.74 | 2780.38
26 | 118102 | Bastrop SP - Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilization of shoreline adjacent to Cabins #1 and #12. | General Revenue - (SGST) | 57765.0675 | 143706.71 | 2018-01-11 17:00 | 100% | 100% | -7.1054e-15 | 139933.43 | 3773.28
27 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | General Revenue - (SGST) | 325000 | 172457.9 | 2018-09-11 | 100% | 100% | 72083.37 | 86832.64 | 13541.89
28 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace two obsolete restrooms with one large restroom complex. The scope of work includes a new forty-four fixture count restroom facility, five new host sites, all associated site work, utilities, parking, and the hazmat removal and demolition of the existing restroom. | General Revenue - (SGST) | 396567.447 | 228414.42 | 2018-10-10 17:00 | 100% | 62% | 20395.39 | 117064.26 | 90954.77
29 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | General Revenue - (SGST) | 25000 | 73554.88 | 2019-08-05 17:00 | 100% | 0% | 49775 | 14913.37 | 8866.51
30 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | General Revenue - (SGST) | 224748.543 | 235194.64 | 2018-10-17 17:00 | 100% | 93% | 38155.62 | 103085.36 | 93953.66
31 | 115356 | Choke Canyon State Park (South Shore Unit) - Boat Ramp 358 Recreation Rd 8 Calliham, TX 78007 (Live Oak County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 52419.699 | 35907.79 | 2018-03-05 17:00 | 100% | 100% | 1.819e-12 | 29799.88 | 6107.91
32 | 115389 | Fort Parker State Park - Boat Ramp 194 Park Rd 28 Mexia, Tx 76667 (Limestone County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 130000 | 58860.17 | 2018-08-17 | 100% | 100% | 3.638e-12 | 58860.17 | 0
33 | 116036 | Inks Lake State Park - Boat Ramp 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. (Project on Hold), TPWD did not receive a qualified construction bid in FY17 so funds for the project were lost due to lack of UB authority. | General Revenue - (SGST) | 0 | 216529.53 | 2019-05-06 17:00 | 100% | 5% | 95532.13 | 6661.97 | 114335.43
34 | 117036 | Ray Roberts Lake SP - Isle du Bois Unit - Boat Ramp 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 25000 | 2553.86 | 2018-06-29 | 100% | 100% | 0 | 2553.86 | 0
35 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 327367.1595 | 260192.91 | 2019-01-09 17:00 | 100% | 72% | 36762.59 | 114003.63 | 109426.69
36 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Advance planning costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | General Revenue - (SGST) | 25000 | 50000 | 2023-06-14 17:00 | 0% | 0% | 0 | 0 | 50000
37 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Construction costs Planning and design costs to install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | General Revenue - (SGST) | 25000 | 443240.4 | 2019-12-30 17:00 | 60% | 0% | 133011.25 | 2616.76 | 307612.39
38 | 118450 | Buescher SP - Boundary Fence Replacement - Fire Recovery 100 Park Road 1E Smithville, TX 78957-0075 (Bastrop County) | Replace approximately 7.5 miles of boundary fence around Buescher State Park and along Park Road 1-C, a majority of which sustained significant damage or was totally destroyed in a wildfire that began mid October 2015. | General Revenue - (SGST) | 150000 | 33223.87 | 2018-10-05 17:00 | 100% | 100% | 7.3275e-14 | 24004.04 | 9219.83
39 | 118414 | Lake Whitney SP - Camp Loop Restroom - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Restore Restroom #5 at Area E's interior finishes and critical structural components prior to re-opening the facility which was damaged in the 2016 Flood. | General Revenue - (SGST) | 49072.647 | 38385.79 | 2018-05-30 | 100% | 100% | -1.1369e-13 | 28046.24 | 10339.55
40 | 137395 | McKinney Falls SP - Restroom #4 Upper Falls North - Flood Recovery 5808 McKinney Falls Pkwy Austin, TX 78744 (Travis County) | Repair interior and exterior finishes damaged by the flood. Work will also address major mechanical, electrical and plumbing systems needed to restore full function of the restroom facility. | General Revenue - (SGST) | 25000 | 10000 | 2017-11-15 17:00 | 100% | 100% | 0 | 0 | 10000
41 | 128233 | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Pressure wash and repaint elevated water tank per TCEQ regulations. | General Revenue - (SGST) | 70000 | 22600.3 | 2018-09-14 | 100% | 100% | -1.7764e-15 | 22600.3 | 0
42 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | General Revenue - (SGST) | 236087.121 | 0 | 2018-04-17 10:00 | 100% | 100% | 0 | 0 | 0
43 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | General Revenue - (SGST) | 452827.5105 | 218822.81 | 2018-10-10 17:00 | 100% | 95% | 41285.3 | 143734.84 | 33802.67
44 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | General Revenue - (SGST) | 50000 | 0 | 2018-01-17 17:00 | 100% | 100% | 0 | 0 | 0
45 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | General Revenue - (SGST) | 20400 | 34138.78 | 2018-08-14 17:00 | 100% | 100% | 26129.77 | 4657.03 | 3351.98
46 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | General Revenue - (SGST) | 63367.2375 | 37670.79 | 2019-01-30 12:00 | 100% | 85% | 25279.95 | 2787.56 | 9603.28
47 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | General Revenue - (SGST) | 97679.52 | 131500 | 2019-02-13 17:00 | 100% | 87% | 258.28 | 6334.65 | 124907.07
48 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | General Revenue - (SGST) | 125000 | 125000 | 2019-04-22 17:00 | 100% | 55% | 37105.03 | 85801.41 | 2093.56
49 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | General Revenue - (SGST) | 317000 | 400000 | 2020-01-20 17:00 | 60% | 0% | 0 | 0 | 400000
50 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Planning and design cost for replacing the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | General Revenue - (SGST) | 68673.9555 | 47557.96 | 2023-09-04 12:00 | 60% | 0% | 0 | 11629.65 | 35928.31
51 | 118540 | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. | General Revenue - (SGST) | 250000 | 161570.85 | 2022-09-29 | 30% | 0% | 4.6185e-14 | 48673.03 | 112897.82
52 | 126107 | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | General Revenue - (SGST) | 10000 | 115805.64 | 2019-10-01 | 30% | 0% | 96887 | 6023.88 | 12894.76
53 | 115897 | Palo Duro Canyon SP - Repairs to Juniper Camp Loop 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Repairs to existing facilities and address storm water drainage issues around the buildings. | General Revenue - (SGST) | 15000 | 0 | 2017-10-13 | 100% | 100% | 0 | 0 | 0
54 | 115900 | Caddo Lake SP - Restroom Replacement 245 Park Rd 2 Karnack, TX (Harrison county) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 150000 | 159302.38 | 2018-11-17 17:00 | 100% | 95% | 2956.17 | 148274.14 | 8072.07
55 | 117585 | Statewide - Unspecified Radio Tower Assessments | Perform repairs on the 35 remotely-located, active TPWD radio tower sites, towers, and building structures supporting the radio equipment. Repairs will maintain Federal Communications Commission compliance and will meet obligations to maintain the towers and sites as part of lease agreements. | General Revenue - (SGST) | 77399 | 50771.05 | 2018-06-25 17:00 | 100% | 100% | 2525.11 | 15557.8 | 32688.14
56 | 128106 | Palmetto SP - Group Camp Area Erosion Control 78 Park Road 11 South Gonzales, TX 78629 (Gonzalez County) | Planning and assessment needed to prepare a Preliminary Engineering Report (PER) of riverbank erosion and stabilization recommendations and final repairs below the Group Camp Area. Planning and Design will be funded with 18/19 funds. | General Revenue - (SGST) | 25000 | 25000 | 2022-10-17 17:00 | 30% | 0% | 25000 | 0 | 0
57 | 128197 | Galveston Island SP - Repair Historical Residences 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Repairs and upgrades to the historic Stewart House and Ranch House. | General Revenue - (SGST) | 11625 | 0 | 2018-05-17 17:00 | 100% | 100% | 0 | 0 | 0
58 | 132416 | Hill Country SNA - Water System Replacement and Distribution 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Replace existing water facilities with a new water distribution network. Add a water treatment system to the main existing well, creating a Public Water System. | General Revenue - (SGST) | 30000 | 0 | 2019-01-30 17:00 | 100% | 95% | 0 | 0 | 0
59 | 134236 | Garner SP - Wastewater Treatment Plant Replacement US 83 N Concan, TX 78838 (Uvalde County) | Replace the undersized, leaking wastewater treatment plant with a modernized and efficient system. | General Revenue - (SGST) | 25000 | 25851.92 | 2017-05-30 17:00 | 100% | 100% | 0 | 5578.51 | 20273.41
60 | 137357 | Balmorhea SP - Repair Motel Roofs and Replace Laundry Facility 9207 H. 17S Toyahvale, TX (Reeves County) | Replace the CCC motel building's damaged clay tile roof, and repair critical structural, mechanical, electrical and plumbing systems concealed in the attic space. | General Revenue - (SGST) | 250000 | 0 | 2019-05-01 | 100% | 76% | 0 | 0 | 0
61 | 110005 | Bastrop SP - CCC Pool Repairs 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning, Design and Repairs to the CCC Pool water treatment, pumping and distribution system. Project will assess overall leaks within the pool's aging pumping/piping system to include the overall pool liner structure as necessary. | General Revenue - (SGST) | 0 | 702950 | 2018-09-07 | 100% | 100% | 4898.99 | 673496.77 | 24554.24
62 | 1110166 | Wyler Aerial Tramway - Facility Upgrades 1700 McKinley Drive, El Paso, TX 79931 (El Paso County) | Replace obsolete FINCOR unit, cabin controls and PLC controller. Tramway's original controls are past their intended service and recommended for replacement by the annual inspection. | General Revenue - (SGST) | 0 | 250028.28 | 2021-02-19 | 5% | 0% | 6018.58 | 17671.4 | 226338.3
63 | 118517 | Lake Arrowhead SP - Wastewater Collection and Treatment System Repairs 229 Park Road 63, Wichita Falls, TX 76310 (Clay County) | Repairs to the Wastewater treatment plant and collection system; including full TCEQ Certifications and permitting of the plant. | General Revenue - (SGST) | 0 | 1255021.13 | 2020-08-14 17:00 | 30% | 0% | 0 | 19164.26 | 1235856.87
64 | 1110100 | Big Bend Ranch SP - Building Renovations HCR 67 Box 33 Marfa, TX 79843 (Brewster and Presidio County) | Planning and Design costs to renovate interior, exterior and utilities for the Big House and Superintendent's Residence. | General Revenue - (SGST) | 0 | 182208.56 | 2021-01-15 | 10% | 0% | 0 | 1829.62 | 180378.94
65 | 190078 | Battleship Texas SHP - Structural Repairs(leaks) 3523 Independence Parkway S LaPorte, TX,77571 (Harris County) | Emergency leak repairs | General Revenue - (SGST) | 0 | 111973.09 | N/A | 100% | 82% | 46496 | 65477.09 | 0
66 | 1110156 | Balmorhea SP -Wastewater system assessment and repairs 9207 H. 17S Toyahvale, TX (Reeves County) | Wastewater system assessment | General Revenue - (SGST) | 0 | 253356.7 | 2021-10-26 | 10% | 0% | 145935.16 | 15541.87 | 91879.67
67 | 1110283 | Balmorhea SP - Emergency pool repairs 9207 H. 17S Toyahvale, TX (Reeves County) | Emergency pool repairs | General Revenue - (SGST) | 0 | 1692467.42 | 2019-01-29 | 100% | 42% | 1119148.72 | 45293.75 | 528024.95
68 | 1910077 | Tyler SP - Demolish CCC Residence 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Demolish CCC Residence | General Revenue - (SGST) | 0 | 121000 | 2019-12-21 | N/A | 0% | 0 | 27360 | 93640
69 | NEW - 114525 | Palo Duro Canyon SP - Water Supply Utility Upgrades 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Construction of a new water treatment plant and modifications to the distribution piping on the canyon floor, raw water storage facilities, and installation of new storage tanks and pumps. | General Revenue - (SGST) | 0 | 1031960.49 | TBD | 100% | 0% | 0 | 0 | 1031960.5 | *
70 | NEW - 1110160 | Balmorhea SP - Manager's Residence Roof Replacement 9207 H. 17S Toyahvale, TX (Reeves County) | Remove and replace the tile roof on the manager's residence. The roof currently has significant leaks. | General Revenue - (SGST) | 0 | 275500 | 2020-07-09 | 60% | 0% | 75445 | 19.23 | 200035.77 | *
71 | 116769 | Bastrop SP - Dam Replacement and Road Repairs 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | 2015 and 2016 Weather Related (State Parks) - Replace the breached dam and repair roads due to the 2015 memorial day flooding. | General Revenue - (SGST) | 6274215 | 6289318.54 | 2021-09-20 | 60% | 0% | 70117.1 | 17814.28 | 6201387.16
72 | 128269 | Cedar Hill SP - Facility Repairs - Flood Recovery 1570 FM 1382 Cedar Hill, TX 75104 (Dallas County) | 2015 and 2016 Weather Related (State Parks) - Repair the Day Use Swim Beach, replacement of multiple restrooms, a pavilion and overall shoreline reinforcement which were damaged by the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 17031700 | 15560781.8 | 2020-09-25 | 60% | 0% | 445141.53 | 66131.73 | 15049508.54
73 | 128301 | Lake Somerville SP - Birch Creek Unit - Facility Repairs - Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | 2015 and 2016 Weather Related (State Parks) - Construction costs to repair facilities in the Birch Creek Unit day use area. Planning and Design of Repairs to the Cedar Elm camping area, the Old Hickory and Bucktail bridge(s) which were damaged by multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 2481400 | 861384.69 | 2020-08-07 | 60% | 0% | 123750 | 38857.04 | 698777.65
74 | 128322 | Lake Somerville SP - Nails Creek Unit - Facility Repairs - Flood Recovery 6280 FM 180 Ledbetter, TX 78946-9512 (Lee County) | 2015 and 2016 Weather Related (State Parks) - Construction costs to restore public access facilities (Fish Cleaning Stations) in the day use area. Planning and Design of repairs to the Cedar Creek camping area, and the Boat Ramp camping area which were damaged by the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 1632000 | 178437.77 | 2019-11-14 | 100% | 0% | 32605 | 6677.1 | 139155.67
75 | 128323 | Lake Somerville SP - Trailway - Bridge Repairs- Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design of repairs to multiple bridges, culverts, and access ways along the Somerville Trailway that were damaged by multiple flooding events in 2015 and 2016. (On Hold) | General Revenue - (SGST) | 157950 | 11764.24 | 2020-06-01 | 100% | 0% | 0 | 3099.68 | 8664.56
76 | 118477 | Lake Whitney SP - Erosion Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design of erosion damage, a boat ramp, and address soil stabilization that resulted from the multiple 2016 flood events. | General Revenue - (SGST) | 1660500 | 63107.25 | 2021-05-17 | 60% | 0% | 0 | 8800.23 | 54307.02
77 | 118476 | Lake Whitney SP - Facilities Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design to Repair of limited facilities (restroom #3, restroom #4, and several shade shelter replacements) at key areas damaged during multiple 2016 flood events. Planning and design for the remainder of the impacted areas that include the Towash shelter loop, day use area, the group camp & dinning hall, and all shade shelters. | General Revenue - (SGST) | 4286250 | 64355.66 | 2018-10-09 | 100% | 100% | 0 | 41720.1 | 22635.56
78 | TBD | Mother Neff SP - Restroom and CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | 2015 and 2016 Weather Related (State Parks) - Replace day use restroom with a new CXT and stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. (On Hold) | General Revenue - (SGST) | 977000 | 0 | N/A | 100% | 0% | 0 | 0 | 0
79 | 128302 | Ray Roberts Lake SP - Complex Wide- Site Repairs - Flood Recovery 100 PW 4137 Pilot Point, TX 76258-8944 (Denton County) | 2015 and 2016 Weather Related (State Parks) - Repair concrete walks, shoreline stabilization, playground areas, and the green belt trail which was damaged during the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 8729250 | 3457618.57 | 2019-12-23 | 100% | 0% | 188566.55 | 32251.02 | 3236801
80 | TBD | Statewide - Unspecified State Park Flood Recovery | 2015 and 2016 Weather Related (State Parks)- Hazardous tree removal from the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 300000 | 0 | N/A | N/A | 0% | 0 | 0 | 0
81 | 1910092 | Statewide - Unspecified State Park Flood Recovery | Hazardous Tree Removal for State Parks Region 5 - Waco Regioal Office | General Revenue - (SGST) | 0 | 30000 | N/A | N/A | 0% | 0 | 0 | 30000
82 | 1910246 | Statewide - Unspecified State Park Flood Recovery | Hazardous Tree Removal for State Parks Region 6 - Cedar Hill | General Revenue - (SGST) | 0 | 41000 | N/A | N/A | 46% | 0 | 18830 | 22170
83 | NEW- 1910247 | Statewide - Unspecified State Park Flood Recovery | Hazardous Tree Removal for State Parks Region 6 - Ray Roberts Isle Du Bois | General Revenue - (SGST) | 0 | 108000 | N/A | N/A | 34.9% | 0 | 37695 | 70305 | *
84 | 128406 | Stephen F Austin SHS - Facility Repairs - Flood Recovery 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | 2015 and 2016 Weather Related (State Parks) - Repair mini cabin(s), screen shelter(s), group dining hall(s), staff residence, the Bullinger Creek bunkhouse, the Nature Center, and multiple restrooms that were damaged during the 2016 flood. | General Revenue - (SGST) | 4164700 | 4092501.01 | 2020-04-23 | 60% | 0% | 66904 | 27393 | 3998204.01
85 | TBD | Statewide - Unspecified State Park Harvey Recovery | HARVEY - Emergency funding reserved and redirected to address state park 2017 Harvey damages. Now that comprehensive damage assessments have been completed, individual projects (by site) are now set up. | General Revenue - (SGST) | 813600 | 15277 | N/A | N/A | 0% | 0 | 0 | 15277
86 | 1210250 | Brazos Bend SP - Facility Repairs - Harvey Damage Recovery | HARVEY - Planning and Design to repair levee | General Revenue - (SGST) | 0 | 317723.87 | 2022-07-21 | 10% | 0% | 288056.4 | 2911.86 | 26755.61
87 | 118686 | Buescher SP - CCC Dam Spillway Restoration - Harvey Recovery 100 Park Road 1E, Smithville, TX 78957 | HARVEY - Planning and Design/Interim repairs to the CCC Dam Spillway damaged during the 2017 hurricane event. Significant erosion occurred on downstream slope of the Dam spillway threatening the Safety of the Dam. Project will assess damages, prepare construction documents and repair the damaged structure to meet TCEQ regulations. | General Revenue - (SGST) | 0 | 1253077.75 | 2021-05-18 12:00 | 30% | 0% | 66296.21 | 156554.63 | 1030226.91
88 | 1210062 | Goliad SP - Facility Repairs - Harvey Damage Recovery 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | HARVEY - Repair/renovate maintenance building | General Revenue - (SGST) | 0 | 303911.27 | 2019-12-24 | 10% | 15% | 41831.83 | 44860.37 | 217219.07
89 | 1210094 | Goose Island SP - Facility Repairs - Harvey Recover 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Construction costs to repair all Park Operational facilities, utility systems, Wooded Area Camping Loop, CCC Recreation Hall, Boat Ramp, Beach Side Camping facilities, Fishing pier, Wildlife viewing overlook, Day-use area, Beach Camping area/boardwalk, and the Big Tree area. Project will prepare construction documents and repair damaged structures to include mold remediation and replacement of damaged interior finishes. | General Revenue - (SGST) | 0 | 1805031.72 | 2020-07-22 | 60% | 0% | 157732.46 | 97890.36 | 1549408.9
90 | 128684 | Goose Island SP - Facility Repairs - Harvey Recovery 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Roofing repairs to multiple facilities (Park HQ, Maintenance Shop, and Restrooms) throughout the park damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior needed to prevent additional water intrusion damage to interior finishes. | General Revenue - (SGST) | 0 | 123830.23 | N/A | N/A | 100% | 6.8212e-13 | 123830.23 | 0
91 | 128679 | Goose Island SP - Facility Repairs - Harvey Recovery 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Repair residence roof damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior necessary to prevent additional water intrusion damage including minimal interior finishes. | General Revenue - (SGST) | 0 | 58714.25 | N/A | N/A | 100% | 0 | 58714.25 | 0
92 | 128702 | Mustang Island SP - Facility Repairs - Harvey Recovery 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | HARVEY - Construction costs to repair all Park Operational facilities (Headquarters, Residences and Maintenance yard), site utility systems, RV Camping Loop, Day-use and Beach area services. Project will prepare construction documents and repair damaged structures to include mold remediation and replacement of damaged interior finishes. | General Revenue - (SGST) | 0 | 981859.9 | 2020-06-25 17:00 | 30% | 0% | 160711.47 | 75053.64 | 746094.79
93 | 128677 | Mustang Island SP - Facility Repairs - Harvey Recovery 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | HARVEY - Roofing repairs to both Residences damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior necessary to prevent additional water intrusion damage to interior finishes. | General Revenue - (SGST) | 0 | 127375.29 | N/A | N/A | 100% | 4.6896e-13 | 127375.29 | 0
94 | 128676 | Rockport Regional Office - Facility Repairs - Harvey Recovery 715 Hwy 35 S, Rockport, TX 78382 (Aransas County) | HARVEY - Repairs to the Headquarters facility damaged during the 2017 hurricane event. Project will assess overall building damage, prepare construction documents and repair all interior damages including mold remediation and replacement of interior finishes. Project includes replacement of an adjacent support office building and associated utility connections. All phases - Planning & Design and Construction - will be funded with 18/19 funds consisting of actual construction activities to include all cost associated with the Bidding, Construction and Project Closeout phases. | General Revenue - (SGST) | 0 | 645860.02 | 2018-10-31 17:00 | 100% | 98% | 48589.48 | 536777.11 | 60493.43
95 | 128693 | Sheldon Lake SP - Facility Repairs - Harvey Recovery 14320 Garrett Road, Houston, TX 77049 (Harris County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Construction costs to repair the Park Headquarters, Residence, Acorn Annex and Wellhead. Project will perform interior repairs to include mold remediation and replacement of damaged interior finishes. Construction - will be funded with 18/19 funds. | General Revenue - (SGST) | 0 | 194594.23 | 2018-04-04 | N/A | 100% | -1.819e-12 | 194594.23 | 0
96 | 118692 | Statewide Radio Towers - Facility Repairs - Harvey Recovery | HARVEY - Emergency repairs to two radio towers damaged during the 2017 hurricane event. Project assessed towers and equipment damages providing immediate repairs necessary to restore life safety communications. | General Revenue - (SGST) | 0 | 150000 | 2018-04-03 17:00 | N/A | 100% | 0 | 123423.08 | 26576.92
97 | 190062 | Stephen F. Austin SP - Facility Repairs - Harvey Recovery San Felipe, TX 77473 (Austin County) | HARVEY - State Park Managed Harvey Repairs | General Revenue - (SGST) | 0 | 5416.8 | N/A | N/A | 100% | 0 | 5396.1 | 20.7
98 | 128683 | Stephen F. Austin SP - Facility Repairs - Harvey Recovery San Felipe, TX 77473 (Austin County) | HARVEY - Repairs to the Park Headquarters and Maintenance complex damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exteriors necessary to prevent additional water intrusion damage including minimal interior finishes. Overall restoration is incorporated into the prior Weather Related event. | General Revenue - (SGST) | 0 | 100848.79 | 2018-03-01 | N/A | 100% | -1.4552e-11 | 97046.39 | 3802.4
99 | 128695 | Village Creek SP - Facility Repairs - Harvey Recovery 8854 Park Road 74, Lumberton, TX 77657 (Hardin County) | HARVEY - Repairs to the Cabin, Pavilion, and Pedestrian bridge damaged during the 2017 hurricane event. Project will assess damages, provide a structural Preliminary Engineering Report for the Cabin, prepare construction documents and repair damaged structures. | General Revenue - (SGST) | 0 | 339723.43 | 2019-12-18 12:00 | 30% | 0% | 45024.8 | 38765.92 | 255932.71
100 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | General Revenue - (SGST) | 41338.35 | 8618.91 | 2017-12-06 | 100% | 100% | 0 | 8618.91 | 0
101 | 118669 | Austin Headquarters Complex - Multiple HVAC System Upgrades 4200 Smith School Road Austin, TX 78744 (Travis County) | Planning and design costs to upgrade and/or replace aging HVAC system(s) at the Austin HQ facilities. | General Revenue - (SGST) | 29507.25 | 39000.79 | 2018-11-02 | 100% | 0% | 1.1369e-13 | 9360.58 | 29640.21
102 | 117417 | Austin Headquarters Complex - Construct Building D Roof Access 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | General Revenue - (SGST) | 0 | 282 | 2017-07-26 | 100% | 100% | 0 | 282 | 0
103 | TBD | Austin Headquarters Complex - Unspecified Emergency Repairs 4200 Smith School Road Austin, TX 78744 (Travis County) | Funding reserved to address Austin Headquarter Complex emergency repairs. | General Revenue Dedicated - (Fund9) | 300000 | 0 | N/A | N/A | 0% | 0 | 0 | 0
104 | TBD | Statewide - Unspecified Fund9 Division Flood Recovery | 2015 and 2016 Weather Related (Fund 9) - Various WMA repairs resulting from the 2015 and 2016 floods included roads, fencing, and lake dams at Guadalupe Delta WMA, Kerr WMA, Gus Engeling WMA, and Fawcett WMA. | General Revenue Dedicated - (Fund9) | 677100 | 1180233 | NA | N/A | 0% | 0 | 0 | 1180233
105 | 127570 | Brownsville Field Station - Replace Storage Building 95 Fish Hatchery Road, Brownsville, TX 78520 (Cameron County) | Construct building addition to the Main Boat and Truck storage facility to increase secure storage capacity from five to twelve vehicles. | General Revenue Dedicated - (SWFS) | 150000 | 61047.37 | 2018-11-13 17:00 | 100% | 66% | 15566.85 | 39191.19 | 6289.33
106 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | General Revenue Dedicated - (Fund9) | 395000 | 122295.21 | 2019-01-11 17:00 | 100% | 73% | 13576.99 | 32260.67 | 76457.55
107 | 128535 | CCA Marine Development Center - Repairs to Ponds 1-10 Harvest Kettles 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Repair damaged concrete harvest kettles at Ponds 1-10. These ten ponds are original to the site and are in a stage of decay. Repairs would include structural concrete work and efforts to minimize existing pond leaks. | General Revenue Dedicated - (SWFS) | 20000 | 1163.81 | 2018-04-05 | 100% | 100% | 0 | 1163.81 | 0
108 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | General Revenue Dedicated - (SWFS) | 72000 | 62862.67 | 2018-07-13 17:00 | 100% | 100% | 5.4605e-12 | 52176.05 | 10686.62
109 | 125873 | Dickinson Marine Lab - Roof Replacement 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Replace deteriorated office building roof. | General Revenue Dedicated - (Fund9) | 61000 | 218020.08 | 2019-01-10 17:00 | 100% | 98% | 34479.92 | 126420.35 | 57119.81
110 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and Design for the renovation and/or replacement of facility buildings, utilities, ponds and infrastructure. In addition to the new hatchery design, project includes the planning and design for a new Seawater Intake System to feed the site's fish rearing ponds. | General Revenue Dedicated - (Fund9) | 325000 | 50162.27 | 2023-05-10 | 30% | 0% | -2.6645e-15 | 25830.14 | 24332.13
111 | 128533 | Perry R Bass Marine Research Station - Replace Residences HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Construction administration to complete (2) residence replacements. | General Revenue Dedicated - (Fund9) | 55000 | 21227.58 | 2018-07-12 17:00 | 100% | 100% | 0 | 9365.02 | 11862.56
112 | 127861 | Rockport Annex - Boat Maintenance Shop Repairs 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | Renovate existing and install new wall panels and repair roof leaks. | General Revenue Dedicated - (SWFS) | 30000 | 74548.75 | 2018-11-27 17:00 | 100% | 62% | 25145.58 | 16497.11 | 32906.06
113 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, TX 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife and human intrusion. | General Revenue Dedicated - (Fund9) | 75000 | 41519.43 | 2018-10-25 17:00 | 100% | 100% | 462.62 | 33132.02 | 7924.79
114 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | General Revenue Dedicated - (Fund9) | 150000 | 87231 | 2018-11-20 17:00 | 100% | 95% | 1286.9 | 74524.41 | 11419.69
115 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | General Revenue Dedicated - (Fund9) | 28000 | 1554.66 | 2017-10-17 | 100% | 100% | 0 | 1554.66 | 0
116 | 1210307 | Sea Center Texas - Pond Electrical System Improvements - Phase II 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Modify pond lighting and electrical. | General Revenue Dedicated - (Fund9) | 0 | 40176 | 2019-12-01 | 10% | 0% | 0 | 0 | 40176
117 | 128687 | CCA Marine Development Center - Facility Repairs - Harvey Recovery 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Project will replace damaged roofing at the Bass Bldg. and Shop bldg. | General Revenue Dedicated - (Fund9) | 0 | 194255.06 | 2018-06-27 17:00 | 100% | 100% | 1.8189e-11 | 173437.45 | 20817.61
118 | 190072 | CCA Marine Development Center - Facility Repairs - Harvey Recovery 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (SWFS) | 0 | 3359.38 | N/A | N/A | 100% | 0 | 3356.97 | 2.41
119 | 190073 | Dickenson Marine Lab - Facility Repairs - Harvey Recovery 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 27500 | N/A | N/A | 100% | 0 | 27500 | 0
120 | 128696 | Dickinson Marine Lab - Facility Repairs - Harvey Recovery 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Scope of work includes mold remediation and interior demolition and repairs at the warehouse and office building. | General Revenue Dedicated - (Fund9) | 0 | 231102.29 | 2019-01-30 17:00 | 100% | 92% | 50120.65 | 141778.86 | 39202.78
121 | 190074 | Rockport Annex - Facility Repairs - Harvey Recovery 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 14444 | N/A | N/A | 95% | 0 | 14444 | 0
122 | 128685 | Rockport Boat Maintenance Shop - Facility Repairs - Harvey Recovery Rockport, TX 78382 (Aransas County) | HARVEY -Repairs to facilities damaged during the 2017 hurricane event. Project will repair damage structures. | General Revenue Dedicated - (Fund9) | 0 | 190000.43 | 2019-01-01 | N/A | 100% | 9069 | 146797.99 | 34133.44
123 | 190075 | Rockport Harbor Building - Facility Repairs - Harvey Recovery 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 2795 | N/A | N/A | 100% | 0 | 2795 | 0
124 | 190070 | Matagorda Island WMA - Facility Repairs - Harvey Recovery Port O'Connor, TX 77982 (Calhoun County) | HARVEY - Cost to temporarily shore up building that was damaged during Harvey. | General Revenue Dedicated - (Fund9) | 0 | 11490 | N/A | N/A | 100% | 0 | 11490 | 0
125 | 128694 | JD Murphree WMA - Facility Repairs - Harvey Recovery Park Road 10, Port Arthur, TX 77640 (Jefferson County) | HARVEY - Repairs to the Main Office, Biologist Office and Bunkhouse at the WMA damaged during the 2017 hurricane event. Project includes treating internal water/mold damage and the overall restoration of their interior finishes. | General Revenue Dedicated - (Fund9) | 0 | 131923.72 | 2019-02-01 17:00 | 100% | 60% | 7809 | 120338.3 | 3776.42
126 | 128697 | Guadalupe Delta WMA - Facility Repairs - Harvey Recovery Bay City, TX 77414 (Calhoun/Refugio/Victoria Counties) | HARVEY - Repairs to the Bunkhouse at the WMA damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 57328.84 | 2018-08-09 17:00 | N/A | 100% | 0 | 50541.79 | 6787.05
127 | 126484 | The Tyler Nature Center - Regional Office Replacement 11942 FM 848, Tyler, TX 75707 (Smith County) | Construction for phase 1 of the multi-regional complex. The current office complex supports business operations for 5 agency divisions and the existing facilities inadequately support business operations. Phase 1 will address the agency staff currently office in the 1950's Quail Hatchery Building. | General Revenue Dedicated - (Fund9) | 1539000 | 700124 | 2021-08-16 | 60% | 0% | 0 | 0 | 700124
128 | 127573 | Gus Engeling WMA.Fence right of way clearing | Fence right of way clearing | General Revenue Dedicated - (Fund9) | 0 | 735.72 | 2018-04-23 | 100% | 100% | 0 | 735.72 | 0
129 | 1110307 | The Game Warden Training Center - Fire Sprinklers 4363 FM1047, Hamilton, TX 76531 (Hamilton County) | Install building fire sprinkler system in cadet dorms as recommended by the State Firm Marshall. | General Revenue Dedicated - (Fund9) | 0 | 350000 | 2019-12-01 | 10% | 0% | 23255 | 158.66 | 326586.34
130 | 123377 | AE Wood Fish Hatchery - Incubation System 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Renovate portions of the hatchery process systems including tanks, troughs, distribution piping, and valving and System Control and Data Acquisition (SCADA) system. | General Revenue Dedicated - (FWFS) | 125000 | 423668.08 | 2018-12-28 17:00 | 100% | 95% | 58420.02 | 348083.93 | 17164.13
131 | 1210289 | AE Wood Fish Hatchery - HVAC Replacements 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Design and construction to replace the HVAC system at the Lab Building. | General Revenue Dedicated - (FWFS) | 0 | 351718.04 | 2020-12-01 | 30% | 0% | 64485 | 11862.52 | 275370.52
132 | 128562 | AE Wood Fish Hatchery - Rivers Studies Building 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Design and construction for site work, site utilities, building foundation and landscaping and the installation of a new modular office for the Rivers Studies staff | General Revenue Dedicated - (FWFS) | 75000 | 396699.78 | 2019-06-26 17:00 | 100% | 0% | 255162.78 | 57655.97 | 83881.03
133 | 128632 | Dundee Fish Hatchery - Ozone System 16824 FM1180, Electra, TX 76360 (Archer County) | Construction of an ozone disinfection system to control toxic golden algae present in the water source. In order to sustain hatchery operation during intermittent or persistent drought conditions, the project would also design and construct a system to collect the effluent from the six hatchery discharge points and pump it back to Lake Diversion to minimize the water lost from the reservoir as a result of hatchery operations. | General Revenue Dedicated - (FWFS) | 4180000 | 1740901 | 2021-02-18 | 95% | 0% | -8.4377e-15 | 7918.4 | 1732982.6
134 | 1110061 | Dundee Fish Hatchery - Pump Repairs 16824 FM1180, Electra, TX 76360 (Archer County) | Project will develop a Preliminary Engineering Report with follow on Planning and Design of an effluent water pump back system that will collect wastewater from fish rearing ponds and pump it back into Lake Diversion. Additional Construction cost may be required at the end of 19 into 20/21. | General Revenue Dedicated - (FWFS) | 0 | 400000 | 2021-09-17 | 30% | 0% | 352936.58 | 32703.5 | 14359.92 | *
135 | 128314 | East Texas Fish Hatchery - Chemical Storage Unit 900 County Road 218, Brookeland, TX 75931 (Jasper County) | Construct concrete slab and install modular storage unit | General Revenue Dedicated - (FWFS) | 25000 | 0 | 2017-08-02 | 100% | 100% | 0 | 0 | 0
136 | 1210288 | East Texas Fish Hatchery - Replace/Repair Pumps 900 County Road 218, Brookeland, TX 75931 (Jasper County) | Replace damaged pump drive shafts on Vertical Turbine Pumps; the existing drive shafts will be machined and kept as shelf stock for future repairs. | General Revenue Dedicated - (FWFS) | 0 | 171599.58 | 2020-01-22 | 10% | 0% | 0 | 819.87 | 170779.71
137 | 127144 | Mathis Office - Design Office Replacement 9892 FM 3377, Mathis, TX 78368 (San Patricio County) | Plan and Design efforts for an Inland Fisheries Field Office replacement. The new building will include offices and a vehicle/equipment shop. | General Revenue Dedicated - (FWFS) | 0 | 105000 | 2021-06-02 | 10% | 0% | 95054.56 | 7223 | 2722.44
138 | 127550 | Possum Kingdom Fish Hatchery - Hatchery Pond Renovation and Expansion 401 Red Bluff Rd, Graford, TX 76449 (Palo Pinto County) | Plan and Design of modern harvest kettles. Improvements will provide staff with greater efficiencies in harvesting fish and assist in reducing stress on fish during harvest. (Project On Hold) | General Revenue Dedicated - (FWFS) | 500000 | 0 | TBD | 100% | 0% | 0 | 0 | 0
139 | 118667 | Possum Kingdom Fish Hatchery - Ozone Chiller Replacement 401 Red Bluff Rd, Graford, TX 76449 (Palo Pinto County) | Replace the existing failing ozone system chiller unit. The system circulates chilled water used to cool ozonation equipment. | General Revenue Dedicated - (FWFS) | 10000 | 4178.08 | TBD | 100% | 100% | 0 | 4178.08 | 0
140 | NEW - 1210301 | Possum Kingdom Fish Hatchery - Micro Filtration System - 401 Red Bluff Rd, Graford, TX 76449 (Palo Pinto County) | Design and install micro-filtration system to remove Zebra Mussels and mitigate risk to the hatchery operations. | General Revenue Dedicated - (FWFS) | 0 | 1000000 | TBD | 10% | 0% | 302159 | 1513 | 696328 | *
141 | 117303 | Statewide - Inland Fisheries - Upgrade SCADA System | Upgrades to hatchery Supervisory Control and Data Acquisition (SCADA) systems for three (3) sites including A.E. Wood Fish Hatchery, Possum Kingdom Fish Hatchery and East Texas Fish Hatchery. | General Revenue Dedicated - (FWFS) | 30000 | 78069.83 | 2019-01-04 | 100% | 95% | 60877.99 | 10616.57 | 6575.27
142 | 116446 | Texas Freshwater Fisheries Center - Construct Effluent Re-Use System 5550 FM2495, Athens, TX 75752 (Henderson County) | Construct water infrastructure improvements. | General Revenue Dedicated - (FWFS) | 25000 | 2075.62 | TBD | 100% | 100% | 0 | 2075.62 | -7.276e-12
143 | 128235 | Texas Freshwater Fisheries Center - Replace Ozone Tower 5550 FM2495, Athens, TX 75752 (Henderson County) | Replace portions of the ozone injection system including the ozone contact columns and affected distribution piping and valving | General Revenue Dedicated - (FWFS) | 30000 | 39054.94 | 2018-09-10 17:00 | 100% | 100% | 0.01 | 30581.92 | 8473.01
144 | 1210282 | The Tyler Nature Center - Regional Office Replacement 11942 FM 848, Tyler, TX 75707 (Smith County) | Temporary office space needed for Inland Fisheries staff located in the Quail Building. | General Revenue Dedicated - (FWFS) | 0 | 287035.04 | 2019-02-15 | 100% | 43% | 50210.07 | 167748.09 | 69076.88
|  |  |  | Totals: | 66185665.1385 | 66185664.99 |  |  |  | 6297690.72 | 7994434.7 | 51893539.58

## TPWD Sup.
| Agency: | Texas Parks & Wildlife
| Date: | 2018-12-15
| Prepared by: | Infrastructure Division
Project Priority | Supplemental Information
4 | Goliad Waste Water Repairs - For FY18/19 work on this project will only include design. Construction anticipated to be performed in FY20/21. Construction funds being swept will be used to perform critical water system repairs at Palo Duro Canyon (see below).
69 | New Project - Palo Duro Canyon Water Supply. This is a bond funded project that has been in planning and design since 14/15. The project is now ready for construction, however, we need more funds than what was appropriated in FY14/15.
70 | New Project - Balmorhea SP Residence Roof Repairs. New emergency project resulting from significant roof leaks.
83 | New project to better identify and account for where the hazardous tree removal is occurring. Originally hazardous tree removal was generically called out on line 80.
134 | Dundee Fish Hatchery Pump Repairs - For FY18/19 work on this project will only include planning and design. Construction anticipated to be performed in FY20/21. Construction funds being swept to fund new emergency project at Possum Kingdom FH (see below).
140 | New Project - Possum Kingdom Micro-Filtration System. New emergency project to design and install a micro-filtration system at the Possum Kingdom Fish Hatchery to mitigate the risk of Zebra Mussel infestation impacting hatchery operations. The reservoir has recently been identified has being high risk for Zebra Muscle infestation. The current budget allocation of $1,000,000 is just an earmark guesstimate at this time; this will definitely change once Infrastructure has more time to work with consultants to finalize project deliverables.
KEY
1 - 70 | Grouping of - State Parks Deferred Maintenance Projects
71 - 84 | Grouping of - State Parks 2015 and 2016 Weather Related Program
85 - 99 | Grouping of - State Parks HARVEY projects
100 - 103 | Grouping of - Austin HQ Projects
104 - 129 | Grouping of - Fund 9 Coastal Fisheries, Wildlife, and Law Enforcement Projects
130 - 144 | Grouping of - Fund 9 Inland Fisheries Program

## TDCJ
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2018-12-14 | [9 empty] | 2018-12-14
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 03017005 | Jester III Unit, Richmond | Facility Repair: Convert TCI Factory to Sheltered Beds | Economic Stabilization Fund No. 0599 | 437400 | 437400 | 2018-10-29 | 100% | 100% | 207.03 | 396704.5 | 40488.47 | Yes
2 | 06717005 | Telford Unit, New Boston | Facility Repair: Convert TCI Factory to Sheltered Beds | Economic Stabilization Fund No. 0599 | 877300 | 629001.16 | 2018-07-09 | 100% | 100% | 0 | 629001.16 | 0 | Yes
3 | 12917002 | Young Unit, Dickinson | Facility Repair: Convert Surgical Suites to Sheltered Beds | Economic Stabilization Fund No. 0599 | 139700 | 139700 | 2018-05-07 | 100% | 100% | 0 | 53705.93 | 85994.07
4 | 10013001 | Lychner Unit, Humble | Security: Replace Intercom System | Economic Stabilization Fund No. 0599 | 134000 | 134000 | 2020-07-19 | 100% | 0% | 0 | 796.57 | 133203.43 | Yes
5 | 09115026 | Chasefield Unit, Beeville | Roofing: Replace Roof - Maintenance Building | Economic Stabilization Fund No. 0599 | 1000000 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | Yes
6 | 02214021 | Beto Unit, Tennessee Colony | Facility Repair: Renovate Vault & Replace Refrigeration System - Icehouse | Economic Stabilization Fund No. 0599 | 1000000 | 1000000 | 2020-02-01 | 100% | 0% | 0 | 1289.78 | 998710.22 | Yes
7 | 01215009 | Goree Unit, Huntsville | Facility Repair: Construct Enclosure - Intake Processing | Economic Stabilization Fund No. 0599 | 98900 | 98900 | 2019-03-29 | 100% | 2% | 8118.27 | 85850.43 | 4931.3
8 | 01313001 | Huntsville Unit, Huntsville | Roofing: Replace Roof and Repair North Wall - Infirmary Building | Economic Stabilization Fund No. 0599 | 153600 | 401500 | 2019-06-28 | 100% | 1% | 382264 | 1459.76 | 17776.24
9 | 04317001 | Kyle Unit, Kyle | Facility Repair: Replace Ceiling - Main Hallway & Kitchen | Economic Stabilization Fund No. 0599 | 52500 | 73300 | 2019-05-24 | 100% | 58% | 42009.75 | 28408.75 | 2881.5 | Yes
10 | 02710004 | Terrell Unit, Rosharon | Infrastructure: Replace Concrete Drive / Back Gate | Economic Stabilization Fund No. 0599 | 1600280 | 1680380 | 2019-06-28 | 100% | 66% | 518945.15 | 1065073.23 | 96361.62
11 | 07015010 | Neal Unit, Amarillo | Roofing: Replace Roof - Beef Processing Plant | Economic Stabilization Fund No. 0599 | 3015000 | 3814900 | 2019-08-23 | 100% | 1% | 3556977.25 | 76429.06 | 181493.69
12 | 06313004 | Duncan Unit, Diboll | Facility Repair: Replace Shower Stalls - Unit Wide | Economic Stabilization Fund No. 0599 | 140000 | 551300 | 2019-12-20 | 100% | 27% | 251814.6 | 154150.13 | 145335.27
13 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: Construct Elevated Storage Tank & Replace Ground Storage Tank | Economic Stabilization Fund No. 0599 | 6249400 | 0 | N/A | N/A | N/A | 0 | 0 | 0
14 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: Replace Water Lines - Distribution System & Replace Ground Water Storage | Economic Stabilization Fund No. 0599 | 5651409 | 5361100 | 2020-07-20 | 100% | 1% | 5306350.7 | 18308.44 | 36440.86
15 | 03708003 | Clements Unit, Amarillo | Safety: Repair/Replace Fire Line - Administrative Segregation | Economic Stabilization Fund No. 0599 | 474100 | 0 | N/A | N/A | N/A | 0 | 0 | 0
16 | 00613017 | Coffield Unit, Tennessee Colony | Facility Repair: Replace Flooring - Kitchen | Economic Stabilization Fund No. 0599 | 140000 | 1279.6 | N/A | N/A | N/A | 0 | 1279.6 | 0 | Yes
17 | 00615025 | Coffield Unit, Tennessee Colony | Facility Repair: Install Showers - Multiple Locations | Economic Stabilization Fund No. 0599 | 1000000 | 1000000 | 2020-06-01 | 100% | 0% | 0 | 0 | 1000000 | Yes
18 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: Correct Drainage Problems - Multiple Buildings | Economic Stabilization Fund No. 0599 | 435000 | 1196.43 | 2018-12-03 | 100% | N/A | 0 | 1196.43 | 0 | Yes
19 | 03312003 | Jester IV Unit, Richmond | Roofing: Replace Roof - Psychiatric Facility | Economic Stabilization Fund No. 0599 | 2000000 | 6569800 | 2019-07-15 | 100% | 1% | 6401506.95 | 11782.26 | 156510.79
20 | 02217005 | Beto Unit, Tennessee Colony | Infrastructure: Install Transformer - Substation | Economic Stabilization Fund No. 0599 | 1571400 | 1721080 | 2019-12-01 | 98% | 0% | 122541.3 | 6220 | 1592318.7 | Yes
20 | 02217005 | Beto Unit, Tennessee Colony | Infrastructure: Install Transformer - Substation | Sale of Land Proceeds Account No. 0543 |  | 124520 | 2019-12-01 | 98% | 0% | 124520 | 0 | 0 | Yes
21 | 01717008 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Main Building | Economic Stabilization Fund No. 0599 | 60900 | 102200 | 2018-10-18 | 100% | 100% | 16766.5 | 72481.44 | 12952.06 | Yes
22 | 04813003 | McConnell Unit, Beeville | Infrastructure: Replace Steam & Condensate Lines | Economic Stabilization Fund No. 0599 | 687700 | 750500 | 2019-02-01 | 100% | 85% | 457157.55 | 279374.14 | 13968.31 | Yes
23 | 09215007 | Holliday Unit, Huntsville | Facility Repair: Replace Air Handler and Heaters - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 164800 | 2019-03-04 | 100% | 2% | 148900 | 0 | 15900
24 | 03115010 | Hilltop Unit, Gatesville | Roofing: Replace Roof - Medical Department | Economic Stabilization Fund No. 0599 | 245600 | 143334.35 | 2018-06-07 | 100% | 100% | 0 | 143334.35 | 0 | Yes
25 | 04816012 | McConnell Unit, Beeville | Security: Replace Cell Doors - Multiple Locations | Economic Stabilization Fund No. 0599 | 350200 | 350200 | 2019-06-14 | N/A | 4% | 306705 | 1118.4 | 42376.6
26 | 01616002 | Mt. View Unit, Gatesville | Security: Replace Cell Doors - Administrative Segregation | Economic Stabilization Fund No. 0599 | 59300 | 56388 | 2018-08-13 | N/A | 100% | 0 | 56388 | 0 | Yes
27 | 05416004 | Polunsky Unit, Livingston | Security: Replace Cell Doors - Multiple Locations | Economic Stabilization Fund No. 0599 | 327400 | 336500 | 2019-05-24 | N/A | 97% | 336423 | 0 | 77
28 | 02812001 | Powledge Unit, Palestine | Infrastructure: Repair Washout - Outfall Line - Wastewater Treatment Plant | Economic Stabilization Fund No. 0599 | 205800 | 251700 | 2019-03-29 | 100% | 65% | 38304.66 | 178487.86 | 34907.48 | Yes
29 | 03608011 | Michael Unit, Tennessee Colony | Safety: Repair/Replace Fire Line - Administrative Segregation | Economic Stabilization Fund No. 0599 | 474100 | 1187.25 | N/A | N/A | N/A | 75.57 | 1111.68 | 0
30 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate #3 and #4 Pickets | Economic Stabilization Fund No. 0599 | 0 | 65700 | 2019-09-27 | 100% | 64% | 2667.17 | 58286.66 | 4746.17
31 | 10814001 | Sanchez Unit, El Paso | Infrastructure: Renovate Elevated Water Storage Tank | Economic Stabilization Fund No. 0599 | 0 | 605400 | 2018-12-21 | 100% | 99% | 64682 | 490330 | 50388 | Yes
32 | 09199005 | Chasefield Unit, Beeville | Infrastructure: Repair/Replace Fire Alarm System Multiple Buildings | Economic Stabilization Fund No. 0599 | 0 | 137100 | 2019-04-15 | 100% | 1% | 0 | 0 | 137100
33 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Economic Stabilization Fund No. 0599 | 0 | 101300 | 2019-10-25 | 100% | 1% | 0 | 0 | 101300 | Yes
34 | 01313008 | Huntsville Unit, Huntsville | Roofing: Repair/Replace Roof - Mechanical | Economic Stabilization Fund No. 0599 | 0 | 551600 | 2019-08-30 | 100% | 1% | 525231 | 870.22 | 25498.78
35 | 03613004 | Michael Unit, Tennessee Colony | Roofing: Replace Roof - Multiple Buildings | Economic Stabilization Fund No. 0599 | 6500000 | 0 | N/A | N/A | N/A | 0 | 0 | 0
36 | 05413002 | Polunsky Unit, Livingston | Facility Repair: Replace Shower Doors - Administrative Segregation | Economic Stabilization Fund No. 0599 | 0 | 317900 | 2018-10-10 | 100% | 100% | 0 | 284814.85 | 33085.15 | Yes
37 | 12809001 | Bradshaw Unit, Henderson | Facility Repair: Repair Floor - Kitchen | Economic Stabilization Fund No. 0599 | 0 | 242700 | 2019-10-18 | 100% | 15% | 6479.69 | 62501.06 | 173719.25 | Yes
38 | 01212004 | Goree Unit, Huntsville | Safety: Install Generator with Automatic Transfer Switch - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 168000 | 2019-01-25 | 100% | 41% | 29105.19 | 118703.33 | 20191.48 | Yes
39 | 03211005 | Estelle Unit, Huntsville | Security: Replace Exterior Lighting | Economic Stabilization Fund No. 0599 | 0 | 575317.78 | 2019-02-01 | 100% | 96% | 51830.05 | 353695.59 | 169792.14
40 | 00800016 | Byrd Unit, Huntsville | Safety: Install Fire Alarm | Economic Stabilization Fund No. 0599 | 0 | 1493413 | 2019-03-29 | 100% | 62% | 528224.6 | 868743.63 | 96444.77
41 | 07009003 | Neal Unit, Amarillo | Facility Repair: Renovate Mechanical Rooms and Showers | Economic Stabilization Fund No. 0599 | 0 | 184855.95 | 2019-10-25 | 100% | 38% | 5.58 | 88879.49 | 95970.88 | Yes
42 | 09107005 | Chasefield Unit, Beeville | Facility Repair: Renovate Commissary Warehouse | Economic Stabilization Fund No. 0599 | 0 | 205900 | 2020-03-02 | 100% | 49% | 27628.69 | 172868.15 | 5403.16
43 | 07913003 | Moore Unit, Bonham | Facility Repair: Resurface Parking Lot and Perimeter Road | Economic Stabilization Fund No. 0599 | 0 | 986000 | 2019-08-30 | 100% | 30% | 932841 | 77.86 | 53081.14
44 | 02016020 | Wynne Unit, Huntsville | Facility Repair: Replace Deaerator - Boiler Room | Economic Stabilization Fund No. 0599 | 0 | 236100 | 2019-01-11 | 100% | 95% | 0 | 217117.83 | 18982.17 | Yes
45 | 09916006 | Hutchins Unit, Dallas | Facility Repair: Replace Air Handler | Economic Stabilization Fund No. 0599 | 0 | 195100 | 2019-02-22 | 100% | 5% | 162624 | 1329.67 | 31146.33
46 | 09717001 | Gist Unit, Beaumont | Facility Repair: Replace HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 89747.5 | 2018-06-12 | 100% | 100% | 0 | 89747.5 | 0 | Yes
47 | 09717003 | Gist Unit, Beaumont | Facility Repairs: Replace HVAC Unit - Education Building | Economic Stabilization Fund No. 0599 | 0 | 89747.5 | 2018-07-19 | 100% | 100% | 0 | 89747.5 | 0 | Yes
48 | 03715008 | Clements Unit, Amarillo | Facility Repair: Replace Electrical Conduit - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 36400 | 2019-04-19 | N/A | 83% | 0 | 35037.58 | 1362.42
49 | 06614001 | Tulia Unit, Tulia | Facility Repair: Replace Showers - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 128606.6 | 2018-08-23 | N/A | 100% | 0 | 128606.6 | 0 | Yes
50 | 00515002 | Clements Unit, Amarillo | Security: Replace Lighting - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 102100 | 2019-07-26 | N/A | 42% | 4962.18 | 91780.04 | 5357.78
51 | 0412017 | Stiles Unit, Beaumont | Facility Repair: Replace Electrical Panels - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 435600 | 2019-07-12 | 100% | 5% | 0 | 0 | 435600 | Yes
52 | 03615011 | Michael Unit, Tennessee Colony | Infrastructure: Replace Water Line - Between Well & Ground Storage | Economic Stabilization Fund No. 0599 | 50400 | 238100 | 2019-05-03 | 100% | 3% | 64830.9 | 68105.81 | 105163.29 | Yes
53 | 03217025 | Estelle Unit, Huntsville | Safety: Replace Generator - High Security | Economic Stabilization Fund No. 0599 | 0 | 193000 | 2019-04-19 | 100% | 8% | 9797.99 | 170420.04 | 12781.97
54 | 01117019 | Ferguson Unit, Midway | Safety: Replace Generator and Automatic Transfer Switch | Economic Stabilization Fund No. 0599 | 0 | 61248.26 | 2018-09-06 | 100% | 100% | 0 | 61248.26 | 0 | Yes
55 | 04017005 | Lewis Unit, Woodville | Safety: Replace Generators and Automatic Transfer Switch - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 63723.49 | 2018-08-22 | 100% | 100% | 0 | 63723.49 | 0 | Yes
56 | 02417011 | Crain Unit, Gatesville | Facility Repair: Replace Water Heater - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 118359.61 | 2018-09-13 | 100% | 100% | 0 | 112055.71 | 6303.9 | Yes
57 | 10315011 | Lopez Unit, Edinburg | Facility Repair: Replace HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 51900 | 2019-05-31 | 100% | 4% | 40651 | 167.73 | 11081.27
58 | 04717006 | Robertson Unit, Abilene | Facility Repair: Replace Water Heater - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 46899.34 | 2018-06-25 | 100% | 100% | 0 | 46899.34 | 0 | Yes
59 | 01817012 | Stringfellow Unit, Rosharon | Safety: Replace Generator - Boiler Room | Economic Stabilization Fund No. 0599 | 0 | 159500 | 2019-04-12 | 100% | 70% | 8930.29 | 108117.04 | 42452.67 | Yes
60 | 00917007 | Eastham Unit, Lovelady | Facility Repair: Replace Raw Material Feed Bin - Feed Mill | Economic Stabilization Fund No. 0599 | 0 | 149034.5 | 2019-03-22 | 100% | 1% | 76044.5 | 796.57 | 72193.43
60 | 00917007 | Eastham Unit, Lovelady | Facility Repair: Replace Feed Bin - Feed Mill | Sale of Land Proceeds Account No. 0543 | 0 | 1380265.5 | 2019-03-22 | 100% | 1% | 1380265.5 | 0 | 0
61 | 01416005 | Jester I Unit, Richmond | Facility Repair: Demolish Agriculture Buildings | Economic Stabilization Fund No. 0599 | 0 | 170587.04 | 2018-08-28 | N/A | 100% | 0 | 170587.04 | 0 | Yes
62 | 00617003 | Coffield Unit, Tennessee Colony | Infrastructure: Replace Aerators | Economic Stabilization Fund No. 0599 | 0 | 115283.35 | 2018-09-14 | 100% | 100% | 0 | 115283.35 | 0 | Yes
63 | 09916033 | Hutchins Unit, Dallas | Facility Repair: Replace Air Handlers - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 585200 | 2019-02-22 | 100% | 1% | 345576 | 0 | 239624
64 | 03118002 | Hilltop Unit, Gatesville | Safety: Replace Emergency Generator - Infirmary | Economic Stabilization Fund No. 0599 | 0 | 50100 | 2018-08-30 | 100% | 100% | 1140 | 48771.39 | 188.61
65 | 03617001 | Michael Unit, Tennessee Colony | Facility Repair: Replace Duplex Heat Exchangers - Boiler Room | Economic Stabilization Fund No. 0599 | 0 | 84180.31 | 2018-03-30 | N/A | 100% | 0 | 84180.31 | 0
66 | 02817018 | Powledge Unit, Palestine | Facility Repair: Replace Refrigeration Equipment | Economic Stabilization Fund No. 0599 | 0 | 67800 | 2019-01-28 | N/A | 70% | 0 | 52513.17 | 15286.83 | Yes
67 | 01716008 | Houston VI DPO, Houston | Infrastructure: Repair/Resurface Parking Lot | Economic Stabilization Fund No. 0599 | 0 | 39999.98 | 2018-07-03 | 100% | 100% | 0 | 39999.98 | 0 | Yes
68 | 01017018 | Ellis Unit, Huntsville | Infrastructure: Install Water Wells | Economic Stabilization Fund No. 0599 | 299000 | 299000 | 2019-02-22 | N/A | 82% | 282200 | 7093.69 | 9706.31 | Yes
69 | 06714010 | Telford Unit, New Boston | Infrastructure: DESIGN ONLY: Replace Hot Water and Steam Piping | Economic Stabilization Fund No. 0599 | 0 | 310600 | 2019-01-30 | 90% | 0% | 130026.27 | 160706.24 | 19867.49 | Yes
70 | 10117005 | Plane Unit, Dayton | Safety: Replace Main Switchgear - Back Gate | Economic Stabilization Fund No. 0599 | 0 | 69995 | 2018-09-17 | 100% | 100% | 0 | 69995 | 0 | Yes
71 | 02817022 | Powledge Unit, Palestine | Safety: Replace Generator - Wastewater Treatment Plant | Economic Stabilization Fund No. 0599 | 0 | 41505.59 | 2018-06-25 | 100% | 100% | 0 | 41505.59 | 0 | Yes
72 | 02617007 | Pack Unit, Navasota | Security: Install Window Screens - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 23677.64 | 2018-01-05 | N/A | 100% | 0 | 23677.64 | 0
73 | 00918001 | Eastham Unit, Lovelady | Facility Repair: Replace HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 131300 | 2019-04-30 | 100% | 50% | 21724.81 | 101734.72 | 7840.47
74 | 00717018 | Darrington Unit, Rosharon | Facility Repair: Replace Air Handlers - Chapel | Economic Stabilization Fund No. 0599 | 0 | 94800 | 2019-05-31 | 100% | 1% | 90910.56 | 69.6 | 3819.84
75 | 00917005 | Eastham Unit, Lovelady | Facility Repair: Replace Poultry Building and Cage System | Economic Stabilization Fund No. 0599 | 0 | 770000 | 2020-04-03 | 100% | 0% | 0 | 1808.87 | 768191.13
76 | 02717007 | Terrell Unit, Rosharon | Safety: Replace Emergency Generator - Kitchen | Economic Stabilization Fund No. 0599 | 0 | 42300 | 2019-02-15 | 100% | 96% | 0 | 33780 | 8520 | Yes
77 | 02718004 | Terrell Unit, Rosharon | Infrastructure: Resurface Parking Lot | Economic Stabilization Fund No. 0599 | 0 | 357200 | 2019-05-20 | 100% | 1% | 337548 | 683.76 | 18968.24
77 | 02718004 | Terrell Unit, Rosharon | Infrastructure: Resurface Parking Lot | Economic Stabilization Fund No. 0543 | 0 | 25000 | 2019-05-20 | 100% | 1% | 25000 | 0 | 0
78 | 01817014 | Stringfellow Unit, Rosharon | Safety: Replace Generator and Automatic Transfer Switch - Lift Station | Economic Stabilization Fund No. 0599 | 0 | 67400 | 2019-03-08 | 100% | 5% | 3206.69 | 60645 | 3548.31 | Yes
79 | 01917002 | Scott Unit, Angleton | Safety: Replace Generator and Automatic Transfer Switch - Lift Station | Economic Stabilization Fund No. 0599 | 0 | 41200 | 2018-11-21 | 100% | 100% | 202.06 | 33142.96 | 7854.98 | Yes
80 | 09217001 | Holliday Unit, Huntsville | Facility Repair: Replace HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 72900 | 2019-02-22 | 100% | 2% | 59760 | 0 | 13140
81 | 10018001 | Lychner Unit, Humble | Facility Repair: Replace Boilers & Storage Tanks | Economic Stabilization Fund No. 0599 | 0 | 173100 | 2019-09-20 | 100% | 3% | 1565.83 | 142860.28 | 28673.89 | Yes
82 | 03617010 | Michael Unit, Tennessee Colony | Facility Repair: Replace Air Handler | Economic Stabilization Fund No. 0599 | 0 | 230400 | 2019-02-08 | 100% | 3% | 141780 | 0 | 88620
83 | 12017001 | Willacy Unit, Raymondville | Infrastructure: Replace Hot Water Storage Tank - Laundry Room | Economic Stabilization Fund No. 0599 | 0 | 169900 | 2019-03-07 | 100% | 95% | 0 | 157906 | 11994
84 | 01818004 | Stringfellow Unit, Rosharon | Facility Repair: Replace Water Storage Tank and Heat Exchanger | Economic Stabilization Fund No. 0599 | 0 | 114200 | 2018-10-31 | 100% | 100% | 0 | 98484.26 | 15715.74 | Yes
85 | 00617023 | Coffield Unit, Tennessee Colony | Facility Repair: Replace Condensing Unit - Law Library | Economic Stabilization Fund No. 0599 | 0 | 30837.04 | 2018-09-18 | 100% | 100% | 0 | 30837.04 | 0 | Yes
86 | 02418004 | Crain Unit, Gatesville | Safety: Replace Generator and Automatic Transfer Switch | Economic Stabilization Fund No. 0599 | 0 | 56500 | 2019-12-21 | N/A | 22% | 0 | 53826.51 | 2673.49 | Yes
87 | 02618008 | Pack Unit, Navasota | Facility Repair: DESIGN ONLY: Install HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 408258 | 2018-10-18 | 100% | N/A | 194343.33 | 194333.87 | 19580.8 | Yes
88 | 04218005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit | Economic Stabilization Fund No. 0599 | 0 | 213500 | 2019-07-31 | 100% | 3% | 153200 | 4948.08 | 55351.92
89 | 12018001 | Willacy Unit, Raymondville | Facility Repair: Install Electrical Duct Heaters - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 46200 | 2019-08-23 | 100% | 94% | 2141.26 | 27168.56 | 16890.18
90 | 01217001 | Goree Unit, Huntsville | Safety: Replace Generator and two Automatic Transfer Switches - Food Service | Economic Stabilization Fund No. 0599 | 0 | 43400 | 2019-03-29 | 100% | 25% | 0.01 | 39264.72 | 4135.27 | Yes
91 | 02718006 | Terrell Unit, Rosharon | Facility Repair: Replace Water Softener - Boiler Room | Economic Stabilization Fund No. 0599 | 0 | 50400 | 2019-04-19 | 100% | 4% | 0 | 45750 | 4650
92 | 02817010 | Powledge Unit, Palestine | Safety: Install Nurse Call System - Medical | Economic Stabilization Fund No. 0599 | 0 | 64100 | 2019-11-15 | 100% | 2% | 0 | 0 | 64100 | Yes
93 | 07418002 | Wallace Unit, Colorado City | Facility Repair: Replace Water Heater - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 35700 | 2019-12-30 | 100% | 7% | 4085.85 | 26520.3 | 5093.85
94 | 06218001 | Fort Stockton Unit, Ft. Stockton | Facility Repair: Replace Refrigeration Equipment - Kitchen | Economic Stabilization Fund No. 0599 | 0 | 42800 | 2019-10-25 | N/A | 3% | 960 | 30264.96 | 11575.04
95 | 00118006 | Administrative Complex | Facility Repair: Replace HVAC Unit - Classifications | Economic Stabilization Fund No. 0599 | 0 | 122100 | 2019-03-22 | 100% | 1% | 107991 | 0 | 14109
96 | 06118001 | Cotulla Unit, Cotulla | Facility Repair: Replace Refrigeration Equipment - Kitchen | Economic Stabilization Fund No. 0599 | 0 | 48200 | 2019-08-23 | 100% | 0% | 0 | 0 | 48200
97 | 01017008 | Ellis Unit, Huntsville | Facility Repair: Replace Plumbing Controls and Fixtures | State Energy Conservation Office (SECO) | 2709000 | 4124509 | 2020-11-17 | 100% | 10% | 1789300.96 | 70828.96 | 2264379.08 | Yes
98 | 03217006 | Estelle Unit, Huntsville | Facility Repair: Replace Plumbing Controls and Fixtures | State Energy Conservation Office (SECO) | 2596600 | 3590749 | 2020-11-17 | 100% | 10% | 1644409.98 | 15220.57 | 1931118.45 | Yes
99 | 07514005 | Hodge Unit, Rusk | Facility Repair: Replace T-12 Lighting with LED Lighting | State Energy Conservation Office (SECO) | 0 | 146200 | 2019-06-15 | 100% | 3% | 63623.14 | 3932.34 | 78644.52 | Yes
100 | 03414002 | Skyview Unit, Rusk | Facility Repair: Replace T-12 Lighting with LED Lighting | State Energy Conservation Office (SECO) | 0 | 144819 | 2019-06-15 | 100% | 3% | 73051.07 | 58.14 | 71709.79 | Yes
101 | 10518001 | Murray Unit, Gatesville | Facility Repair: Replace Boiler and Hot Water Storage Tanks | Economic Stabilization Fund No. 0599 | 0 | 195900 | 2019-08-16 | 100% | 0% | 0 | 0 | 195900 | Yes
102 | 02618014 | Pack Unit, Navasota | Roofing: Resurface Roofs - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 613140.2 | 2018-10-23 | N/A | 100% | 0 | 613091.06 | 49.14 | Yes
103 | 09118026 | Chasefield Unit, Beeville | Facility Repair: Replace Air Handling Unit | Economic Stabilization Fund No. 0599 | 0 | 45800 | 2019-04-26 | N/A | 1% | 31673 | 0 | 14127 | Yes
104 | 04216010 | Hughes Unit, Gatesville | Safety: Replace Nurse Call System - Infirmary | Economic Stabilization Fund No. 0599 | 0 | 53900 | 2020-03-20 | N/A | 4% | 0 | 0 | 53900 | Yes
105 | 04218007 | Hughes Unit, Gatesville | Facility Repair: Replace Refrigeration Rack System | Economic Stabilization Fund No. 0599 | 0 | 163500 | 2019-04-26 | N/A | 3% | 113823.23 | 21532.79 | 28143.98 | Yes
106 | 01718017 | Ramsey Unit, Rosharon | Facility Repair: Replace Chiller | Economic Stabilization Fund No. 0599 | 0 | 51900 | 2020-02-28 | 100% | 0% | 0 | 0 | 51900 | Yes
107 | 05318003 | Smith Unit, Lamesa | Facility Repair: Replace HVAC Units - Multiple Locations | Economic Stabilization Fund No. 0599 | 0 | 69600 | 2019-07-29 | N/A | 2% | 54590 | 9177.53 | 5832.47 | Yes
108 | 04718008 | Robertson Unit, Abilene | Facility Repair: Replace HVAC Units Administrative Segregation | Economic Stabilization Fund No. 0599 | 0 | 194100 | 2020-01-24 | 13% | 0% | 0 | 0 | 194100 | Yes
109 | 03018003 | Jester III Unit, Richmond | Safety: Replace Emergency Generator | Economic Stabilization Fund No. 0599 | 0 | 103500 | 2019-06-14 | 100% | 1% | 99819 | 0 | 3681 | Yes
110 | 01818005 | Stringfellow Unit, Rosharon | Infrastructure: Replace Pump System and Controls | Economic Stabilization Fund No. 0599 | 0 | 135000 | 2019-12-30 | 14% | 0% | 0 | 0 | 135000 | Yes
111 | 03617012 | Michael Unit, Tennessee Colony | Safety: Replace Nurse Call System - Hospice | Economic Stabilization Fund No. 0599 | 0 | 51700 | 2019-02-22 | N/A | 80% | 49120 | 0 | 2580 | Yes
112 | 10118003 | Plane Unit, Dayton | Facility Repair: Replace Boilers and Hot Water Storage Tank | Economic Stabilization Fund No. 0599 | 0 | 200500 | 2019-12-20 | 100% | 0% | 0 | 0 | 200500 | Yes
113 | 02618022 | Pack Unit, Navasota | Facility Repair: Install HVAC Units | Economic Stabilization Fund No. 0599 | 0 | 199500 | 2019-10-25 | 100% | 11% | 85150.3 | 62268.1 | 52081.6 | Yes
NA | 06115001 | Cotulla Unit, Cotulla | Facility Repair: Replace Shower - Multiple Locations | Economic Stabilization Fund No. 0599 | 900000 | 0 | N/A | N/A | N/A | 0 | 0 | 0
|  |  |  | Totals: | 41635989 | 50700726.97 |  |  |  | 27844310.96 | 9743075.83 | 13113340.18

## TDCJ Sup.
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2018-12-14
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
1 | TIMELINE: (original estimated substantial completion date: 11/02/18; actual: 10/29/18). Pending final expenditures to close project.
2 | BUDGET: Project complete. Budget reduced to final expenditures.
4 | TIMELINE: (original estimated substantial completion date: 1/31/19; revised: 7/19/20)
5 | BUDGET: Construction scheduled for FY20-21
6 | TIMELINE: (original estimated substantial completion date: 12/02/18; revised: 2/1/20)
9 | BUDGET: Lowest qualified bidder higher than original estimate.
16 | BUDGET: Construction scheduled for FY20-21
17 | TIMELINE: (original estimated substantial completion date: 11/10/18; revised: 6/1/20)
18 | TIMELINE: (original estimated substantial completion date: 11/1/19; revised: 12/3/18) BUDGET: Project complete. Budget reduced to final expenditures.
20 | TIMELINE: (original estimated substantial completion date: 12/02/18; revised: 12/1/19)
21 | TIMELINE: (original estimated substantial completion date: 11/29/18; actual: 10/18/18). Pending final expenditures to close project.
22 | TIMELINE: (original estimated substantial completion date: 12/31/18; revised: 2/1/19)
24 | BUDGET: Project complete. Budget reduced to final expenditures.
26 | BUDGET: Project complete. Budget reduced to final expenditures.
28 | TIMELINE: (original estimated substantial completion date: 12/14/18; revised: 03/29/19)
31 | TIMELINE: (original estimated substantial completion date: 11/12/18; actual: 12/21/18). Pending final expenditures to close project.
33 | TIMELINE: (original estimated substantial completion date: 03/08/19; revised: 10/25/19)
36 | TIMELINE: (original estimated substantial completion date: 12/21/18; revised: 10/10/18). Pending final expenditures to close project.
37 | TIMELINE: (original estimated substantial completion date: 02/08/19; revised: 10/18/19)
38 | TIMELINE: (original estimated substantial completion date: 11/30/18; revised: 1/25/19)
41 | BUDGET: Additional material required
44 | TIMELINE: (original estimated substantial completion date: 11/30/18; revised: 1/11/19)
46 | BUDGET: Project complete. Budget reduced to final expenditures.
47 | BUDGET: Project complete. Budget reduced to final expenditures.
49 | BUDGET: Project complete. Budget reduced to final expenditures.
51 | BUDGET: Lowest qualified bidder higher than original estimate.
52 | BUDGET: Lowest qualified bidder higher than original estimate.
54 | TIMELINE: (original estimated substantial completion date: 11/09/18; actual: 9/06/18) BUDGET: Project complete. Budget reduced to final expenditures.
55 | BUDGET: Project complete. Budget reduced to final expenditures.
56 | TIMELINE: (original estimated substantial completion date: 10/01/18; actual: 09/13/18). Pending final expenditures to close project.
58 | BUDGET: Project complete. Budget reduced to final expenditures.
59 | TIMELINE: (original estimated substantial completion date: 11/29/18; revised: 04/12/19)
61 | BUDGET: Project complete. Budget reduced to final expenditures.
62 | TIMELINE: (original estimated substantial completion date: 9/23/18; actual: 9/14/18) BUDGET: Project complete. Budget reduced to final expenditures.
66 | TIMELINE: (original estimated substantial completion date: 11/16/18; revised: 1/28/19)
67 | BUDGET: Project complete. Budget reduced to final expenditures.
68 | TIMELINE: (original estimated substantial completion date: 11/30/18; revised: 2/22/19)
69 | TIMELINE: (original estimated substantial completion date: 11/19/18; revised: 1/30/19) Pending final expenditures to close project.
70 | TIMELINE: (original estimated substantial completion date: 11/16/18; actual: 9/17/18) BUDGET: Project complete. Budget reduced to final expenditures.
71 | BUDGET: Project complete. Budget reduced to final expenditures.
76 | TIMELINE: (original estimated substantial completion date: 11/16/18; revised: 2/15/19)
78 | TIMELINE: (original estimated substantial completion date: 10/26/18; revised: 3/08/19)
79 | TIMELINE: (original estimated substantial completion date: 11/26/18; actual: 11/21/18). Pending final expenditures to close project.
81 | TIMELINE: (original estimated substantial completion date: 12/21/18; revised: 9/20/19)
84 | TIMELINE: (original estimated substantial completion date: 2/22/19; actual: 10/31/18). Pending final expenditures to close project.
85 | TIMELINE: (original estimated substantial completion date: 12/14/18; actual: 9/18/18) BUDGET: Project complete. Budget reduced to final expenditures.
86 | TIMELINE: (original estimated substantial completion date: 11/16/18; revised: 12/21/19)
87 | TIMELINE: (original estimated substantial completion date: 8/2/19; actual: 10/18/18)
90 | TIMELINE: (original estimated substantial completion date: 12/28/18; revised: 3/29/19)
92 | TIMELINE: (original estimated substantial completion date: 12/07/18; revised: 11/15/19)
97 | PRIORITIZATION: Project being funded by the State Energy Conservation Office (SECO). BUDGET: Replace Plumbing Controls and Fixtures (Ellis Unit, Huntsville)
98 | PRIORITIZATION: Project being funded by the State Energy Conservation Office (SECO). BUDGET: Replace Plumbing Controls and Fixtures (Estelle Unit, Huntsville)
99 | PRIORITIZATION: New project. Project being funded by the State Energy Conservation Office (SECO). BUDGET: Replace T-12 Lighting with LED Lighting (Hodge Unit, Rusk)
100 | PRIORITIZATION: New project. Project being funded by the State Energy Conservation Office (SECO). BUDGET: Replace T-12 Lighting with LED Lighting (Skyview Unit, Rusk)
101 | PRIORITIZATION: New project BUDGET: Replace Boilers and Hot Water Storage Tank - Multiple Locations (Murray Unit, Gatesville)
102 | PRIORITIZATION: Priority revised from 97 to 102. TIMELINE: (original estimated substantial completion date: 11/30/18; actual: 10/23/18) Pending final expenditures to close project.
103 | PRIORITIZATION: New project BUDGET: Replace Air Handling Unit (Chasefield Unit, Beeville)
104 | PRIORITIZATION: New project BUDGET: Replace Nurse Call System - Infirmary (Hughes Unit, Gatesville)
105 | PRIORITIZATION: New project BUDGET: Replace Refrigeration Rack System (Hughes Unit, Gatesville)
106 | PRIORITIZATION: New project BUDGET: Replace Chiller (Ramsey Unit, Rosharon)
107 | PRIORITIZATION: New project BUDGET: Replace HVAC Units - Multiple Locations (Smith Unit, Lamesa)
108 | PRIORITIZATION: New project BUDGET: Replace HVAC Units Administrative Segregation (Robertson Unit, Abilene)
109 | PRIORITIZATION: New project BUDGET: Replace Emergency Generator (Jester III Unit, Richmond)
110 | PRIORITIZATION: New project BUDGET: Replace Pump System and Controls (Stringfellow Unit, Rosharon)
111 | PRIORITIZATION: New project BUDGET: Replace Nurse Call System - Hospice (Michael Unit, Tennessee Colony)
112 | PRIORITIZATION: New project BUDGET: Replace Boilers and Hot Water Storage Tank - Multiple Locations (Plane Unit, Dayton)
113 | PRIORITIZATION: New project BUDGET: Install HVAC Units - Trusty Camp (Pack Unit, Navasota)

## TFC
| Agency: | Texas Facilities Commission (303)
| Date: | 2018-12-14 | [9 empty] | 2018-12-14
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | DROC | Replace deteriorated cooling water loop and pumps supplying cooling water to data center. | GR Funds | 2000000 | 2000000 | 2022-12-31 | 95% | 0% | 1116088 | 93951 | 789961 | Yes
2 | 303 | State Bldg/Air Handler Unit Replacements and DM Renovations at Various Buildings, Austin TX Insurance Annex (INX) William P. Clements (WPC) Robert E. Johnson (REJ) Price Daniel Sr. (PDB) Supreme Court Bldg (SCB) Tom C. Clark (TCC) | Renovation/Replacement of air handling units, outside air handling units, air distribution system and control; exterior cladding waterproofing repairs; emergency power and cooling connections and life safety systems. | GR Funds | 39000000 | 39000000 | 2022-12-31 | 100% | 5% | 37509686 | 1490314 | 0 | Yes
3 | 303 | DSHS/ Air Handler Unit Replacements and DM Renovations at Various Buildings, Austin TX DSHS Bldg. G (DHG) DSHS Building K (DHK) ? DSHS Tower Bldg. (DHT) DSHS Records Bldg. (DHR) Robert D Moreton (RDM) DSHS Building F (DHF) DSHS Service Building ( DHSB) Dr. Robert Bernstein Bldg. (RBB) | Renovation/Replacement of air handling units, outside air handling units, air distribution system and control; Structural/cladding/waterproofing repairs; and life safety systems. | GR Funds | 19500000 | 19500000 | 2022-12-31 | 0% | 0% | 583023 | 250959 | 18666018 | No
4 | 303 | Dr. Bob Glaze Laboratory Services (DBGL), Austin TX | Repair/Replace Mechanical systems and enhancement to indoor air quality; Replace/Repair of electrical and plumbing systems; Life safety and fire protection systems; repairs of exterior envelope; repair/replace roof. | GR Funds | 10000000 | 10000000 | 2022-12-31 | 99% | 0% | 9264173 | 88317 | 647510 | Yes
5 | 303 | El Paso (ELP) El Paso TX | Roof Replacement; Repair/Replace mechanical systems; structural/waterproofing repairs; Repair/Install Vestibule. | GR Funds | 1000000 | 1000000 | 2022-12-31 | 1% | 0% | 0 | 0 | 1000000 | Yes
6 | 303 | Stephen F. Austin, Austin TX William B. Travis, Austin, TX | Repair outside air handling units, Fire separations, lightning protection, plumbing and associated Accessibility. | GR Funds | 5850000 | 5850000 | 2022-12-31 | 100% | 10% | 2354801 | 3364874 | 130325 | Yes
7 | 303 | Various Parking Garage Elevators Austin TX | Repair/replacement of elevators. | GR Funds | 2200000 | 2200000 | 2022-12-31 | 100% | 1% | 2097537 | 22463 | 80000 | Yes
8 | 303 | State Parking Garages Austin TX | Repairs to life safety and fire protection systems; repairs to electrical systems; sitework, building envelope, expansion joints and structural systems. | GR Funds | 5150000 | 5150000 | 2022-12-31 | 40% | 0% | 86129 | 232053 | 4831818 | No
9 | 303 | P35 Austin, TX | Repair/Replace Cooling tower; distribution system and associated controls | GR Funds | 2300000 | 2300000 | 2022-12-31 | 5% | 0% | 121844 | 25581 | 2152575 | No
10 | 303 | Program-wide Priority 1 Repairs | Priority IA and IB deferred maintenance deficiencies that have become an immediate need (I) and impact health and life safety of the building occupants (A) or threaten the continuity of operations for critical governemnt operations (B). These needs have advanced to an immediate stage since the proposed appropriation request developed in August of 2016 or may present as an immediate need through he course of the implementation of the 2018-19 deferred maintenance funding strategies. The list of funding strategies provided for the 2018-19 deferred maintenance appropriation request is provided as an exhibit for reference to qualify initiatives in this project. | GR Funds | 3000000 | 3000000 | 2019-01-06 | 5% | 0% | 553723 | 497442 | 1948835 | No
11 | 303
12 | 303
13 | 303
14 | 303
15 | 303
16 | 303
17 | 303
18 | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
|  |  |  | Totals: | 90000000 | 90000000 |  |  |  | 53687004 | 6065954 | 30247042

## TFC Sup.
| Agency: | Texas Facilities Commission (303)
| Date: | 2018-12-15
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | Project was change ordered to an existing FY16-17 project. Project is currently under construction.
2 | Professional service providers in the design phase. CMR providing pre-construction services.
4 | Project was change ordered to an existing FY16-17 project. Project is currently in design phase.
5 | Project currently in design.
6 | Project was issued as a change order to an existing FY16-17 - project and is currently in construction.
7 | Project was issued as a change order to an existing FY16-17 - project and is currently in construction.

## TxDOT
[8 empty] | 2668 | Texas Department of Transportation #601 |  | AY18-19 PROJECTS PLANNED
[8 empty] | Date: | 12/11/18 Final
Priority Audit Trail | [7 empty] | Prepared by: | Diana Miller, Facilities Business Operations Manager - Support Services Division
[8 empty] | Project ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q5 AY18-19) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | AY 2018-19 Encumbered (Based on Contract Award date) | AY 2018-19 Expended | Remaining Project Balance | Comment
AY18-19 Q1 JOC Priority | AY18-19 Q2 JOC Priority | AY18-19 Q3 JOC Priority | AY18-19 Q4 JOC Priority | AY 18-19 Q5 JOC Priority | FY19 Q6 JOC Priority | FY19 Q7 JOC Priority | FY19 Q8 JOC Priority
E1 | E1 | E1 | E1 | E1 |  |  |  | 13470418179 | Building Renovation-Victoria | Capital Repairs | Highway Trans. Fund 6 | 1600000 | 1600000 | 2020-04-06 | 0% | 0% | 204835 | 0 | 1395165 | Project in design phase, consultant fees encumbered
E2 | E2 | E2 | E2 | E2 |  |  |  | 19470418181 | Building Renovation-Atlanta DHQ | Capital Repairs | Highway Trans. Fund 6 | 660000 | 59471 | 2018-06-30 | 100% | 100% | 0 | 59471 | 0 | Project will be completed with District funds. Consultant fees paid.
E3 | E3 | E3 | E3 | E3 |  |  |  | 25470418060 | Building Renovation-Dickens | Capital Repairs | Highway Trans. Fund 6 | 360000 | 360000 | 2019-11-02 | 0% | 0% | 48818 | 0 | 311182 | Project in design phase, consultant fees encumbered
E4 | E4 | E4 | E4 | E4 |  |  |  | 24470418084 | CCURE Security Upgrades (including perimeter fencing)-DHQ | Safety/Security | Highway Trans. Fund 6 | 450000 | 609750 | 2019-03-08 | 100% | 0% | 609750 | 0 | 0 | Project let in August 2018
E5 | E5 | E5 | E5 | E5 |  |  |  | 17470418059 | CCURE Security Upgrades (including perimeter fencing)-DHQ | Safety/Security | Highway Trans. Fund 6 | 350000 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
E6 | E6 | E6 | E6 | E6 |  |  |  | 16470418185 | CCURE Security Upgrades - Perimeter Fencing | Safety/Security | Highway Trans. Fund 6 | 297000 | 325686 | 2018-06-18 | 100% | 100% | 0 | 325686 | 0 | Project let in December 2017
E7 | E7 | E7 | E7 | E7 |  |  |  | 09470418186 | Waco Roofing | Roofing | Highway Trans. Fund 6 | 308000 | 308000 | 2019-05-12 | 0% | 0% | 69113 | 0 | 238887 | Project in design phase, consultant fees encumbered.
|  |  | E8 | E8 |  |  |  | 38470418190 | DMV DE renovation - State Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 320000 | 2019-09-30 | 0% | 0% | 0 | 0 | 320000
|  |  | E9 | E9 |  |  |  | 05470418191 | Waterline replacement - Lubbock | Safety/Security | Highway Trans. Fund 6 | 0 | 340000 | 2019-07-07 | 0% | 0% | 0 | 0 | 340000 | Let on 11/15/18 no bidders; will be let again.
|  |  | E10.1 | E10.1 |  |  |  | 25470418220 | Childress CCURE - Wheeler | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.2 | E10.2 |  |  |  | 25470418221 | Childress CCURE - Shamrock | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.3 | E10.3 |  |  |  | 25470418222 | Childress CCURE - Clarendon | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.4 | E10.4 |  |  |  | 25470418223 | Childress CCURE - Wellington | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.5 | E10.5 |  |  |  | 25470418224 | Childress CCURE - Memphis | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.6 | E10.6 |  |  |  | 25470418225 | Childress CCURE - Silverton | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.7 | E10.7 |  |  |  | 25470418226 | Childress CCURE - Quanah | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.8 | E10.8 |  |  |  | 25470418227 | Childress CCURE - Matador | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.9 | E10.9 |  |  |  | 25470418228 | Childress CCURE - Paducah | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.10 | E10.10 |  |  |  | 25470418229 | Childress CCURE - Crowell | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.11 | E10.11 |  |  |  | 25470418230 | Childress CCURE - Dickens | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.12 | E10.12 |  |  |  | 25470418231 | Childress CCURE - Guthrie | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | E10.13 | E10.13 |  |  |  | 25470418232 | Childress CCURE - Munday | Safety/Security | Highway Trans. Fund 6 | 103385 | 103385 | 2020-02-01 | 0% | 0% | 0 | 0 | 103385 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  |  | E11 |  |  |  | 05470418241 | Seminole Remodel instead of Plains | Capital Repairs | Highway Trans. Fund 6 | 0 | 850000 | 2020-03-04 | 0% | 0% | 0 | 0 | 850000 | Project 05-18134 -Plains remodel changed scope to remodel in Seminole.
|  |  |  | E12 |  |  |  | 03470418242 | Replace Admin. Roof - Wichita Falls | Capital Repairs | Highway Trans. Fund 6 | 0 | 500000 | 2019-11-10 | 0% | 0% | 0 | 0 | 500000 | Project escalated in October 2018
|  |  |  | E13 |  |  |  | 21470418243 | Pharr Generator | Safety/Security | Highway Trans. Fund 6 | 0 | 125000 | 2019-08-31 | 0% | 0% | 0 | 0 | 125000 | Project escalated in October 2018
1 | 1 | 1 | 1 | 1 |  |  |  | 18470418063 | CCURE Security Upgrades (including perimeter fencing)-Corsciana | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
1.1 | 1.1 | 1.1 | 1.1 | 1.1 |  |  |  | 18470418064 | CCURE Security Upgrades (including perimeter fencing)-Dallas (North) | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
1.2 | 1.2 | 1.2 | 1.2 | 1.2 |  |  |  | 18470418065 | CCURE Security Upgrades (including perimeter fencing)-Dallas (Southwest) | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
1.3 | 1.3 | 1.3 | 1.3 | 1.3 |  |  |  | 18470418066 | CCURE Security Upgrades (including perimeter fencing)-Denton | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
1.4 | 1.4 | 1.4 | 1.4 | 1.4 |  |  |  | 18470418067 | CCURE Security Upgrades (including perimeter fencing)-McKinney | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
1.5 | 1.5 | 1.5 | 1.5 | 1.5 |  |  |  | 18470418068 | CCURE Security Upgrades (including perimeter fencing)-Hutchins | Safety/Security | Highway Trans. Fund 6 | 116667 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
4 | 4 | 4 | 4 | 4 |  |  |  | 22470418109 | Roof Replacement- Childress DHQ | Roofing | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-09 | 0% | 0% | 42213 | 0 | 317787 | Project 22-8109, 10, & 11 in design phase, consultant fees encumbered
4.1 | 4.1 | 4.1 | 4.1 | 4.1 |  |  |  | 22470418110 | Roof Replacement- Childress DHQ | Roofing | Highway Trans. Fund 6 | 240000 | 240000 | 2019-10-09 | 0% | 0% | 42213 | 0 | 197787 | Project 22-8109, 10, & 11 in design phase, consultant fees encumbered
4.2 | 4.2 | 4.2 | 4.2 | 4.2 |  |  |  | 22470418111 | Roof Replacement- Childress DHQ | Roofing | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-09 | 0% | 0% | 42213 | 0 | 77787 | Project 22-8109, 10, & 11 in design phase, consultant fees encumbered
6 | 6 | 6 | 6 | 6 |  |  |  | 18470418061 | CCURE Security Upgrades (including perimeter fencing)-Rockwall | Safety/Security | Highway Trans. Fund 6 | 200000 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
6.1 | 6.1 | 6.1 | 6.1 | 6.1 |  |  |  | 18470418062 | CCURE Security Upgrades (including perimeter fencing)-Waxahachie | Safety/Security | Highway Trans. Fund 6 | 200000 | 152116 | 2019-01-15 | 100% | 28% | 59818 | 92298 | 0 | 18-8061, 62, 63, 64, 65,66,67 &68 Let together on 4/3/18
7 | 7 | 7 | 7 | 7 |  |  |  | 02470418085 | CCURE Security Upgrades (including perimeter fencing)-Decatur | Safety/Security | Highway Trans. Fund 6 | 107520 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
7.1 | 7.1 | 7.1 | 7.1 | 7.1 |  |  |  | 02470418086 | CCURE Security Upgrades (including perimeter fencing)-Uless | Safety/Security | Highway Trans. Fund 6 | 107520 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
7.2 | 7.2 | 7.2 | 7.2 | 7.2 |  |  |  | 02470418087 | CCURE Security Upgrades (including perimeter fencing)-Keene | Safety/Security | Highway Trans. Fund 6 | 107520 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
7.3 | 7.3 | 7.3 | 7.3 | 7.3 |  |  |  | 02470418088 | CCURE Security Upgrades (including perimeter fencing)-Stephenville | Safety/Security | Highway Trans. Fund 6 | 107520 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
7.4 | 7.4 | 7.4 | 7.4 | 7.4 |  |  |  | 02470418089 | CCURE Security Upgrades (including perimeter fencing)-Weatherford | Safety/Security | Highway Trans. Fund 6 | 107520 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
17 | 17 | 17 | 17 | 17 |  |  |  | 22470418112 | Construct Concrete Flume with Detention Pond- Childress DHQ | Site Work | Highway Trans. Fund 6 | 180000 | 280000 | 2019-08-15 | 0% | 0% | 36560 | 0 | 243440 | Project in design phase, consultant fees encumbered
18 | 18 | 18 | 18 | 18 |  |  |  | 12470418098 | CCURE Security Upgrades (including perimeter fencing)-Conroe | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.1 | 18.1 | 18.1 | 18.1 | 18.1 |  |  |  | 12470418099 | CCURE Security Upgrades (including perimeter fencing)-Houston (Northeast) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.2 | 18.2 | 18.2 | 18.2 | 18.2 |  |  |  | 12470418100 | CCURE Security Upgrades (including perimeter fencing)-Houston (Northwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.3 | 18.3 | 18.3 | 18.3 | 18.3 |  |  |  | 12470418101 | CCURE Security Upgrades (including perimeter fencing)-Houston (South) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.4 | 18.4 | 18.4 | 18.4 | 18.4 |  |  |  | 12470418102 | CCURE Security Upgrades (including perimeter fencing)-Humble | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.5 | 18.5 | 18.5 | 18.5 | 18.5 |  |  |  | 12470418103 | CCURE Security Upgrades (including perimeter fencing)-Lamarque | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
18.6 | 18.6 | 18.6 | 18.6 | 18.6 |  |  |  | 12470418104 | CCURE Security Upgrades (including perimeter fencing)-Rosenberg | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-15 | 0% | 0% | 0 | 0 | 134400
19 | 19 | 19 | 19 | 19 |  |  |  | 02470418090 | CCURE Security Upgrades (including perimeter fencing)-Gordon | Safety/Security | Highway Trans. Fund 6 | 138240 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
19.1 | 19.1 | 19.1 | 19.1 | 19.1 |  |  |  | 02470418091 | CCURE Security Upgrades (including perimeter fencing)-Jacksboro | Safety/Security | Highway Trans. Fund 6 | 138240 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
19.2 | 19.2 | 19.2 | 19.2 | 19.2 |  |  |  | 02470418092 | CCURE Security Upgrades (including perimeter fencing)-Mineral Wells | Safety/Security | Highway Trans. Fund 6 | 138240 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
19.3 | 19.3 | 19.3 | 19.3 | 19.3 |  |  |  | 02470418093 | CCURE Security Upgrades (including perimeter fencing)-Saginaw | Safety/Security | Highway Trans. Fund 6 | 138240 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
19.4 | 19.4 | 19.4 | 19.4 | 19.4 |  |  |  | 02470418094 | CCURE Security Upgrades (including perimeter fencing)-Special Crews (Southeast) | Safety/Security | Highway Trans. Fund 6 | 138240 | 139100 | 2019-11-11 | 100% | 0% | 0 | 0 | 139100 | Cmsn denied approval Aug 2018 - Will re-let in Dec. 2018 - 18085, 18086, 18087, 18088, 18089, 18090, 18091, 18092, 18093, 18094
|  |  | 23 | 23 |  |  |  | 38470418197 | Flight Services - UPS Site Generator, Chiller Repl. - Austin | Safety/Security | Highway Trans. Fund 6 | 1200000 | 990000 | 2019-07-25 | 0% | 0% | 0 | 0 | 990000 | Oct. 2018 bid came in too high. Project will be rescoped.
33 | 33 | 33 | 33 | 33 |  |  |  | 24470418069 | CCURE Security Upgrades (including perimeter fencing)-Alpine | Safety/Security | Highway Trans. Fund 6 | 134400 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
33.1 | 33.1 | 33.1 | 33.1 | 33.1 |  |  |  | 24470418070 | CCURE Security Upgrades (including perimeter fencing)-El Paso (East) | Safety/Security | Highway Trans. Fund 6 | 134400 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
33.2 | 33.2 | 33.2 | 33.2 | 33.2 |  |  |  | 24470418071 | CCURE Security Upgrades (including perimeter fencing)-El Paso (West) | Safety/Security | Highway Trans. Fund 6 | 134400 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
35 | 35 | 35 | 35 | 35 |  |  |  | 17470418049 | CCURE Security Upgrades (including perimeter fencing)-Brenham | Safety/Security | Highway Trans. Fund 6 | 100800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
35.1 | 35.1 | 35.1 | 35.1 | 35.1 |  |  |  | 17470418050 | CCURE Security Upgrades (including perimeter fencing)-Bryan | Safety/Security | Highway Trans. Fund 6 | 100800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
35.2 | 35.2 | 35.2 | 35.2 | 35.2 |  |  |  | 17470418051 | CCURE Security Upgrades (including perimeter fencing)-Hearne | Safety/Security | Highway Trans. Fund 6 | 100800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
35.3 | 35.3 | 35.3 | 35.3 | 35.3 |  |  |  | 17470418052 | CCURE Security Upgrades (including perimeter fencing)-Huntsville | Safety/Security | Highway Trans. Fund 6 | 100800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
38 | 38 | 38 | 38 | 38 |  |  |  | 05470418117 | CCURE Security Upgrades (including perimeter fencing)-Brownfield | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-05-25 | 0% | 0% | 0 | 0 | 134400
38.1 | 38.1 | 38.1 | 38.1 | 38.1 |  |  |  | 05470418118 | CCURE Security Upgrades (including perimeter fencing)-Littlefield | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-04-27 | 0% | 0% | 0 | 0 | 134400
38.2 | 38.2 | 38.2 | 38.2 | 38.2 |  |  |  | 05470418119 | CCURE Security Upgrades (including perimeter fencing)-Plainview | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-04-27 | 0% | 0% | 0 | 0 | 134400
38.3 | 38.3 | 38.3 | 38.3 | 38.3 |  |  |  | 05470418120 | CCURE Security Upgrades (including perimeter fencing)-Post RDC | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-05-25 | 0% | 0% | 0 | 0 | 134400
43.1 | 43.1 | 43.1 | 43.1 | 43.1 |  |  |  | 02470418095 | Construct Box Culvert (Drainage Improvements)-DHQ | Site Work | Highway Trans. Fund 6 | 1200000 | 1200000 | 2019-11-02 | 0% | 0% | 200719 | 0 | 999281 | 02-8095, 96, 97 will be let together. Project in design phase, consultant fees encumbered.
43.2 | 43.2 | 43.2 | 43.2 | 43.2 |  |  |  | 02470418096 | Parking Lot Resurface- Ft. Worth DHQ | Site Work | Highway Trans. Fund 6 | 240000 | 240000 | 2019-11-02 | 0% | 0% | 40144 | 0 | 199856 | 02-8095, 96, 97 will be let together. Project in design phase, consultant fees encumbered.
50 | 50 | 50 | 50 | 50 |  |  |  | 12470418105 | Building Renovation-Houston NW | Capital Repairs | Highway Trans. Fund 6 | 5000000 | 6069477 | 2019-10-11 | 0% | 0% | 193869 | 0 | 5875608 | Received $12.5M in June 2018, added $2M to this project. Project 12-8105, 06, 07, & 08 in design phase, consultant fees encumbered. Increased scope and estimate to $5M in June 2018
54 | 54 | 54 | 54 | 54 |  |  |  | 24470418072 | CCURE Security Upgrades (including perimeter fencing)-Canutillo | Safety/Security | Highway Trans. Fund 6 | 109964 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
54.1 | 54.1 | 54.1 | 54.1 | 54.1 |  |  |  | 24470418073 | CCURE Security Upgrades (including perimeter fencing)-Dell City | Safety/Security | Highway Trans. Fund 6 | 109964 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
54.2 | 54.2 | 54.2 | 54.2 | 54.2 |  |  |  | 24470418074 | CCURE Security Upgrades (including perimeter fencing)-Fort Davis | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
54.3 | 54.3 | 54.3 | 54.3 | 54.3 |  |  |  | 24470418075 | CCURE Security Upgrades (including perimeter fencing)-Fort Hancock | Safety/Security | Highway Trans. Fund 6 | 109964 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
54.4 | 54.4 | 54.4 | 54.4 | 54.4 |  |  |  | 24470418076 | CCURE Security Upgrades (including perimeter fencing)-Marathon | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
54.5 | 54.5 | 54.5 | 54.5 | 54.5 |  |  |  | 24470418077 | CCURE Security Upgrades (including perimeter fencing)-Marfa | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
54.6 | 54.6 | 54.6 | 54.6 | 54.6 |  |  |  | 24470418078 | CCURE Security Upgrades (including perimeter fencing)-Pine Springs | Safety/Security | Highway Trans. Fund 6 | 109964 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
54.7 | 54.7 | 54.7 | 54.7 | 54.7 |  |  |  | 24470418079 | CCURE Security Upgrades (including perimeter fencing)-Presidio | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
54.8 | 54.8 | 54.8 | 54.8 | 54.8 |  |  |  | 24470418080 | CCURE Security Upgrades (including perimeter fencing)-Sierra Blanca | Safety/Security | Highway Trans. Fund 6 | 109964 | 115259 | 2019-05-19 | 100% | 0% | 115259 | 0 | 0 | Proj 24-8070,71,72,73,75,78,80 let together in June 2018
54.9 | 54.9 | 54.9 | 54.9 | 54.9 |  |  |  | 24470418081 | CCURE Security Upgrades (including perimeter fencing)-Terlingua | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
54.95 | 54.95 | 54.95 | 54.95 | 54.95 |  |  |  | 24470418082 | CCURE Security Upgrades (including perimeter fencing)-Van Horn | Safety/Security | Highway Trans. Fund 6 | 109964 | 133964 | 2019-08-09 | 100% | 0% | 133964 | 0 | 0 | Proj 24-8069,74,76,77,79,81,82 let together in September 2018.
56 | 56 | 56 | 56 | 56 |  |  |  | 14470418034 | CCURE Security Upgrades (including perimeter fencing)-Austin (East) | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.1 | 56.1 | 56.1 | 56.1 | 56.1 |  |  |  | 14470418035 | CCURE Security Upgrades (including perimeter fencing)-Austin (Northwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.2 | 56.2 | 56.2 | 56.2 | 56.2 |  |  |  | 14470418036 | CCURE Security Upgrades (including perimeter fencing)-Austin (West/Southwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.3 | 56.3 | 56.3 | 56.3 | 56.3 |  |  |  | 14470418037 | CCURE Security Upgrades (including perimeter fencing)-Fredericksburg | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.4 | 56.4 | 56.4 | 56.4 | 56.4 |  |  |  | 14470418038 | CCURE Security Upgrades (including perimeter fencing)-Johnson City | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.5 | 56.5 | 56.5 | 56.5 | 56.5 |  |  |  | 14470418039 | CCURE Security Upgrades (including perimeter fencing)-Llano | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.6 | 56.6 | 56.6 | 56.6 | 56.6 |  |  |  | 14470418040 | CCURE Security Upgrades (including perimeter fencing)-Lockhart | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.7 | 56.7 | 56.7 | 56.7 | 56.7 |  |  |  | 14470418041 | CCURE Security Upgrades (including perimeter fencing)-Mason | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.8 | 56.8 | 56.8 | 56.8 | 56.8 |  |  |  | 14470418042 | CCURE Security Upgrades (including perimeter fencing)-San Marcos | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
56.9 | 56.9 | 56.9 | 56.9 | 56.9 |  |  |  | 14470418043 | CCURE Security Upgrades (including perimeter fencing)-Taylor | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
58 | 58 | 58 | 58 | 58 |  |  |  | 17470418053 | CCURE Security Upgrades (including perimeter fencing)-Buffalo | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
58.1 | 58.1 | 58.1 | 58.1 | 58.1 |  |  |  | 17470418054 | CCURE Security Upgrades (including perimeter fencing)-Caldwell | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
58.2 | 58.2 | 58.2 | 58.2 | 58.2 |  |  |  | 17470418055 | CCURE Security Upgrades (including perimeter fencing)-Cameron | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
58.3 | 58.3 | 58.3 | 58.3 | 58.3 |  |  |  | 17470418056 | CCURE Security Upgrades (including perimeter fencing)-Fairfield | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
58.4 | 58.4 | 58.4 | 58.4 | 58.4 |  |  |  | 17470418057 | CCURE Security Upgrades (including perimeter fencing)-Madisonville | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
58.5 | 58.5 | 58.5 | 58.5 | 58.5 |  |  |  | 17470418058 | CCURE Security Upgrades (including perimeter fencing)-Navasota | Safety/Security | Highway Trans. Fund 6 | 156800 | 151218 | 2019-11-19 | 100% | 0% | 151218 | 0 | 0 | Let 17-8049, 50, 51,52,53,54,55,56,57,58 &59 together
60.1 | 60.1 | 60.1 | 60.1 | 60.1 |  |  |  | 05470418121 | CCURE Security Upgrades (including perimeter fencing)-Bovina | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
60.2 | 60.2 | 60.2 | 60.2 | 60.2 |  |  |  | 05470418122 | CCURE Security Upgrades (including perimeter fencing)-Dimmitt | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
60.3 | 60.3 | 60.3 | 60.3 | 60.3 |  |  |  | 05470418123 | CCURE Security Upgrades (including perimeter fencing)-Floydada | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
60.4 | 60.4 | 60.4 | 60.4 | 60.4 |  |  |  | 05470418124 | CCURE Security Upgrades (including perimeter fencing)-Lamesa | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.5 | 60.5 | 60.5 | 60.5 | 60.5 |  |  |  | 05470418125 | CCURE Security Upgrades (including perimeter fencing)-Levelland | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60..6 | 60..6 | 60..6 | 60..6 | 60..6 |  |  |  | 05470418126 | CCURE Security Upgrades (including perimeter fencing)-Lubbock (Northeast) | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.7 | 60.7 | 60.7 | 60.7 | 60.7 |  |  |  | 05470418127 | CCURE Security Upgrades (including perimeter fencing)-Morton | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
60.8 | 60.8 | 60.8 | 60.8 | 60.8 |  |  |  | 05470418128 | CCURE Security Upgrades (including perimeter fencing)-Muleshoe | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
60.9 | 60.9 | 60.9 | 60.9 | 60.9 |  |  |  | 05470418129 | CCURE Security Upgrades (including perimeter fencing)-Plains | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.91 | 60.91 | 60.91 | 60.91 | 60.91 |  |  |  | 05470418130 | CCURE Security Upgrades (including perimeter fencing)-Ralls | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.92 | 60.92 | 60.92 | 60.92 | 60.92 |  |  |  | 05470418131 | CCURE Security Upgrades (including perimeter fencing)-Seminole | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.93 | 60.93 | 60.93 | 60.93 | 60.93 |  |  |  | 05470418132 | CCURE Security Upgrades (including perimeter fencing)-Tahoka | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-25 | 0% | 0% | 0 | 0 | 155100
60.94 | 60.94 | 60.94 | 60.94 | 60.94 |  |  |  | 05470418133 | CCURE Security Upgrades (including perimeter fencing)-Tulia | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-27 | 0% | 0% | 0 | 0 | 155100
69 | 69 | 69 | 69 | 69 |  |  |  | 07470418153 | Installation of Above-Ground Fuel Tank-Big Lake | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-10-09 | 0% | 0% | 66841 | 0 | 353159 | Project 07-8153,54,55,56, & 57 in design phase, consultant fees encumbered
76 | 76 | 76 | 76 | 76 |  |  |  | 15470418158 | Laboratory Building Renovation- San Antonio DHQ | Capital Repairs | Highway Trans. Fund 6 | 2640000 | 2640000 | 2020-05-28 | 0% | 0% | 321495.68 | 0 | 2318504.32 | Project in design phase, consultant fees encumbered.
80 | 80 | 80 | 80 | 80 |  |  |  | 21470418141 | CCURE Security Upgrades (including perimeter fencing)-Hebbronville | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-01-12 | 0% | 0% | 0 | 0 | 100800
80.1 | 80.1 | 80.1 | 80.1 | 80.1 |  |  |  | 21470418142 | CCURE Security Upgrades (including perimeter fencing)-Pharr | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-01-12 | 0% | 0% | 0 | 0 | 100800
80.2 | 80.2 | 80.2 | 80.2 | 80.2 |  |  |  | 21470418143 | CCURE Security Upgrades (including perimeter fencing)-Rio Grande City | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-01-12 | 0% | 0% | 0 | 0 | 100800
80.3 | 80.3 | 80.3 | 80.3 | 80.3 |  |  |  | 21470418144 | CCURE Security Upgrades (including perimeter fencing)-San Benito | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-01-12 | 0% | 0% | 0 | 0 | 100800
82 | 82 | 82 | 82 | 82 |  |  |  | 07470418154 | Installation of Above-Ground Fuel Tank-San Angelo | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-10-09 | 0% | 0% | 66841 | 0 | 353159 | Project 07-8153,54,55,56, & 57 in design phase, consultant fees encumbered
84 | 84 | 84 | 84 | 84 |  |  |  | 04470418002 | CCURE Security Upgrades (including perimeter fencing)-Amarillo (East) | Safety/Security | Highway Trans. Fund 6 | 112000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
84.1 | 84.1 | 84.1 | 84.1 | 84.1 |  |  |  | 04470418003 | CCURE Security Upgrades (including perimeter fencing)-Canyon | Safety/Security | Highway Trans. Fund 6 | 112000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
84.2 | 84.2 | 84.2 | 84.2 | 84.2 |  |  |  | 04470418004 | CCURE Security Upgrades (including perimeter fencing)-Dumas | Safety/Security | Highway Trans. Fund 6 | 112000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
84.3 | 84.3 | 84.3 | 84.3 | 84.3 |  |  |  | 04470418005 | CCURE Security Upgrades (including perimeter fencing)-Pampa | Safety/Security | Highway Trans. Fund 6 | 112000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
92 | 92 | 92 | 92 | 92 |  |  |  | 13470418177 | Building Renovation- Yoakum DHQ | Capital Repairs | Highway Trans. Fund 6 | 1800000 | 1800000 | 2020-01-09 | 0% | 0% | 149663.89 | 0 | 1650336.11 | Project in design phase, consultant fees encumbered.
99 | 99 | 99 | 99 | 99 |  |  |  | 15470418159 | Building Renovation-Transguide | Capital Repairs | Highway Trans. Fund 6 | 1680000 | 1680000 | 2019-11-23 | 0% | 0% | 461356 | 0 | 1218644 | Project in design phase, consultant fees encumbered.
101 | 101 | 101 | 101 | 101 |  |  |  | 24470418083 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 270000 | 379028 | 2219-07-01 | 100% | 0% | 118536 | 0 | 260492 | Project consultant fees encumbered and will be let in December 2018.
102.1 | 102.1 | 102.1 | 102.1 | 102.1 |  |  |  | 21470418145 | CCURE Security Upgrades (including perimeter fencing)-Brownsville | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.3 | 102.3 | 102.3 | 102.3 | 102.3 |  |  |  | 21470418146 | CCURE Security Upgrades (including perimeter fencing)-Edcouch | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.4 | 102.4 | 102.4 | 102.4 | 102.4 |  |  |  | 21470418147 | CCURE Security Upgrades (including perimeter fencing)-Falfurrias | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.5 | 102.5 | 102.5 | 102.5 | 102.5 |  |  |  | 21470418148 | CCURE Security Upgrades (including perimeter fencing)-Mission | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.6 | 102.6 | 102.6 | 102.6 | 102.6 |  |  |  | 21470418149 | CCURE Security Upgrades (including perimeter fencing)-Raymondville | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.7 | 102.7 | 102.7 | 102.7 | 102.7 |  |  |  | 21470418150 | CCURE Security Upgrades (including perimeter fencing)-Santa Isidro | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
102.8 | 102.8 | 102.8 | 102.8 | 102.8 |  |  |  | 21470418151 | CCURE Security Upgrades (including perimeter fencing)-Zapata | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-01-12 | 0% | 0% | 0 | 0 | 172800
105 | 105 | 105 | 105 | 105 |  |  |  | 07470418155 | Installation of Above-Ground Fuel Tank - San Angelo DHQ | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-10-09 | 0% | 0% | 66841 | 0 | 353159 | Project 07-8153,54,55,56, & 57 in design phase, consultant fees encumbered
106.1 | 106.1 | 106.1 | 106.1 | 106.1 |  |  |  | 04470418006 | CCURE Security Upgrades (including perimeter fencing)-Amarillo | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.2 | 106.2 | 106.2 | 106.2 | 106.2 |  |  |  | 04470418007 | CCURE Security Upgrades (including perimeter fencing)-Borger | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.3 | 106.3 | 106.3 | 106.3 | 106.3 |  |  |  | 04470418008 | CCURE Security Upgrades (including perimeter fencing)-Canadian | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.4 | 106.4 | 106.4 | 106.4 | 106.4 |  |  |  | 04470418009 | CCURE Security Upgrades (including perimeter fencing)-Channing | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.5 | 106.5 | 106.5 | 106.5 | 106.5 |  |  |  | 04470418010 | CCURE Security Upgrades (including perimeter fencing)-Claude | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.6 | 106.6 | 106.6 | 106.6 | 106.6 |  |  |  | 04470418011 | CCURE Security Upgrades (including perimeter fencing)-Dalhart | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.7 | 106.7 | 106.7 | 106.7 | 106.7 |  |  |  | 04470418012 | CCURE Security Upgrades (including perimeter fencing)-Darrouzett | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.8 | 106.8 | 106.8 | 106.8 | 106.8 |  |  |  | 04470418013 | CCURE Security Upgrades (including perimeter fencing)-Groom | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.9 | 106.9 | 106.9 | 106.9 | 106.9 |  |  |  | 04470418014 | CCURE Security Upgrades (including perimeter fencing)-Groover | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.1 | 106.1 | 106.1 | 106.1 | 106.1 |  |  |  | 04470418015 | CCURE Security Upgrades (including perimeter fencing)-Hereford | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.11 | 106.11 | 106.11 | 106.11 | 106.11 |  |  |  | 04470418016 | CCURE Security Upgrades (including perimeter fencing)-Panhandle | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
106.12 | 106.12 | 106.12 | 106.12 | 106.12 |  |  |  | 04470418017 | CCURE Security Upgrades (including perimeter fencing)-Perrington | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.13 | 106.13 | 106.13 | 106.13 | 106.13 |  |  |  | 04470418018 | CCURE Security Upgrades (including perimeter fencing)-Stratford | Safety/Security | Highway Trans. Fund 6 | 120000 | 142458 | 2019-09-10 | 100% | 0% | 142458 | 0 | 0 | Project 04-18004, 18005, 18007, 18008, 18011, 18012, 18014, 18017, 18018 let together in August 2018
106.14 | 106.14 | 106.14 | 106.14 | 106.14 |  |  |  | 04470418019 | CCURE Security Upgrades (including perimeter fencing)-Vega | Safety/Security | Highway Trans. Fund 6 | 120000 | 107217 | 2019-12-27 | 100% | 0% | 107217 | 0 | 0 | Project 04-18002, 18003, 18006, 18009, 18010, 18013, 18015, 18016, 18019 let together in November 2018.
107.1 | 107.1 | 107.1 | 107.1 | 107.1 |  |  |  | 11470418135 | CCURE Security Upgrades (including perimeter fencing)-Center | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
107.2 | 107.2 | 107.2 | 107.2 | 107.2 |  |  |  | 11470418136 | CCURE Security Upgrades (including perimeter fencing)-Crockett | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
107.3 | 107.3 | 107.3 | 107.3 | 107.3 |  |  |  | 11470418137 | CCURE Security Upgrades (including perimeter fencing)-Groveton | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
107.4 | 107.4 | 107.4 | 107.4 | 107.4 |  |  |  | 11470418138 | CCURE Security Upgrades (including perimeter fencing)-Hemphill | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
107.5 | 107.5 | 107.5 | 107.5 | 107.5 |  |  |  | 11470418139 | CCURE Security Upgrades (including perimeter fencing)-Lufkin | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
107.6 | 107.6 | 107.6 | 107.6 | 107.6 |  |  |  | 11470418140 | CCURE Security Upgrades (including perimeter fencing)-Sheperd | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-02-09 | 0% | 0% | 0 | 0 | 156801
109.1 | 109.1 | 109.1 | 109.1 | 109.1 |  |  |  | 19470418020 | CCURE Security Upgrades (including perimeter fencing)-Gilmer | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-25 | 0% | 0% | 0 | 0 | 100800
109.2 | 109.2 | 109.2 | 109.2 | 109.2 |  |  |  | 19470418021 | CCURE Security Upgrades (including perimeter fencing)-Marshall | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-25 | 0% | 0% | 0 | 0 | 100800
109.3 | 109.3 | 109.3 | 109.3 | 109.3 |  |  |  | 19470418022 | CCURE Security Upgrades (including perimeter fencing)-Mount Pleasant | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-25 | 0% | 0% | 0 | 0 | 100800
109.4 | 109.4 | 109.4 | 109.4 | 109.4 |  |  |  | 19470418023 | CCURE Security Upgrades (including perimeter fencing)-Texarkana | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-25 | 0% | 0% | 0 | 0 | 100800
119 | 119 | 119 | 119 | 119 |  |  |  | 13470418178 | Building Renovation-Yoakum DHQ | Capital Repairs | Highway Trans. Fund 6 | 1920000 | 1920000 | 2020-01-09 | 0% | 0% | 0 | 0 | 1920000
120 | 120 | 120 | 120 | 120 |  |  |  | 05470418134 | Building Renovation-Plains | Capital Repairs | Highway Trans. Fund 6 | 1080000 | 181662 | 2018-09-24 | 100% | 100% | 181662 | 0 | 0 | Change in District plans, new project in Seminole only consultant fees encumbered
132 | 132 | 132 | 132 | 132 |  |  |  | 07470418156 | Installation of Above-Ground Fuel Tank-Junction | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-10-09 | 0% | 0% | 66841 | 0 | 353159 | Project 07-8153,54,55,56, & 57 in design phase, consultant fees encumbered
133 | 133 | 133 | 133 | 133 |  |  |  | 13470418180 | Generator Replacement- Yoakum DHQ | Safety/Security | Highway Trans. Fund 6 | 720000 | 720000 | 2020-01-09 | 0% | 0% | 149663.89 | 0 | 570336.11 | Project in design phase, consultant fees encumbered.
138.1 | 138.1 | 138.1 | 138.1 | 138.1 |  |  |  | 03470418173 | CCURE Security Upgrades (including perimeter fencing)-Gainsville | Safety/Security | Highway Trans. Fund 6 | 100800 | 109128 | 2018-12-20 | 100% | 48% | 109128 | 0 | 0 | Let 03-8173, 74, 75 & 76 in May 2018
138.2 | 138.2 | 138.2 | 138.2 | 138.2 |  |  |  | 03470418174 | CCURE Security Upgrades (including perimeter fencing)-Graham | Safety/Security | Highway Trans. Fund 6 | 100800 | 109128 | 2018-12-20 | 100% | 48% | 109128 | 0 | 0 | Let 03-8173, 74, 75 & 76 in May 2018
138.3 | 138.3 | 138.3 | 138.3 | 138.3 |  |  |  | 03470418175 | CCURE Security Upgrades (including perimeter fencing)-Vernon | Safety/Security | Highway Trans. Fund 6 | 100800 | 109128 | 2018-12-20 | 100% | 48% | 109128 | 0 | 0 | Let 03-8173, 74, 75 & 76 in May 2018
138.4 | 138.4 | 138.4 | 138.4 | 138.4 |  |  |  | 03470418176 | CCURE Security Upgrades (including perimeter fencing)-Wichita Falls | Safety/Security | Highway Trans. Fund 6 | 100800 | 109128 | 2018-12-20 | 100% | 48% | 109128 | 0 | 0 | Let 03-8173, 74, 75 & 76 in May 2018
139.1 | 139.1 | 139.1 | 139.1 | 139.1 |  |  |  | 19470418024 | CCURE Security Upgrades (including perimeter fencing)-Carthage | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-25 | 0% | 0% | 0 | 0 | 161280
139.2 | 139.2 | 139.2 | 139.2 | 139.2 |  |  |  | 19470418025 | CCURE Security Upgrades (including perimeter fencing)-Daingerfield | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-25 | 0% | 0% | 0 | 0 | 161280
139.3 | 139.3 | 139.3 | 139.3 | 139.3 |  |  |  | 19470418026 | CCURE Security Upgrades (including perimeter fencing)-Jefferson | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-25 | 0% | 0% | 0 | 0 | 161280
139.4 | 139.4 | 139.4 | 139.4 | 139.4 |  |  |  | 19470418027 | CCURE Security Upgrades (including perimeter fencing)-Linden | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-25 | 0% | 0% | 0 | 0 | 161280
139.5 | 139.5 | 139.5 | 139.5 | 139.5 |  |  |  | 19470418028 | CCURE Security Upgrades (including perimeter fencing)-New Boston | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-25 | 0% | 0% | 0 | 0 | 161280
|  |  | 140.1 | 140.1 |  |  |  | 08470418210 | Abilene DW Generator - Jayton | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.2 | 140.2 |  |  |  | 08470418211 | Abilene DW Generator - Jayton (MNT Yard) | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.3 | 140.3 |  |  |  | 08470418212 | Abilene DW Generator - Gail | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.4 | 140.4 |  |  |  | 08470418213 | Abilene DW Generator - Snyder | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.5 | 140.5 |  |  |  | 08470418214 | Abilene DW Generator - Aspermount | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.6 | 140.6 |  |  |  | 08470418215 | Abilene DW Generator - Baird | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.7 | 140.7 |  |  |  | 08470418216 | Abilene DW Generator - Albany | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.8 | 140.8 |  |  |  | 08470418217 | Abilene DW Generator - Sweetwater | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.9 | 140.9 |  |  |  | 08470418218 | Abilene DW Generator - DHQ | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 140.1 | 140.1 |  |  |  | 08470418219 | Abilene DW Generator - AEM | Safety/Security | Highway Trans. Fund 6 | 150000 | 150000 | 2019-12-10 | 0% | 0% | 0 | 0 | 150000 | Received $12.5M additional appropriation in June 2018 - This project was added.
141 | 141 | 141 | 141 | 141 |  |  |  | 02470418097 | Building Renovation-Ft. Worth DHQ | Capital Repairs | Highway Trans. Fund 6 | 3600000 | 3600000 | 2019-11-02 | 0% | 0% | 602158 | 0 | 2997842 | 02-8095, 96, 97 will be let together. Project in design phase, consultant fees encumbered.
142 | 142 | 142 | 142 | 142 |  |  |  | 14470418044 | Drainage Improvements-San Marcos | Site Work | Highway Trans. Fund 6 | 59447 | 59447 | 2018-06-30 | 100% | 100% | 59447 | 0 | 0 | June 2018 Project will be funded by District - Now reflecting Consultant fees that were incurred.
146 | 146 | 146 | 146 | 146 |  |  |  | 21470418152 | Building Renovation-Pharr DHQ | Capital Repairs | Highway Trans. Fund 6 | 3360000 | 3360000 | 2019-12-24 | 0% | 0% | 564821 | 0 | 2795179 | Project in design phase, consultant fees encumbered
157 | 157 | 157 | 157 | 157 |  |  |  | 07470418157 | Installation of Above-Ground Fuel Tank-Menard | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-10-09 | 0% | 0% | 66841 | 0 | 353159 | Project 07-8153,54,55,56, & 57 in design phase, consultant fees encumbered
|  |  | 159.1 | 159.1 |  |  |  | 09470418233 | Waco DW Generator Program - Hamilton | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-10 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.2 | 159.2 |  |  |  | 09470418234 | Waco DW Generator Program - Meridian | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.3 | 159.3 |  |  |  | 09470418235 | Waco DW Generator Program - Mexia | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.4 | 159.4 |  |  |  | 09470418236 | Waco DW Generator Program - Marlin | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.5 | 159.5 |  |  |  | 09470418237 | Waco DW Generator Program - Special Crews | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.6 | 159.6 |  |  |  | 09470418238 | Waco DW Generator Program - Waco DHQ Admin Bldg | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.7 | 159.7 |  |  |  | 09470418239 | Waco DW Generator Program - Waco DHQ Lab Bldg | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 159.8 | 159.8 |  |  |  | 09470418240 | Waco DW Generator Program - Waco DHQ Ops Bldg | Safety/Security | Highway Trans. Fund 6 | 315000 | 315000 | 2019-12-18 | 0% | 0% | 0 | 0 | 315000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.1 | 166.1 |  |  |  | 19470418200 | Atlanta DW Generator - Carthage | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.2 | 166.2 |  |  |  | 19470418201 | Atlanta DW Generator - Daingerfield | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.3 | 166.3 |  |  |  | 19470418202 | Atlanta DW Generator - Gilmer | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.4 | 166.4 |  |  |  | 19470418203 | Atlanta DW Generator - Mt. Pleasant | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.5 | 166.5 |  |  |  | 19470418204 | Atlanta DW Generator - New Bosto | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.6 | 166.6 |  |  |  | 19470418205 | Atlanta DW Generator - Texarkana | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.7 | 166.7 |  |  |  | 19470418206 | Atlanta DW Generator - Jefferson | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-23 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.8 | 166.8 |  |  |  | 19470418207 | Atlanta DW Generator - Linden | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-24 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
|  |  | 166.9 | 166.9 |  |  |  | 19470418208 | Atlanta DW Generator - Marshall | Safety/Security | Highway Trans. Fund 6 | 360000 | 360000 | 2019-10-24 | 0% | 0% | 0 | 0 | 360000 | Received $12.5M additional appropriation in June 2018 - This project was added.
192 | 192 | 192 | 192 | 192 |  |  |  | 14470418182 | Roof Replacement-Southwest Austin MNT | Roofing | Highway Trans. Fund 6 | 350000 | 184299 | 2018-12-01 | 100% | 83% | 184299 | 0 | 0 | Let July 2018
|  |  | 208 | 208 |  |  |  | 16470403034-2 | Alice Waterwell other half from 16/17 16470403034 | Site Work | Highway Trans. Fund 6 | 0 | 1357000 | 2019-08-30 | 100% | 0% | 1357000 | 0 | 0 | Phase moved from16/17, Phase II approved
274.1 | 274.1 | 274.1 | 274.1 | 274.1 |  |  |  | 14470418029 | CCURE Security Upgrades (including perimeter fencing)-Austin (North) | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
274.2 | 274.2 | 274.2 | 274.2 | 274.2 |  |  |  | 14470418030 | CCURE Security Upgrades (including perimeter fencing)-Austin | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
274.3 | 274.3 | 274.3 | 274.3 | 274.3 |  |  |  | 14470418031 | CCURE Security Upgrades (including perimeter fencing)-Bastrop | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
274.4 | 274.4 | 274.4 | 274.4 | 274.4 |  |  |  | 14470418032 | CCURE Security Upgrades (including perimeter fencing)-Burnett | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
274.5 | 274.5 | 274.5 | 274.5 | 274.5 |  |  |  | 14470418033 | CCURE Security Upgrades (including perimeter fencing)-Georgetown | Safety/Security | Highway Trans. Fund 6 | 134400 | 187844 | 2019-04-27 | 100% | 52% | 88147 | 99697 | 0 | 14-8029-43 Let together Feb 2018
U1 | U1 | U1 | U1 | U1 |  |  |  |  | Statewide Unspecified Repairs | Safety/Security | Highway Trans. Fund 6 | 4660836 | 242135 | 2019-08-31 | 0% | 0% | 0 | 0 | 242135
PROJECTS LISTED ABOVE CURRENTLY FUNDED $62.5M | [11 empty] | 62500000 | 62500000 |  |  |  | 13907049.46 | 2618996 | 45973954.54
HURRICANE HARVEY RELIEF DM PROJECTS $493M
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q3 AY18) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
FY18 Q1 JOC Priority | FY18 Q2 JOC Priority | FY18 Q3 JOC Priority | FY18 Q4 JOC Priority | FY19 Q5 JOC Priority | FY19 Q6 JOC Priority | FY19 Q7 JOC Priority | FY19 Q8 JOC Priority
|  | AF1 | AF1 | AF1 |  |  |  | 16470418701 | Maintenance Building Rehabilitation (Harvey) - Beaumont District | Capital Repairs | Highway Trans. Fund 6 | 39000 | 39000 | 2/30/19 | 0% | 0% | 0 | 0 | 39000
|  | AF2 | AF2 | AF2 |  |  |  | 16470418702 | Rehabilitate Boardwalk, Arbors, Kiosk (Harvey) - Beaumont District | Capital Repairs | Highway Trans. Fund 6 | 52000 | 52000 | 2019-12-31 | 0% | 0% | 0 | 0 | 52000
|  | AF3 | AF3 | AF3 |  |  |  | 16470418703 | Landscaping Rehabilitation (Harvey) - Beaumont District | Capital Repairs | Highway Trans. Fund 6 | 78000 | 78000 | 2019-03-29 | 0% | 0% | 0 | 0 | 78000
|  | AF4 | AF4 | AF4 |  |  |  | 16470418704 | Lift Station Repairs (Harvey) -Beaumont District | Capital Repairs | Highway Trans. Fund 6 | 91000 | 91000 | 4/31/19 | 0% | 0% | 0 | 0 | 91000
|  | AF5 | AF5 | AF5 |  |  |  | 16470418705 | Portable Restrooms (Harvey) - Beaumont District | Capital Repairs | Highway Trans. Fund 6 | 98000 | 98000 | 2019-03-31 | 0% | 0% | 29048 | 0 | 68952 | Consultant fees encumbered
|  | AF6 | AF6 | AF6 |  |  |  | 16470418706 | Maintenance Building Roof Replacement (Harvey) - Corpus Christi District | Capital Repairs | Highway Trans. Fund 6 | 135000 | 135000 | 2019-07-19 | 0% | 0% | 0 | 0 | 135000
HURRICANE HARVEY RELIEF DM PROJECTS $493,000 | [11 empty] | 493000 | 493000 |  |  |  | 29048 | 0 | 463952
DEFERRED DM PROJECTS
30 | 30 | 30 | 30 | 30 |  |  |  | 22470418113 | Parking Lot Expansion (Northeast)-DHQ | Site Work | Highway Trans. Fund 6 | [8 empty] | 3/2/18 Will be done with other funds
87 | 87 | 87 | 87 | 87 |  |  |  | 09470418168 | Well Improvements and Waterline Replacement-Marlin | Capital Repairs | Highway Trans. Fund 6 | [8 empty] | 3/2/18 Will be done with other funds
39 | 39 | 39 | 39 | 39 |  |  |  | 22470418114 | Building Renovation-Comstock | Capital Repairs | Highway Trans. Fund 6 | [8 empty] | Q3 AY18 moved below line
148 | 148 | 148 | 148 | 148 |  |  |  | 22470418116 | Building Renovation-Brackettville | Capital Repairs | Highway Trans. Fund 6 | [8 empty] | Q3 AY18 moved below line
| E8 | E8 | E8 | E8 |  |  |  | 16470418188 | Rockport demolition and renovation | Capital Repairs | Highway Trans. Fund 6 | [8 empty] | This project will be combined with New Rockport MNT project with new funds granted in May 2018.
113 | 113 | 113 | 113 | 113 |  |  |  | 22470418115 | Building Renovation-La Pryor | Capital Repairs | Highway Trans. Fund 6
143 | 143 | 143 | 143 | 143 |  |  |  | 14470418044 | Drainage Improvements-San Marcos | Site Work | Highway Trans. Fund 6 | [8 empty] | Project in design phase, consultant fees incurred. Anticipate project scope to change.
65 | 65 | 65 | 65 | 65 |  |  |  | 12470418106 | Building Demolition-Houston NW | Site Work | Highway Trans. Fund 6 | [8 empty] | Project moved below line, expanding work in Project 12-18105
79 | 79 | 79 | 79 | 79 |  |  |  | 12470418107 | Replacement of Generator (Campus-wide)-Houston NW | HVAC | Highway Trans. Fund 6 | [8 empty] | Project moved below line, expanding work in Project 12-18105
122 | 122 | 122 | 122 | 122 |  |  |  | 12470418108 | Installation of Above-Ground Fuel Tank-Houston NW | Site Work | Highway Trans. Fund 6 | [8 empty] | Project moved below line, expanding work in Project 12-18105
TOTAL OF INITIAL $62,993,000 DM AY18-19 DM PROJECTS | [11 empty] | 62993000 | 62993000 |  |  |  | 13936097.46 | 2618996 | 46437906.54
Note on A7: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on A219: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on C219: Diana Miller: Now Ordering based on Start Sheet Dates

## TxDOT New Const.
[8 empty] | 2668 | Texas Department of Transportation #601
[8 empty] | Date: | 12/11/18 Final
Priority Audit Trail | [7 empty] | Prepared by: | Diana Miller, Facilities Business Operations Manager - Support Services Division
CAMPUS CONSOLIDATION - NEW CONSTRUCTION
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q5 AY18-19) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
AY18-19 Q1 JOC Priority | AY18-19 Q2 JOC Priority | AY18-19 Q3 JOC Priority | AY18-19 Q4 JOC Priority | AY18-19 Q5 JOC Priority | AY18-19 Q6 JOC Priority | AY18-19 Q7 JOC Priority | AY18-19 Q8 JOC Priority
1NC | 1NC | 1NC | 1NC | 1NC |  |  |  | 38470418001 | Campus Consolidation Design | New Construction | Highway Trans. Fund 6 | 30000000 | 30000000 | 2022-01-09 | 10% | 0% | 8173952 | 21826048 | 0 | Planning, design and site preparation only.
TOTAL CAMPUS CONSOLIDATION - NEW CONSTRUCTION $30,000,000 | [11 empty] | 30000000 | 30000000 |  |  |  | 8173952 | 21826048 | 0
RADIO TOWERS $6,000,000 - NEW CONSTRUCTION | [11 empty] | #REF! | #REF! |  |  |  | #REF! | #REF! | #REF!
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q3 AY18) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
AY18-19 Q1 JOC Priority | AY18-19 Q2 JOC Priority | AY18-19 Q3 JOC Priority | AY18-19 Q4 JOC Priority | AY18-19 Q5 JOC Priority | AY18-19 Q6 JOC Priority | AY18-19 Q7 JOC Priority | AY18-19 Q8 JOC Priority
ERT 1 | ERT 1 | ERT 1 | ERT 1 | ERT 1 |  |  |  | 20470418604 | Radio Tower Replacement of 400 - Beaumont | New Construction | Highway Trans. Fund 6 | 500000 | 732854 | 2018-07-27 | 100% | 100% | 40072.2 | 692781.8 | 0 | Awarded Oct. 2017
442 | 442 | 442 | 442 | 442 |  |  |  | 03470418613 | Radio Tower Replacement of 175' - Wichita Falls | New Construction | Highway Trans. Fund 6 | 250000 | 206086 | 2019-04-06 | 100% | 0% | 206086 | 0 | 0 | Awarded in Q4 AY18
504 | 504 | 504 | 504 | 504 |  |  |  | 25470418612 | Radio Tower Replacement of 175' - Childress | New Construction | Highway Trans. Fund 6 | 250000 | 206086 | 2019-04-06 | 100% | 0% | 206086 | 0 | 0 | Awarded in Q4 AY18
630 | 630 | 630 | 630 | 630 |  |  |  | 14470418601 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2019-12-05 | 0% | 0% | 0 | 0 | 450000
712 | 712 | 712 | 712 | 712 |  |  |  | 04470418615 | Radio Tower Replacement of 175' - Amarillo | New Construction | Highway Trans. Fund 6 | 250000 | 243579 | 2019-06-14 | 100% | 0% | 243579 | 0 | 0 | Awarded in Q4 AY18
743 | 743 | 743 | 743 | 743 |  |  |  | 07470418608 | Radio Tower Replacement of 300' - San Angelo | New Construction | Highway Trans. Fund 6 | 400000 | 457672 | 2019-01-04 | 100% | 0% | 457672 | 0 | 0 | Project Awarded in Feb. 2018
|  | ERT2 | ERT2 | ERT2 |  |  |  | 07470418624 | San Angelo Radio Tower | New Construction | Highway Trans. Fund 6 |  | 243579 | 2019-06-14 | 100% | 0% | 243579 | 0 | 0 | Awarded in Q4 AY18
|  | ERT3 | ERT3 | ERT3 |  |  |  | 11470418620 | Lufkin Radio Tower | New Construction | Highway Trans. Fund 6 |  | 234454 | 2019-06-16 | 100% | 0% | 234454 | 0 | 0 | Awarded in Q4 AY18
|  | ERT4 | ERT4 | ERT4 |  |  |  | 13470418622 | Yoakum Radio Tower | New Construction | Highway Trans. Fund 6 |  | 228445 | 2019-06-14 | 100% | 0% | 228445 | 0 | 0 | Awarded in Q4 AY18
|  | ERT5 | ERT5 | ERT5 |  |  |  | 15470418623 | San Antonio Radio Tower | New Construction | Highway Trans. Fund 6 |  | 228445 | 2019-06-14 | 100% | 0% | 228445 | 0 | 0 | Awarded in Q4 AY18
|  | ERT6 | ERT6 | ERT6 |  |  |  | 20470418621 | Beaumont Radio Tower | New Construction | Highway Trans. Fund 6 |  | 234454 | 2019-06-16 | 100% | 0% | 234454 | 0 | 0 | Awarded in Q4 AY18
SUBTOTAL 2018 RADIO TOWERS | [11 empty] | 2100000 | 3465654 |  |  |  | 2322872.2 | 692781.8 | 450000
461 | 461 | 461 | 461 | 461 |  |  |  | 03470418614 | Radio Tower Replacement of 175' - Wichita Falls | New Construction | Highway Trans. Fund 6 | 250000 | 200000 | 2020-02-02 | 0% | 0% | 0 | 0 | 200000
705 | 705 | 705 | 705 | 705 |  |  |  | 23470418605 | Radio Tower Replacement of 175' - Brownwood | New Construction | Highway Trans. Fund 6 | 250000 | 450000 | 2020-02-19 | 0% | 0% | 0 | 0 | 450000
719 | 719 | 719 | 719 | 719 |  |  |  | 04470418609 | Radio Tower Replacement of 350' - Amarillo | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2020-01-07 | 0% | 0% | 0 | 0 | 450000
732 | 732 | 732 | 732 | 732 |  |  |  | 17470418606 | Radio Tower Replacement of 300' - Bryan | New Construction | Highway Trans. Fund 6 | 400000 | 400000 | 2019-11-28 | 0% | 0% | 0 | 0 | 400000
|  | ERT7 | ERT7 | ERT7 |  |  |  | 18470418625 | Radio Tower 400' - Kaufman | New Construction | Highway Trans. Fund 6 |  | 510000 | 2020-03-18 | 0% | 0% | 0 | 0 | 510000 | Added in Q3 AY18
U2 | U2 | U2 | U2 | U2 |  |  |  |  | Unanticipated Emergency Tower Replacement | New Construction | Highway Trans. Fund 6 | 2550000 | 524346 | 2019-09-30 | 0% | 0% | 0 | 0 | 524346
SUBTOTAL 2019 RADIO TOWERS | [11 empty] | 3900000 | 2534346 |  |  |  | 0 | 0 | 2534346
615 | 615 | 615 | 615 | 615 |  |  |  | 14470418602 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
648 | 648 | 648 | 648 | 648 |  |  |  | 14470418603 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
700 | 700 | 700 | 700 | 700 |  |  |  | 21470418607 | Radio Tower Replacement of 300' - Pharr | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
706 | 706 | 706 | 706 | 706 |  |  |  | 19470418610 | Radio Tower Replacement of 175' - Atlanta | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
713 | 713 | 713 | 713 | 713 |  |  |  | 19470418611 | Radio Tower Replacement of 175' - Atlanta | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
|  | ERT9 | ERT9 | ERT9 |  |  |  | 10470418627 | Radio Tower 175' - Mineola | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed Q3 AY18
|  | ERT8 | ERT8 | ERT8 |  |  |  | 10470418626 | Radio Tower 175' - Jacksonville | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed August 2018
|  | ERT10 | ERT10 | ERT10 |  |  |  | 21470418618 | Radio Tower Replacement of 300' Pharr | New Construction | Highway Trans. Fund 6 | [8 empty] | Removed August 2018
SUBTOTAL RADIO TOWERS NO LONGER ON PLAN | [11 empty] | 0 | 0 |  |  |  | 0 | 0 | 0
TOTAL RADIO TOWERS - NEW CONSTRUCTION $6,000,000 | [11 empty] | 6000000 | 6000000 |  |  |  | 2322872.2 | 692781.8 | 2984346
HURRICANE HARVEY RELIEF $6,850,000 - NEW CONSTRUCTION PROJECTS
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q3 AY18) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
AY18-19 Q1 JOC Priority | AY18-19 Q2 JOC Priority | AY18-19 Q3 JOC Priority | AY18-19 Q4 JOC Priority | AY18-19 Q5 JOC Priority | AY18-19 Q6 JOC Priority | AY18-19 Q7 JOC Priority | AY18-19 Q8 JOC Priority
|  | AF0 | AF0 | AF0 |  |  |  | 16470418700 | Demolish and Replace MNT Facility on Site (Harvey) - Corpus Christi Dist. Includes 16-8188 work moved from DM. | New Construction | Highway Trans. Fund 6 | 6500000 | 6500000 | 2020-06-20 | 0% | 0% | 385134 | 0 | 6114866 | Consultant Fees encumbered
|  | AF7 | AF7 | AF7 |  |  |  | 16470418707 | Replace Radio Tower (Harvey) - Corpus Christi District | New Construction | Highway Trans. Fund 6 | 350000 | 350000 | 2019-09-30 | 0% | 0% | 0 | 0 | 350000
TOTAL HURRICANE HARVEY RELIEF NEW CONSTRUCTION PROJECTS - $6,850,000 | [11 empty] | 6850000 | 6850000 |  |  |  | 385134 | 0 | 6464866
TOTAL ALL NEW CONSTRUCTION PROJECTS - $42,850,000 | [11 empty] | 42850000 | 42850000 |  |  |  | 10881958.2 | 22518829.8 | 9449212
Note on A8: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on C8: Diana Miller: Now Ordering based on Start Sheet Dates
Note on A15: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on C15: Diana Miller: Now Ordering based on Start Sheet Dates
Note on A49: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on C49: Diana Miller: Now Ordering based on Start Sheet Dates

## TxDOT Space planning
TxDOT SPACE NEEDS REPORT
Pursuant to Article IX, Section 18.10 General Appropriations Act, 84th Legislature, state agencies, or the facilities Commission on behalf of state agencies, shall notify the committee of any need for new space, exceeding 50,000 square feet, expected in the next ten years, no later than 30 days after a need for new space is confirmed.
5002 Construction of Buildings and Facilities |  | Anticipated Space Needed | AY2018 | AY2020 | AY2022 | $ Reported on AY 18/19
1 | Campus Consolidation | 500,000 sq/ft |  | 147775000 |  | 30000000
2 | New Paris District Headquarters Campus | 50,000 sq/ft |  | 15000000 |  | 270000
3 | El Paso District Headquarters Campus (24470418083) | 50,000 sq/ft |  |  | 24000000 | No

## THC
| Agency: | Texas Historical Commission (808)
| Date: | 2018-11-30
| Prepared by: | Kenneth Biddle
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 2nd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 808-18-0450 | Mission Dolores State Historic Site, San Augustine, San Augustine County, Texas | Renovate the museum and laboratory buildings and construct a maintenance building to provide an improved educational experience to visitors. | Economic Stabilization Fund (Fund 0599) | 1425000 | 1425000 | 2019-08-31 | 100% | 0% | 1048744.5 | 132528.58 | 243726.92 | Yes
2 | 808-17-0452 | San Felipe de Austin State Historic Site, San Felipe, Austin County, Texas | Construct a new museum, exhibits and maintenance building to provide an improved educational experience to visitors. | Economic Stabilization Fund (Fund 0599) & General Revenue - Sporting Goods Sales Tax (Fund 0001) | 2000000 | 2000000 | 2018-04-30 | 100% | 100% |  | 2000000 | 0 | Yes
3 | 808-18-0449 | National Museum of the Pacific War, Fredericksburg, Gillespie County, Texas | Renovate the interior of the Admiral Nimitz Hotel to enhance efficiency and improve the visitor experience. | Economic Stabilization Fund (Fund 0599) | 2000000 | 2000000 | 2019-08-31 | 100% | 0% | 808159.4 | 191840.6 | 1000000 | Yes
4 | 808-18-STAFF | Mission Dolores State Historic Site, San Augustine, San Augustine County, Texas | Mission Dolores State Historic Site - Staffing (two years) | Economic Stabilization Fund (Fund 0599) | 575000 | 575000 | 2019-08-31 | N/A | N/A | 13983.51 | 270197.3 | 290819.19 | Yes
5 | 808-19-X1B56 | Roof Repairs - State Historic Sites (Statewide) | FY 19: Conduct necessary roof repairs at various sites in order to safeguard the buildings and their contents. | Economic Stabilization Fund (Fund 0599) | 204000 | 204000 | 2019-08-31 | 0% | 0% | 0 | 0 | 204000 | Yes
6 | 808-19-X2G42 | Interior Renovations - State Historic Sites (Statewide) | FY 19: Conduct renovations to various buildings in order to enhance function and interpretation | Economic Stabilization Fund (Fund 0599) | 146000 | 146000 | 2019-08-31 | 0% | 0% | 0 | 0 | 146000 | Yes
|  |  |  | Totals: | 6350000 | 6350000 |  |  |  | 1870887.41 | 2594566.48 | 1884546.11

## THC sup.
| Agency: | Texas Historical Commission (808)
| Date: | 2018-11-30
| Prepared by: | Kenneth Biddle
Project Priority | Supplemental Information
1, 4 | Texas Historical Commission Rider 26 requires THC to not spend less than $1,425,000 on Deferred Maintenance projects at the Mission Dolores State Historic Site. The remaining $575,000 is intended for staffing at the site for FYs 2018-2019. Hawkins Architects have been contracted for the Architectural/Engineering Services. THC Rider 2 splits the capital funding evenly $712,500 in each year of the biennium.
2 | This is a continuation of the new Construction project for which appropriations were made by the 83rd and 84th Legislatures. This is funded with $750,000 of Economic Stabilization Funds (Fund 0599) and $1,250,000 of GR - Sporting Goods Sales Tax (Fund 0001). THC Rider 26 requires not less than $2,000,000 be spent on the San Felipe de Austin State Historic Site. THC Rider 2 splits the capital funding evenly $1,000,000 in each year of the biennium. The project has been completed.
3 | THC Rider 26 requires not less than $2,000,000 be spent on the National Museum of the Pacific War. McKinney York Architects have been contracted for the Architectural/Engineering Services. Duecker Construction Co. has been contracted for the renovations. THC Rider 2 splits the capital funding evenly $1,000,000 in each year of the biennium.
5 | THC Rider 26 requires not less than $350,000 be spent on the deferred maintenance projects at State Historic Sites. THC Rider 2 splits the capital funding evenly $175,000 in each year of the biennium. There are multiple sites with roof replacement needs.
6 | THC Rider 26 requires not less than $350,000 be spent on the deferred maintenance projects at State Historic Sites. THC Rider 2 splits the capital funding evenly $175,000 in each year of the biennium. There are multiple sites with interior renovation needs.

## SPB
| Agency: | STATE PRESERVATION BOARD (809)
| Date: | 2018-12-18
| Prepared by: | BOB CASH, CYNTHIA PROVINE
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 4th Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | CRP18001 | Capitol Elevator Modernization/Upgrade Phase 1 | Modernization of all Capitol and Extension Elevators. Project is in the design / RFQ phase. RFQ to be issued in the next month. Delayed due to Special Session | FUND 0001 | 1250000 | 1250000 | 2019 | 90% | 10% | 161654.5 | 78689 | 1009656.5 | Consultant is engaged in design and MEP has been selected. CDs' 95% complete. Bid package to Elevator vendors due by 12/21/18. RFP will be issued at beginning of January, 2019.
2 | CRP18017 | Capitol Elevator Modernization/Upgrade Phase 2 | Modernization of all Capitol and Extension Elevators. Project is in the design / RFQ phase. RFQ to be issued in the next month. Delayed due to Special Session | FUND 0001 | 1250000 | 1250000 | 2019 | 90% | 5% | 0 | 0 | 1250000 | Consultant is engaged in design and MEP has been selected. CDs' 95% complete. Bid package to Elevator vendors due by 12/21/18. RFP will be issued at beginning of January, 2019
3 | CRP18015 | HVAC Automation System Upgrade Capitol Extension | RFP for materials being crafted, expect issue of RFP in the next 3 months - Delayed due to Special Session | FUND 0001 | 2200000 | 2200000 | 2018-06-01 | 95% | 45% | 0 | 288760 | 1911240 | Materials have arrived and systems are being programmed for installation. CPU / System upgrades have been in stalled and N4 is up and running. All software licenses have been obtained and updated. Installation of field devices under way.
0
0
0
0
0
0
|  |  |  | Totals: | 4700000 | 4700000 |  |  |  | 161654.5 | 367449 | 4170896.5

## DSHS
| Agency: | Department of State Health Services - 537
| Date: | 2018-12-15
| Prepared by: | Amanda Hudson
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 3rd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 53700 | TCID Building Renovation | HVAC Repair/Replacement | ESF (other) | 623772 | 623772 | 2019-08-31 | 10% | 0% | 10415 | 0 | 613357 | Health and Human Services Commission manages and implements 18-403 TCD HVAC Repair/Replacement for Bldg. 533. The repair/replacement is pending a new architect engineer but the initial assessment is complete. A schedule and action plan are now being developed for the project. Once approved, the project duration should be within 6 months.
1 | 53700 | TCID Building Renovation | Roof Repairs and Replacements | ESF (other) | 776228 | 776228 | 2019-07-31 | 100% | 3% | 14741 | 22111 | 739376 | Health and Human Services Commission manages and implements 18-402-TCD Roof replacement for BLG 501 administration building. Construction documents for roofing consultant were submitted on June 15. Pending delegation from the Comptroller to start the solicitation process. Construction will start in the winter with a duration of 90 days depending on weather.
2 | 53700 | Laboratory Deferred Maintenance | Texas Facilities Commission Contract # 13-109 | General Revenue | 186193 | 186193 | 2019-08-31 | 0% | 0% | 0 | 186193 | 0 | Funds have been expended under Texas Facilities Commission Contract 13-109 for chemical fume hoods in the DSHS Laboratory.
2 | 53700 | Laboratory Deferred Maintenance | Miscellaneous Building Repair and Renovation Costs | General Revenue | 213807 | 213807 | 2019-08-31 | 0% | 0% | 0 | 0 | 213807 | The estimated cost for Roof Repairs on the South Texas Lab are $50K. Renovations are needed for BAX Q7 and UPS lab equipment which are currently awaiting firm estimates. Remaining funds will be utilized for unplanned building repairs, as well as renovation costs that will be required as part of purchasing miscellaneous laboratory equipment. Funds anticipated to be fully expended by 08/31/19.
|  |  | Totals: |  | 1800000 | 1800000 |  |  |  | 25156 | 208304 | 1566540
1800000

## HHSC-SH
| Agency: | HHSC 529 State Hospitals
| Date: | 2018-11-30
| Prepared by: | HHSC State-Operated Facilities Division - Facilities Support Services
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 16-012-KSH | Kerrville State Hospital | HVAC & Chiller Replacement | ESF (other) | 80100 | 1070300 | TBD | 100% | 87.16% | 125096.54 | 932834.25 | 12369.21
1 | 16-018-RSH | Rusk State Hospital | Fire Escape & Wall Replacement | ESF (other) | 1502187 | 1489834 | TBD | 100% | 0% | 0 | 0 | 1489834
1 | 17-003-RSH | Rusk State Hospital | Site Drainage Corrections | ESF (other) |  | 533366.65 | TBD | 100% | 0% | 11440 | 0 | 521926.65
1 | 17-006-WCY | Waco Center for Youth | Security Fence Installation | ESF (other) | 200000 | 0 | TBD | 100% | 0% | 0 | 0 | 0
1 | 18-001-ASH | Austin State Hospital | Anti-Ligature & Hardware | ESF (other) | 2432595.69 | 2316758 | TBD | 100% | 0% | 165376 | 41344 | 2110038
1 | 18-002-BSH | Big Spring State Hospital | Roof Repairs & Replacement | ESF (other) | 655961.25 | 624725 | TBD | 100% | 0% | 24398.44 | 31073.41 | 569253.15
1 | 18-003-BSH | Big Spring State Hospital | Sanitary Sewer Repair | ESF (other) | 5515938.75 | 5253275 | TBD | 100% | 0% | 198298.19 | 125874.55 | 4929102.26
1 | 18-004-BSH | Big Spring State Hospital | Electrical Upgrades | ESF (other) | 3081366.75 | 2934635 | TBD | 100% | 0% | 87777 | 107283 | 2739575
1 | 18-005-BSH | Big Spring State Hospital | Anti-Ligature & Exterior Stairs | ESF (other) | 4810165.5 | 4581110 | TBD | 100% | 0% | 240423.6 | 71215.9 | 4269470.5
1 | 18-006-EPC | El Paso Psychiatric Center | HVAC Control Replacement | ESF (other) | 572985.23 | 545700 | TBD | 100% | 0% | 50268.15 | 8870.85 | 486561
1 | 18-007-KSH | Kerrville State Hospital | Chiller & Boiler Replacements | ESF (other) | 3225984.3 | 3072366 | TBD | 100% | 0% | 259544 | 68694 | 2744128
1 | 18-008-KSH | Kerrville State Hospital | Security Fence | ESF (other) | 1260000 | 1200000 | TBD | 0% | 0% | 0 | 0 | 1200000
1 | 18-009-KSH | Kerrville State Hospital | Roof Repairs & Replacement | ESF (other) | 3434026.05 | 3270501 | TBD | 100% | 0% | 73806.25 | 44283.75 | 3152411
1 | 18-010-VSH | North Texas State Hospital - Vernon | Utility Upgrades | ESF (other) | 3132141.6 | 2842713 | TBD | 100% | 0% | 0 | 0 | 2842713
1 | 18-011-VSH | North Texas State Hospital - Vernon | Roofing Replacements | ESF (other) | 2462341.35 | 2345087 | TBD | 100% | 0% | 79641.9 | 97340.1 | 2168105
1 | 18-012-VSH | North Texas State Hospital - Vernon | Water Tank Repairs | ESF (other) | 590110.5 | 502751 | TBD | 100% | 100% | 0 | 502751 | 0
1 | 18-013-VSH | North Texas State Hospital - Vernon | Anti-Ligature & Kitchen Expansion | ESF (other) | 3456716.55 | 3292111 | TBD | 100% | 0% | 212421 | 46629 | 3033061
1 | 18-014-WFH | North Texas State Hospital - Wichita Falls | Building Renovations | ESF (other) | 5107200 | 4864000 | TBD | 100% | 0% | 145500 | 222725 | 4495775
1 | 18-015-WFH | North Texas State Hospital - Wichita Falls | Emergency Generator | ESF (other) | 268800 | 256000 | TBD | 100% | 0% | 28384.2 | 18922.8 | 208693
1 | 18-016-WFH | North Texas State Hospital - Wichita Falls | Roof Replacements | ESF (other) | 2100000 | 2000000 | TBD | 100% | 0% | 189300 | 24975 | 1785725
1 | 18-017-RSC | Rio Grande State Center | Building Renovations | ESF (other) | 2784091.8 | 2651516 | TBD | 100% | 0% | 73462.95 | 103428.05 | 2474625
1 | 18-018-RSC | Rio Grande State Center | Sewer Repair | ESF (other) | 400590.75 | 381515 | TBD | 100% | 0% | 14379 | 40468.5 | 326667.5
1 | 18-019-RSH | Rusk State Hospital | Anti-ligature & Hardware Upgrade | ESF (other) | 5681688.6 | 5411132 | TBD | 50% | 0% | 369000 | 0 | 5042132
1 | 18-020-RSH | Rusk State Hospital | Emergency Generators | ESF (other) | 800625 | 0 | TBD | 0% | 0% | 0 | 0 | 0
1 | 18-021-RSH | Rusk State Hospital | Building Renovations | ESF (other) | 3990000 | 349650 | TBD | 100% | 0% | 276315 | 73335 | 0
1 | 18-022-SAH | San Antonio State Hospital | Fire Sprinkler, Alarm System & Smoke Partitions | ESF (other) | 2327495.1 | 2216662 | TBD | 100% | 0% | 95196.8 | 121141.2 | 2000324
1 | 18-023-TSH | Terrell State Hospital | Anti-ligature Renovations | ESF (other) | 5640640.43 | 5372039 |  | 100% | 0% | 176980.83 | 296375.37 | 4898682.8
1 | 18-024-TSH | Terrell State Hospital | EMS Upgrade & HVAC Replacements | ESF (other) | 2824185 | 2689700 | TBD | 100% | 0% | 126523.2 | 71005.8 | 2492171
1 | 18-025-TSH | Terrell State Hospital | Roof Replacements | ESF (other) | 2100000 | 2000000 | TBD | 100% | 0% | 64395.9 | 78706.1 | 1856898
1 | 18-026-WCY | Waco Center for Youth | Replace Fire Alarm System | ESF (other) | 712358.33 | 678437 | TBD | 100% | 0% | 58823.4 | 10380.6 | 609233
1 | 18-027-WCY | Waco Center for Youth | Anti-Ligature & Emergency Generator | ESF (other) | 581670.33 | 553971 | TBD | 100% | 0% | 31016 | 7754 | 515201
1 | 18-028-SH | Various Hospitals | System Wide CSI Remediation | ESF (other) | 5228854 | 1136914.24 | TBD | 100% | 78.59% | 241903.45 | 893495.98 | 1514.81
1 | 18-029-SH | Various Hospitals | System Wide Anti Ligature Remediation | ESF (other) | 3039179.7975 | 1818225.64 | TBD | 0% | 0% | 0 | 0 | 1818225.64
1 | 18-030-RSH | Rusk State Hospital | Boiler and Canopy Replacement | ESF (other) | 0 | 14200 | TBD | 100% | 100% | 0 | 14200 | 0
1 | 18-032-SAH | San Antonio State Hospital | Chiller Replacement | ESF (other) | 0 | 103800 | TBD | 100% | 100% | 0 | 103800 | 0
1 | 18-031-ASH | Austin State Hospital | Main Switch Gear Replacement | ESF (other) | 0 | 37566 | TBD | 100% | 100% | 0 | 37566 | 0
| 18-041-RSC | Rio Grande State Center | Emergency HVAC Replacement | ESF (other) | 0 | 44137.03 | TBD | 100% | 0% | 0 | 0 | 44137.03
| 18-040-SH | Various Hospitals | Legionella Water Management Plan | ESF (other) | 0 | 454588 | TBD | 100% | 0% | 0 | 0 | 454588
| 18-043-ASH | Austin State Hospital | Emergency Freezer Repair | ESF (other) | 0 | 26931 | TBD | 100% | 0% | 0 | 0 | 26931
| 18-042-RSH | Rusk State Hospital | New Administration Building | ESF (other) | 0 | 7200000 | TBD | 25% | 0% | 681750 | 0 | 6518250
| 18-029-KSH | Kerrville State Hospital | Anti-Ligature | ESF (other) | 0 |  | TBD | 50% | 0% | 0 | 0 | 0
| 18-029-EPC | El Paso Psychiatric Center | Anti-Ligature | ESF (other) | 0 |  | TBD | 50% | 0% | 0 | 0 | 0
| HHSC/WCY | Various Hospitals | Transfer Fund | ESF (other) | 0 | 2823574.38 | N/A | 0% | 0% | N/A | N/A | 2823574.38
|  |  |  | Totals: | 79999999.6575 | 78959790.94 |  |  |  | 4101421.8 | 4196473.21 | 70661895.93
GO Bond | 16-032-WCY | Waco Center for Youth | Gym Floor and Ceiling Replacement | ESF (other) | 0 | 15566 |  | 100% | 100% | 0 | 15566 | 0
GO Bond | 14-005-BSH | Big Spring State Hospital | Air Conditioning System Replacement Bldg. 503 | ESF (other) | 0 | 4788 |  | 100% | 58.23% | 2000.01 | 2787.99 | 0
GO Bond | 16-028-TSH | Terrell State Hospital | HVAC System Replacement | ESF (other) | 0 | 903065.16 |  | 100% | 0% | 0 | 0 | 903065.16
GO Bond | 16-029-TSH | Terrell State Hospital | HVAC System Replacement | ESF (other) | 0 | 105110.28 |  | 100% | 56.6% | 9987.96 | 59488.31 | 35634.01
GO Bond | 17-019-RSH | Rusk State Hospital | Condensing Rack Replacement | ESF (other) | 0 | 10858 |  | 100% | 100% | 0 | 10858 | 0
GO Bond | 16-007-BSH | Big Spring State Hospital | Electrical System Upgrade & Replacement | ESF (other) | 0 | 821.62 |  | 100% | 100% | 0 | 821.62 | 0
|  |  |  | Totals: | 0 | 1040209.06 |  |  |  | 11987.97 | 89521.92 | 938699.17
|  |  |  | Grand Totals: | 79999999.6575 | 80000000 |  |  |  | 4113409.77 | 4285995.13 | 71600595.1
Note on G39: Muli,Stanley (HHSC): Add up all the 18 -028 projects
Note on G50: Muli,Stanley (HHSC): Add up all holding accts for HHSC and WCY bqlqnces.
Note on M50: Muli,Stanley (HHSC): Add up all holding accts for HHSC and WCY bqlqnces.

## HHSC-SSLC
| Agency: | HHSC 529 State Supported Living Centers
| Date: | 2018-11-30
| Prepared by: | HHSC State-Operated Facilities Division - Facilities Support Services
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 18-101-ABL | Abilene State Supported Living Center | Exterior Building Renovations, Roofing & Masterlock Replacement | ESF (other) | 4575102 | 4357240 | TBD | 100% | 0% | 91227 | 167573 | 4098440
1 | 18-103-ABL | Abilene State Supported Living Center | HVAC System Replacement | ESF (other) | 488927.25 | 465645 | TBD | 100% | 0% | 0 | 0 | 465645
1 | 18-104-ABL | Abilene State Supported Living Center | Walk-In Coolers / Freezer Replacement | ESF (other) | 209699.7 | 199715 | TBD | 100% | 0% | 0 | 0 | 199715
1 | 18-105-ABL | Abilene State Supported Living Center | Steam Heating Replacement | ESF (other) | 1108191 | 1055420 | TBD | 100% | 0% | 80325 | 24675 | 950420
1 | 18-106-AUL | Austin State Supported Living Center | Water Drainage Remediation | ESF (other) | 637767.69 | 607398 | TBD | 50% | 0% | 0 | 0 | 607398
1 | 18-107-AUL | Austin State Supported Living Center | Windows Replacement | ESF (other) | 7370171.42 | 7019211 | TBD | 100% | 0% | 336163.2 | 267048.8 | 6415999
1 | 18-108-AUL | Austin State Supported Living Center | Water Lines Replacement, HVAC Repair, and Generator Installation | ESF (other) | 1843079.7 | 1755314 | TBD | 50% | 0% | 162000 | 0 | 1593314
1 | 18-109-AUL | Austin State Supported Living Center | Roof Repair and Replacement | ESF (other) | 439531.93 | 418602 | TBD | 100% | 0% | 7600 | 0 | 411002
1 | 18-110-BLC | Brenham State Supported Living Center | Building Renovations and Sanitary Sewer Lines Replacement | ESF (other) | 8004522.35 | 7262755 | TBD | 50% | 0% | 240400 | 0 | 7022355
1 | 18-111-BLC | Brenham State Supported Living Center | Water Distribution Replacement and Water Tank Repair | ESF (other) | 410447.87 | 390903 | TBD | 100% | 0% | 47330 | 5970 | 337603
1 | 18-112-BLC | Brenham State Supported Living Center | Roof Repair and Replacement | ESF (other) | 684809.72 | 652200 | TBD | 100% | 0% | 40848 | 0 | 611352
1 | 18-113-CLC | Corpus Christi State Supported Living Center | HVAC, Emergency Generator Replacement, and Masterlock Replacement | ESF (other) | 1938369.3 | 1846066 | TBD | 100% | 0% | 73588.5 | 89941.5 | 1682536
1 | 18-114-CLC | Corpus Christi State Supported Living Center | Walkway and ADA Improvements | ESF (other) | 693300.3 | 721897 | TBD | 100% | 0% | 17873.4 | 37828.6 | 666195
1 | 18-115-DLC | Denton State Supported Living Center | Boiler Replacements, Electrical Panels, HVAC and Controls Replacement | ESF (other) | 8279550.72 | 7885286 | TBD | 100% | 0% | 99848 | 195972 | 7589466
1 | 18-116-DLC | Denton State Supported Living Center | Roof Replacements | ESF (other) | 2036160 | 1939200 | TBD | 100% | 0% | 69085.35 | 84437.65 | 1785677
1 | 18-117-ELC | El Paso State Supported Living Center | Site Electrical and Water Distribution Replacement | ESF (other) | 339897.05 | 583711 | TBD | 100% | 0% | 49182.7 | 8679.3 | 525849
1 | 18-118-ELC | El Paso State Supported Living Center | Building and Patio Renovations | ESF (other) | 2414869.58 | 2299876 | TBD | 100% | 0% | 82838.7 | 101247.3 | 2115790
1 | 18-119-LBL | Lubbock State Supported Living Center | HVAC, Plumbing Renovations, and Ceiling Replacement | ESF (other) | 8888758.2 | 8465484 | TBD | 100% | 0% | 401088.57 | 267392.38 | 7797003.05
1 | 18-120-LFL | Lufkin State Supported Living Center | Bathroom Renovations | ESF (other) | 2216025 | 2110500 | TBD | 100% | 0% | 128640 | 32360 | 1949500
1 | 18-121-LFL | Lufkin State Supported Living Center | Fuel Tank Installation | ESF (other) | 614775 | 585500 | TBD | 100% | 0% | 18244 | 27366 | 539890
1 | 18-122-LFL | Lufkin State Supported Living Center | Roof Repairs and Replacements | ESF (other) | 601125 | 572500 | TBD | 100% | 0% | 16666.7 | 25000.05 | 530833.25
1 | 18-123-MLC | Mexia State Supported Living Center | Emergency Generator, Vent Hood Fire Suppression and Boiler and Water System Replacement | ESF (other) | 3503004.88 | 3336195 | TBD | 100% | 0% | 99350 | 0 | 3236845
1 | 18-124-MLC | Mexia State Supported Living Center | Bathroom Renovation and Covered Walkway Replacement | ESF (other) | 3916470.9 | 3729972 | TBD | 100% | 0% | 179250 | 119500 | 3431222
1 | 18-125-RLC | Richmond State Supported Living Center | Window Replacement | ESF (other) | 908302.08 | 865050 | TBD | 100% | 0% | 57400 | 0 | 807650
1 | 18-126-RLC | Richmond State Supported Living Center | Sanitary Sewer Line Replacement | ESF (other) | 2588906.41 | 2271070 | TBD | 75% | 0% | 0 | 0 | 2271070
1 | 18-127-RLC | Richmond State Supported Living Center | Cooling Tower and Chiller Replacement | ESF (other) | 796524.77 | 758595 | TBD | 75% | 0% | 0 | 0 | 758595
1 | 18-128-RLC | Richmond State Supported Living Center | Roof Repairs and Replacements | ESF (other) | 4210107.36 | 0 | TBD | 0% | 0% | 0 | 0 | 0
1 | 18-129-SGL | San Angelo State Supported Living Center | Bathroom Renovations | ESF (other) | 2924250 | 2785000 | TBD | 75% | 0% | 172055.2 | 43103.8 | 2569841
1 | 18-130-SGL | San Angelo State Supported Living Center | Roof Repairs and Replacements | ESF (other) | 1010609.25 | 962485 | TBD | 100% | 0% | 50569.34 | 43999.34 | 867916.32
1 | 18-131-SGL | San Angelo State Supported Living Center | Emergency Generators & Mechanical System Upgrade | ESF (other) | 1640730 | 1562600 | TBD | 100% | 0% | 50949 | 62271 | 1449380
1 | 18-132-SAL | San Antonio State Supported Living Center | Exterior Building Renovation and Emergency Generator Installation | ESF (other) | 637838.25 | 607465 | TBD | 100% | 0% | 36000 | 24000 | 547465
1 | 18-133-SAL | San Antonio State Supported Living Center | Sanitary Sewer Line Replacement | ESF (other) | 1607713 | 1531156 | TBD | 100% | 0% | 60686.71 | 3194.04 | 1467275.25
1 | 18-134-SGL | San Angelo State Supported Living Center | Chiller Controls | ESF (other) | 70400 | 70400 | TBD | 100% | 100% | 0 | 70400 | 0
1 | 18-135-DLC | Denton State Supported Living Center | New Guardhouse | ESF (other) | 192200 | 292200 | TBD | 100% | 0% | 0 | 0 | 292200
1 | 18-136-DLC | Denton State Supported Living Center | Climate Control Retrofit | ESF (other) | 217680 | 217680 | TBD | 100% | 0% | 0 | 0 | 217680
1 | 18-137-SAL | San Antonio State Supported Living Center | Chiller Replacement | ESF (other) | 121605 | 121605 | TBD | 100% | 100% | 0 | 121605 | 0
1 | 18-145-ABL | San Antonio State Supported Living Center | Chiller Replacement | ESF (other) | 26672 | 26672 | TBD | 100% | 100% | 0 | 26672 | 0
1 | 18-146-AUL | San Antonio State Supported Living Center | Chiller Replacement | ESF (other) | 80993.37 | 80993.37 | TBD | 100% | 100% | 0 | 80993.37 | 0
1 | 18-147-ELC | San Antonio State Supported Living Center | Chiller Replacement | ESF (other) | 164500 | 164500 | TBD | 100% | 40% | 98704 | 65796 | 0
| 18-150-MLC | Mexia State Supported Living Center | Sewer Treatment Repairs Emergency Project |  | 0 | 40000 | TBD | 100% | 0% | 0 | 0 | 40000
| 18-149-SSLC | Various Facilities | Legionella Water Management Plan |  | 0 | 610000 | TBD | 100% | 0% | 0 | 0 | 610000
| 18-148-AUL | Austin State Supported Living Center | Emergency Electrical Transformer |  | 0 | 59657.13 | TBD | 100% | 0% | 59657 | 0 | 0.13
| 18-044-RSC | Rio Grande State Center | HVAC Replacement |  | 0 | 36600 | TBD | 100% | 0% | 0 | 0 | 36600
| 18-151-AUL | Austin State Supported Living Center | Remediation |  | 0 | 382328.44 | TBD | 100% | 0% | 0 | 0 | 382328.44
| HHSC | Various Facilities | Transfer Fund |  | 0 | 6706941.42 | N/A | 0% | 0% | 0 | 0 | 6706941.42
|  |  | Totals: |  | 78413588.05 | 78413588.36 |  |  |  | 2827570.37 | 1997026.13 | 73588991.86
GO Bond | 10-097-MSS | Mexia State Supported Living Center | Men and Women Forensic Units | ESF (other) | 37885.85 | 37885.85 | TBD | 100% | 95% | 37885.85 | 0 | 0
GO Bond | 14-054-LFS | Lufkin State Supported Living Center | Life Safety and ADA Renovations Project Increase Request | ESF (other) | 10038.79 | 10038.79 | TBD | 100% | 100% | 0 | 10038.79 | 0
GO Bond | 16-061-SAS | San Antonio State Supported Living Center | Grease Trap Relocation | ESF (other) | 97237 | 97237 | TBD | 100% | 100% | 0 | 97237 | 0
GO Bond | 17-018-LFS | Lufkin State Supported Living Center | Grease Trap Relocation | ESF (other) | 41250 | 41250 | TBD | 100% | 100% | 0 | 41250 | 0
|  |  | Totals: |  | 186411.64 | 186411.64 |  |  |  | 37885.85 | 148525.79 | 0
|  |  | Grand Total: |  | 78599999.69 | 78600000 |  |  |  | 2865456.22 | 2145551.92 | 73588991.86